- Section 3.0 Equipment List - Detailed Division of Responsibility

| Material/Responsibility | Qty | Description |
| --- | --- | --- |
| Owner | 1 Lot | Removal of all unused building foundations, underground piping, etc. on the proposed project site |
|  | 1 Lot | Natural Gas Pipeline and supply metered at inter-tie point within 50’ of Plant Boundary |
|  | 3 | 100 % Fuel Gas Compressors |
|  | 1 Lot | Fuel Gas and Liquid Fuel for Commissioning / Start-up that meets P&W Fuel Specifications |
|  | 1 Lot | Liquid Fuel Treatment System |
|  | 1 Lot | Raw Water Supply to site boundary |
|  | 1 Lot | Raw Water for Commissioning and Startup |
|  | 1 Lot | Waste Water and Waste Oil Truck Removal |
|  | 1 Lot | Permits for Environmental, Importation, Transportation, Building, Operations, etc. to allow plant construction and commercial operations |
|  | 1 Lot | Construction Commissioning 480V three phase power |
|  | 1 Lot | Access Roads to site |
|  | 1 Lot | Any required Electric Utility 230 KVTie-In interconnect to the Utility |
|  | 1 Lot | Import Duties and Taxes |
|  | I Lot | Construction lay down area as available on the existing site |
|  | 1 lot | Right of Way, easements, etc. to allow proposed interconnects as required |
|  |  | Gas Turbine Generator |
|  | 3 | Pratt & Whitney FT8-3 SwiftPac (60Hz) Dual Fueled Gas Turbine Generator packages |
|  | 6 | Exhaust Stacks with Silencers |
|  | 3 | Modular Control Buildings with: |
|  |  | -Turbine Control Panel |
|  |  | - Generator Control Panel and Protection Panel |
|  |  | - 24 VDC Batteries and Chargers |
|  |  | - 125 VDC Batteries and Chargers |
|  |  | - 125 VDC Rundown motor starter |
|  |  | - 13.8 KV Generator Breaker Nema 3R |
|  |  | - GTG 480 V MCC |
|  | 1 | 350 KW Black Start Generator |
|  | 3 | 13.8 KV to 230 KV GSU Transformers , 90MVA |
|  | 1 | Water Treatment consisting of Multi-Media filters and R.O. System |
| Contractor – Responsibility |  |  |
| Civil / Structural |  |  |
|  | 1 Lot | Site Soil Borings & Studies to design Foundations |
|  | 1 Lot | Site Preparation, Rough Grading, Excavation, final grading and fencing |
|  | 1 Lot | Temporary Power Distribution |
|  | 1 Lot | Plant Concrete Foundations |
|  | 1 Lot | Plant Paving, Gravel and Pads for the GTG Turbines and Generators |
|  | 1 Lot | Structural piping supports, platforms, ladders, and Misc structural steel supports. (Note: Platforms and ladders for the exhaust stacks to be furnished by Owner) |
|  | 1 Lot | Erection of the (3) Owner Furnished FT8 SwiftPac Gas Turbine Generators, Exhaust Stacks, Control Modules and associated accessories. |
| Material/Responsibility | Qty | Description |
| Contractor (continued) |  |  |
| Buildings |  |  |
|  | 1 | Demin Water Treatment & Forwarding Pump & Firewater pump Building |
|  | 1 | Gas Compressor shed |
|  | 1 | Liquid Fuel Treatment, Diesel Pump Shed. |
|  | 1 | Control Room and, Office Building. |
|  | 1 | Warehouse and Maintenance building |
|  | 1 | Water Treatment Building |
|  | 1 | Liquid Fuel Treatment Unloading Rack and Shed |
| Mechanical |  |  |
|  | 1 | Fuel Gas Plant ESD Valve |
|  | 1 | Fire Water System including pumps, controls, Loop, Monitors and Hydrants |
|  | 1 | 675,00 gallon raw water/firewater Carbon Steel Storage Tank |
|  | 1 | 275,000 stainless steel Demin Water Storage Tank |
|  | 3 | GTG Duplex Demin Water Filter Skids |
|  | 1 | Demineralized Water Treatment system (EDI) |
|  | 3 | Demin Water forwarding Pumps |
|  | 2 | Oily Water Separator |
|  | 1 | Waste Oil Tank 15,000 Gallon w/waste oil pump to Truck for disposal |
|  | 1 | Waste Water Tank 15,000 Gallon w/waste water pump to Truck for disposal |
|  | 2 | 675,000 gallon Carbon Steel raw liquid fuel storage tanks |
|  | 2 | 400,000 gallon Stainless Steel clean liquid fuel storage tanks |
|  | 2 | 100% capacity Liquid Fuel forwarding pumps |
|  | 3 sets | Duplex Liquid Fuel Filters |
|  | 1 Lot | Pipe, Valves and Fittings with Insulation as required |
|  | 1 Lot | Mechanical Labor |
| Electrical |  |  |
|  | 2 | 13.8 KV Fused Disconnects (Station Service) NEMA 3R |
|  | 1 | 13.8 KV/4160 V 2000 KVA Fuel Gas Compressor |
|  | 2 | 13.8 KV/480 V 750 KVA Transformers |
|  | 1 | 4160 V MCC for Fuel Gas Compressor |
|  | 1 | 480 V Distribution Switch board |
|  | 1 | 480 V BOP MCC |
|  | 1 Lot | BOP 480/220 V Transformers, Lights, Panels etc |
|  | 1 | 120 V UPS System for Control Room |
|  | 1 | Plant Grounding Grid |
|  | 1 Lot | Lightning Protection 50 lux |
|  | 1 Lot | Cathodic Protection for underground steel piping |
|  | 1 Lot | Area Lighting |
|  | 1 Lot | 480 V Welding Receptacles |
|  | 1 Lot | Electrical Labor |
|  | 1 Lot | Local Subcontractor(s) Civil, Electrical & Mechanical Craft Labor |
| Material/Responsibility | Qty | Description |
| Contractor (continued) |  |  |
| Instrumentation & Control |  |  |
|  | 1 Lot | Plant Instrumentation |
|  | 1 | Remote DCS PLC |
|  | 1 Lot | I&C Installation and Construction |
| Construction |  |  |
|  | 1 Lot | Major Equipment Erection |
|  | 1 Lot | Mechanical Installation and Construction |
|  | 1 Lot | Construction Tools, Rental Equipment & Rental Cranes |
|  | 1 Lot | Lubricants, Chemicals, Filters, etc. for Plant Commissioning |
|  |  | and Start up |
|  | 1 Lot | Balance of Plant Start up and Commissioning Spare Parts |
|  | 1 Lot | Transportation of all BOP Equipment to site |
|  | 1 Lot | Plant Commissioning and Performance Testing |
|  | 1 Lot | Overall Plant Training |
| Engineering |  |  |
|  | 1 Lot | Conceptual and Detail Design engineering (Total Plant) |
|  | 1 Lot | Project Manuals including O&M, Warranty, and Engineering Calculations |
|  | 1 Lot | As Built Drawings |
|  | 1 Lot | Recommended Vendor Spare Parts List |
| Project Management |  |  |
|  | 1 Lot | Project Management with QA/QC, Safety, and Training |
|  | 1 Lot | Construction Permits |
|  | 1 Lot | Local Business Taxes |
|  | 1 Lot | Project manuals including project procedures, Systems Turnover Manuals, project implementation, QA/QC, safety and training |
|  | 1 lot | Training of Operators for the FT8 Generators and BOP |