La Raisa LM6000 Plant

Project Progress Payment Schedule

US $		BsF

Down Payment Due Upon Contract Signing			  50%		30%

Milestone 1

Civil Works

Site Preparation Complete

Gas Turbine Foundations Poured for equipment			   10%		20%

Milestone 2

Gas Turbines Set on Foundations				   10%		 20%

Milestone 3

Gas Turbines, 							 15%		15%

Assembly of Major Gas Turbines

Modules Complete, Exhaust Stacks Erected

Milestone 4

Pre commissioning Complete					    10%		10%

All Mechanical Equipment Flushed and Checked

All Hydrostatic Testing Complete

All Pumps Rotated and Tested

All Mechanical Systems Ready for Startup

All Electrical Equipment Statically Tested

All Electrical Systems Read for Startup

Milestone 5

Commissioning & Testing Complete				    5%		    5%

Gas Turbines Tested and Ready for Commercial Operation

All Mechanical Auxillary Ready for Commercial Operation

All Electrical Auxiliary Equipment Tested and Ready for

Commercial Operation