## Sheet1
TACOA - Acceleration cost
The real concern is the local labor working the month of December. In order to make the February schedule we must have
a full crew working over the holidays.
US Dollars Cost
| Number of Staff | Number of Days | Rate Per Day | Total Cost
Mechanical Labor | 10 | 30 | 750 | 225000
Electrical Labor | 8 | 30 | 750 | 180000
Technicians | 6 | 30 | 750 | 135000
Engineering | 2 | 30 | 1100 | 66000
Expediting of Equipment Purchase |  |  |  | 60000
|  |  | Total USD | 666000
Bs Cost
Additional local labor | 12 | 45 | 1585 | 855900
Additional equipment | 3 | 45 | 1500 | 202500
Hotel and expenses for US Labor | 26 | 30 | 1100 | 858000
|  |  | Total BS | 1916400