## CO Log
CHANGE ORDER LOG
Project Name: | LaRaisa Power Plant
Project Number: | T-9018
Client: | Derwick Associates
Revision Date: | 2010-11-15
Change Order Number | Date Submitted | Description | Type | Portion in VEBF's | Portion in USD
T-9018-CO-001 | June | Gas Pipe Line from header arrangement to Single line | Fixed Price | 382578 | 109711
T-9018-CO-002 | June | Client request no underground piping. Move all piping above grade | Fixed Price | 3600859 | 312188
T-9018-CO-003 | June | Removal of spoils from site trash and garbage | Fixed Price | 0
T-9018-CO-004 | Sept. 09 | Client requested 15Kv disconnect switches be changed to 15 Kv draw-out breakers | Fixed Price | 0 | 896210
T-9018-CO-005 | Sept. 09 | Client requested 5Kv disconnects switches be changed to 5Kv draw-out breakers | Fixed Price | 0 | 773180
T-9018-CO-006 | Sept. 10 | Change Fire system from HDPE to Carbon Steel | Fixed Price | 686328 | 208200
T-9018-CO-006 | Sept. 09 | Add Nema 3R fused disconnect switch on P&W units | Fixed Price | 0 | 0
T-9018-CO-007 | Sept. 09 | Add fire water deluge system to GSU | Fixed Price | 237781 | 290149
T-9018-CO-008 |  | Clear and Level site and remove spoils | Fixed Price | 817000
T-9018-CO-009 |  | Change of the original high voltage CT in switch yard | Fixed Price | 1965673
T-9018-CO-010 | Revise | Storage tank paint and blasting | Fixed Price | 0
T-9018-CO-011 | Sept. 10 | Crane lease | Fixed Price | 60000
T-9018-CO-012 | Sept. 10 | Refill of 48 Co2 bottles for P&W | Fixed Price | 107520
T-9018-CO-013 |  | GTG expoxy / grout for anchor bolts | Fixed Price | 124763
T-9018-CO-015 | Sept. 10 | Delays and changes incurred during the transformer dress-out. | Fixed Price | 1485629 | 477410
T-9018-CO-23 | Sept. 10 | Accelleration and extra work | T&M | 3292200 | 2317284
|  | Subtotal |  | 12760331 | 5384332
Work not started pending approval
T-9018-CO-014 | Sept. 10 | Prepare interface engineering for client substation |  |  | 76781
T-9018-CO-016 | Sept. 10 | Install grating over the open containment areas of the GSU | Fixed Price | 2900000 | 0
T-9018-CO-017 |  | Engineering changes and bridge crossing | Fixed Price | 4270050 | 1114493
T-9018-CO-018 | Client deleted request | Structural removal for main control room construction | Fixed Price | 0 | 0
T-9018-CO-019 | Sept. 10 | Intregrate Phase II and Phase III into Phase I DCS | Fixed Price | 673684 | 1842818
T-9018-CO-20 |  | Engineering and construct of substation drainage | Fixed Price | 2500000 | 250000
Subtotal: |  |  |  | 10343734 | 3207311
Total |  | Total |  | 23104065 | 8591643
Current Status Legend:
| Approved | Client has approved Change Order. PES to proceed with scope.
| Rejected - Resubmit | Client has rejected change order. PES to resubmit with additional support
| Rejected - Withdrawn | Client has rejected change order. PES to perform work, will not resubmit Change Order.
| Rejected - Do Not Proceed | Client has instructed ProEnergy not to perform this scope
| Submitted | Change Order is in Client's hands for approval
| Pending | PES is preparing Change Order
| Variance | PES has identified a potential Change Order scope for internal review. Not yet on Change Order Paper