## LM2500 Milestone Schedule
TACOA LM2500 Project Progress Payment Schedule # 10-T9003A | [9 empty] | TACOA LM2500 Project Progress Payment Schedule # 10-T9003A
Contract Amount | [9 empty] | Contract Amount
US$ | [9 empty] | Bs$
12536000 |  |  | Invoice Amount | [6 empty] | 10218950 |  |  | Invoice Amount
US Payment Milestones |  |  | US Dollars | [6 empty] | Local Payment Milestones |  |  | Bolivars | [6 empty] | Days
| Total Unit 1 & 2 | Inv # | Unit 1 | Date | Amt | Inv # | Unit 2 | Date | Amt |  | Total Unit 1 & 2 | Inv # | Unit 1 | Date | Amt | Inv # | Unit 2 | Date | Amt
Down Payment | 4387600 | 1-DP-U1 | 17.5% | 2009-07-01 | 2193800 | 2-DP-U2 | 17.5% | 2009-07-01 | 2193800 | Down Payment | 1021895 | 1-DP-U1 | 5% | 2009-07-01 | 510947.5 | 2-DP-U2 | 5% | 2009-07-01 | 510947.5 | 0
|  | 100147 |  | 2009-07-31 |  | 100148 |  | 2009-07-31
Milestone 1 (Civil Works & Conceptual Engineering) | [9 empty] | Milestone 1 (Civil Works & Conceptual Engineering)
Conceptual Engineering | 501440 | 3-M1A-U1 | 2% | 2009-08-15 | 250720 | 4-M1A-U2 | 2% | 2009-08-15 | 250720 | Civil Works
Project Procedures Manual Issued |  | 100152 |  | 2009-08-18 |  | 100153 |  | 2009-08-18 |  | Mobilization to Site | 510947.5 | 3-M1A-U1 | 2.5% | 2009-08-15 | 255473.75 | 4-M1A-U2 | 2.5% | 2009-08-15 | 255473.75
Site Plot Plan | [9 empty] | Site Preparation Complete | 510947.5 | 5-M1B-U1 | 2.5% | 2009-08-15 | 255473.75 | 6-M1B-U2 | 2.5% | 2009-08-15 | 255473.75
Process Flow Diagram | [9 empty] | Site Excavation Complete | 306568.5 | 7-M1C-U1 | 1.5% | 2009-08-15 | 153284.25 | 8-M1C-U2 | 1.5% | 2009-08-15 | 153284.25
Electrical One Line Drawings | [9 empty] | Foundation Steel on Site | 204379 | 9-M1D-U1 | 1% | 2009-08-15 | 102189.5 | 10-M1D-U2 | 1% | 2009-08-15 | 102189.5
Major Equipment PO's Issued | 752160 | 5-M1B-U1 | 3% | 2009-08-15 | 376080 | 6-M1B-U2 | 3% | 2009-08-15 | 376080 | Gas Turbine Foundation Forms Set | 204379 | 11-M1E-U1 | 1% | 2009-08-15 | 102189.5 | 12-M1E-U2 | 1% | 2009-08-15 | 102189.5
|  | 100154 |  | 2009-08-18 |  | 100155 |  | 2009-08-18 |  | Gas Turbine Foundation Ready to Pour Concrete | 306568.5 | 13-M1F-U1 | 1.5% | 2009-08-15 | 153284.25 | 14-M1F-U2 | 1.5% | 2009-08-15 | 153284.25
[10 empty] | Concrete Poured in Gas Turbine Foundations | 510947.5 | 15-M1G-U1 | 2.5% | 2009-08-15 | 255473.75 | 16-M1G-U2 | 2.5% | 2009-08-15 | 255473.75
Total for Milestone 1 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 1 | 2554737.5 |  | 12.5% |  |  |  | 12.5% |  |  | 45
Milestone 2 (Gas Turbines Set on Foundations) | [9 empty] | Milestone 2 (Gas Turbines Set on Foundations)
Engineering 30% Review | 501440 | 7-M2A-U1 | 2% | 2009-09-09 | 250720 | 8-M2A-U2 | 2% | 2009-09-09 | 250720 | Gas Turbine Packages Set on Foundations | 613137 | 17-M2A-U1 | 3% | 2009-09-09 | 306568.5 | 18-M2A-U2 | 3% | 2009-09-09 | 306568.5
|  | 100170 |  | 2009-09-17 |  | 100171 |  | 2009-09-17
Mechanical Bulk Material Purchased | 376080 | 9-M2B-U1 | 1.5% | 2009-09-09 | 188040 | 10-M2B-U2 | 1.5% | 2009-09-09 | 188040 | Mechanical Contractor Mobilized to Site | 204379 | 19-M2B-U1 | 1% | 2009-09-09 | 102189.5 | 20-M2B-U2 | 1% | 2009-09-09 | 102189.5
|  | 100172 |  | 2009-09-17 |  | 100173 |  | 2009-09-17
Electrical Bulk Material Purchased | 376080 | 11-M2C-U1 | 1.5% | 2009-09-09 | 188040 | 12-M2C-U2 | 1.5% | 2009-09-09 | 188040 | Electrical Contractor Mobilized to Site | 204379 | 21-M2C-U1 | 1% | 2009-09-09 | 102189.5 | 22-M2C-U2 | 1% | 2009-09-09 | 102189.5
|  | 100174 |  | 2009-09-17 |  | 100175 |  | 2009-09-17
Total for Milestone 2 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 2 | 1021895 |  | 5% |  |  |  | 5% |  |  | 68
Milestone 3 (Gas Turbine Package Erection) | [9 empty] | Milestone 3 (Gas Turbine Package Erection)
Engineering 60% Review | 125360 | 13-M3A-U1 | 0.5% | 2009-10-07 | 62680 | 14-M3A-U2 | 0.5% | 2009-10-07 | 62680 | Gas Turbine Package Erection Complete | 1021895 | 23-M3A-U1 | 5% | 2009-10-07 | 510947.5 | 24-M3A-U2 | 5% | 2009-10-07 | 510947.5
Engineering 90% Review | 125360 | 15-M3B-U1 | 0.5% | 2009-10-07 | 62680 | 16-M3B-U2 | 0.5% | 2009-10-07 | 62680 | Exhaust Stack Erection Complete | 204379 | 25-M3B-U1 | 1% | 2009-10-07 | 102189.5 | 26-M3B-U2 | 1% | 2009-10-07 | 102189.5
Shipment of Major BOP Equipment | 501440 | 17-M3C-U1 | 2% | 2009-10-07 | 250720 | 18-M3C-U2 | 2% | 2009-10-07 | 250720 | Complete BOP Foundations | 306568.5 | 27-M3C-U1 | 1.5% | 2009-10-07 | 153284.25 | 28-M3C-U2 | 1.5% | 2009-10-07 | 153284.25
Shipment of BOP Bulk Material | 501440 | 19-M3D-U1 | 2% | 2009-10-07 | 250720 | 20-M3D-U2 | 2% | 2009-10-07 | 250720
Total for Milestone 3 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 3 | 1532842.5 |  | 7.5% |  |  |  | 7.5% |  |  | 99
Milestone 4 (Mechanical Completion) | [9 empty] | Milestone 4 (Mechanical Completion)
Mechanical Engineering Complete | 250720 | 21-M4A-U1 | 1% | 2009-11-09 | 125360 | 22-M4A-U2 | 1% | 2009-11-09 | 125360 | Set Gas Compressors on Foundations | 408758 | 29-M4A-U1 | 2% | 2009-11-09 | 204379 | 30-M4A-U2 | 2% | 2009-11-09 | 204379
Project Manuals Complete | 376080 | 23-M4B-U1 | 1.5% | 2009-11-09 | 188040 | 24-M4B-U2 | 1.5% | 2009-11-09 | 188040 | Erect Water Treatment Equipment | 306568.5 | 31-M4B-U1 | 1.5% | 2009-11-09 | 153284.25 | 32-M4B-U2 | 1.5% | 2009-11-09 | 153284.25
Mobilize Tech Representatives from US | 626800 | 25-M4C-U1 | 2.5% | 2009-11-09 | 313400 | 26-M4C-U2 | 2.5% | 2009-11-09 | 313400 | Interconnect Piping Installed | 306568.5 | 33-M4C-U1 | 1.5% | 2009-11-09 | 153284.25 | 34-M4C-U2 | 1.5% | 2009-11-09 | 153284.25
Total for Milestone 4 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 4 | 1021895 |  | 5% |  |  |  | 5% |  |  | 131
Milestone 5 (Electrical Completion) | [9 empty] | Milestone 5 (Electrical Completion)
Electrical Engineering | 250720 | 27-M5A-U1 | 1% | 2009-11-09 | 125360 | 28-M5A-U2 | 1% | 2009-11-09 | 125360 | Electrical BOP Equipment Installed | 204379 | 35-M5A-U1 | 1% | 2009-11-09 | 102189.5 | 36-M5A-U2 | 1% | 2009-11-09 | 102189.5
Project Manuals | 376080 | 29-M5B-U1 | 1.5% | 2009-11-09 | 188040 | 30-M5B-U2 | 1.5% | 2009-11-09 | 188040 | Electrical BOP Interconnect Cabling Installed | 408758 | 37-M5B-U1 | 2% | 2009-11-09 | 204379 | 38-M5B-U2 | 2% | 2009-11-09 | 204379
Project Management | 626800 | 31-M5C-U1 | 2.5% | 2009-11-09 | 313400 | 32-M5C-U2 | 2.5% | 2009-11-09 | 313400 | 69KV Transmission Relocation Complete | 408758 | 39-M5C-U1 | 2% | 2009-11-09 | 204379 | 40-M5C-U2 | 2% | 2009-11-09 | 204379
Total for Milestone 5 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 5 | 1021895 |  | 5% |  |  |  | 5% |  |  | 131
Milestone 6 (Precommissioning Complete) | [9 empty] | Milestone 6 (Precommissioning Complete)
Mobilize Precommissioning Techs from US | 501440 | 33-M6A-U1 | 2% | 2009-12-12 | 250720 | 34-M6A-U2 | 2% | 2009-12-12 | 250720 | Mechanical Equipment Flushed and Checked | 408758 | 41-M6A-U1 | 2% | 2009-12-12 | 204379 | 42-M6A-U2 | 2% | 2009-12-12 | 204379
Electrical Engineering Complete | 250720 | 35-M6B-U1 | 1% | 2009-12-12 | 125360 | 36-M6B-U2 | 1% | 2009-12-12 | 125360 | Hydrostatic Testing Complete | 204379 | 43-M6B-U1 | 1% | 2009-12-12 | 102189.5 | 44-M6B-U2 | 1% | 2009-12-12 | 102189.5
Mechanical Engineering Complete | 250720 | 37-M6C-U1 | 1% | 2009-12-12 | 125360 | 38-M6C-U2 | 1% | 2009-12-12 | 125360 | Pumps Rotated and Tested | 204379 | 45-M6C-U1 | 1% | 2009-12-12 | 102189.5 | 46-M6C-U2 | 1% | 2009-12-12 | 102189.5
Project Management | 250720 | 39-M6D-U1 | 1% | 2009-12-12 | 125360 | 40-M6D-U2 | 1% | 2009-12-12 | 125360 | Mechanical Systems Ready for Startup | 306568.5 | 47-M6D-U1 | 1.5% | 2009-12-12 | 153284.25 | 48-M6D-U2 | 1.5% | 2009-12-12 | 153284.25
[10 empty] | Electrical Equipment Statically Tested | 408758 | 49-M6E-U1 | 2% | 2009-12-12 | 204379 | 50-M6E-U2 | 2% | 2009-12-12 | 204379
Total for Milestone 6 | 1253600 |  | 5% |  |  |  | 5% |  |  | Total for Milestone 6 | 1532842.5 |  | 7.5% |  |  |  | 7.5% |  |  | 164
Milestone 7 (Plant Commissioning & Testing Complete) | [9 empty] | Milestone 7 (Plant Commissioning & Testing Complete)
Mobilize Test Technicians from US | 376080 | 41-M7A-U1 | 1.5% | 2010-01-15 | 188040 | 42-M7A-U2 | 1.5% | 2010-01-15 | 188040 | Gas Turbines Tested and Ready for Commercial Operation | 306568.5 | 51-M7A-U1 | 1.5% | 2010-01-15 | 153284.25 | 52-M7A-U2 | 1.5% | 2010-01-15 | 153284.25
Engineering As Built Drawings Complete | 125360 | 43-M7B-U1 | 0.5% | 2010-01-15 | 62680 | 44-M7B-U2 | 0.5% | 2010-01-15 | 62680 | Plant Equipment Ready for Commercial Operation | 102189.5 | 53-M7B-U1 | 0.5% | 2010-01-15 | 51094.75 | 54-M7B-U2 | 0.5% | 2010-01-15 | 51094.75
O&M Manuals Complete | 125360 | 45-M7C-U1 | 0.5% | 2010-01-15 | 62680 | 46-M7C-U2 | 0.5% | 2010-01-15 | 62680 | All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation | 102189.5 | 55-M7C-U1 | 0.5% | 2010-01-15 | 51094.75 | 56-M7C-U2 | 0.5% | 2010-01-15 | 51094.75
Total for Milestone 7 | 626800 |  | 2.5% |  |  |  | 2.5% |  |  | Total for Milestone 7 | 510947.5 |  | 2.5% |  |  |  | 2.5% |  |  | 180
Total US Dollar Payment | 12536000 |  | 50% |  | 6268000 |  | 50% |  | 6268000 | Total Bolivar Payments | 10218950 |  | 50% |  |  |  | 50%