- Summary

of

ProEnergy Response

to

EDC Statement on Contract Terms dated April 28, 2009

- Tacoa Project

Updated May 17, 2009

| 1 | Contract Structure | For tax reasons the main contract to be signed between EDC and Derwick. With respect to ProEnergy’s scope of work, Derwick and PES to sign one subcontract for onshore content and one subcontract for offshore content. Subcontracts will (i) include and reference the technical scope document (TSD)previously submitted by ProEnergy, (ii) conform to the terms of this Summary, and (iii) otherwise be in accordance with the contract draft previously submitted to Derwick by ProEnergy. EDC, Derwick and ProEnergy will also be required to sign a document which stipulates (i) all proceeds paid under the main contract be paid into an escrow account for the benefit of Derwick and ProEnergy and (ii) no changes to the main contract will be made without the prior consent of ProEnergy. |
| --- | --- | --- |
| 2 | Validity | ProEnergy’s price for its scope of work is subject to change in the event all contract agreements are not executed and the Advance Payments are received within 60 days from the date of the previously submitted ProEnergy proposal. |
| 3 | Bonds | Derwick will furnish and pay for all bonds required by EDC. ProEnergy will not be required to provide bonds or any other form of security under the subcontracts. |
| 4 | Insurance | ProEnergy will explore its ability to obtain Builders Risk Insurance. If such insurance is available ProEnergy will pay the first $150,000.00 of the cost and any excess cost will be paid by Derwick. Such insurance will be issued on terms reasonably acceptable to ProEnergy. If such insurance is unavailable and/or EDC chooses not to acquire said insurance on its own then the subcontracts will provide that ProEnergy will have no liability for any damage or loss to the facility or the equipment. |
| 5 | Currency | The payment under the onshore subcontract will be paid in Venz. currency and the payment under the offshore subcontract will be paid in U.S. currency. |
| 6 | Escalation | Not applicable. |
| 7 | Payment Terms | $U.S. BsF. 1. Advance Payment 35% 10% 2. Prepare Site for Foundations 10% 25% 3. GTGs on Foundations 5% 10% 4. Complete Assembly of GTGs 10% 15% 5. Mechanical and 6. Electrical Completion 20% 20% 7. Precommissioning 10% 15% 8. Plant Testing and Commissioning 10% 5% |
| 8 | Warranty Period | ProEnergy will warrant the LM2500 gas turbine units, all balance of plant equipment and all ProEnergy services performed under the subcontracts for a period of 12 months from Provisional Acceptance. Such warranty will be in accordance with the terms set for in the LM2500 equipment contracts and as otherwise stated in Article 11 in the contract draft previously submitted to Derwick by ProEnergy. No warranty is provided with respect to the LM6000 equipment and other auxiliary equipment purchased by EDC from other third parties. |
| 9 | Performance Guarantees Schedule Guarantee | ProEnergy / Derwick will guarantee kw output and Btu/Kwh (LHV) heat rate on each of the LM2500 GTGs as defined in the table below. No performance guarantees will be provided on the LM6000 GTG. Tests will be carried out with the LM2500 GTGs running on gas fuel meeting GE recommendations and the guaranties will be subject to and corrected for (i) the GE performance curve for the GTGs, (ii) ambient condition at the project site, (iii) net of any plant auxiliary loads, (iv) tested in accordance with PTC 46-1996 and PTC 19.1 or as otherwise agreed by ProEnergy, and (v) measurements will be taken at the output terminals of the generator. Guarantee Conditions: 80F; 78% RH; 100 ft (Design Conditions) Power – Gas Fuel, With Water Injection: 20,129 Kw at Generator Output Terminals Heat Rate – Gas Fuel, With Water Injection; 10,552.5 Btu/kWh (LHV) ProEnergy will guarantee that Provisional Acceptance of the facility will occur in accordance with the table below which is based on the number of days starting from the later of the signing of all of the contract agreements and receipt of the Advance Payments. The schedule will be extended day-for-day for each day of delay in ProEnergy receiving any payment under the subcontracts or for force majeure or any other delay in ProEnergy performing its work not due to its own fault. Guaranteed Completion Dates LM2500 Unit #1 – 180 days LM2500 Unit #2 – 195 days LM6000 PC Unit #1 – 200 days LM6000 PD Unit #2 – 215 days (Pre-Commissioning and Ready for GE Control Adjustments and supervision of First Fire) |
| 10 | Liquidated Damages Performance Guarantees Schedule Guarantee Bonus | US $ 500.00 per KW shortfall on each LM2500 GTG US $ 4,800.00 per Btu/Kwh overage on each LM2500 GTG (or the graduated schedule as proposed in the latest commercial summary sent out over the weekend.) Liquidated damages for performance guarantees capped at 10% of the aggregate subcontract price. US $ 4,000.00 per day, per unit (Days 1-15) US $ 6,000.00 per day, per unit (Days 16-30) US $ 8,000.00 per day, per unit (Days 31 +) Liquidated damages for schedule guarantee capped at 10% of the aggregate subcontract price. Note: Final Commissioning of the LM6000PD requires a GE representative at site to adjust the gas turbine control system. Contractor is not responsible for the cost of this representative, modifications to the GT Control or for delays as a result of the adjustments required to operate and test this unit. All liquidated damages for performance guarantees and schedule guarantee are capped at 15% of the aggregate subcontract price. An equivalent bonus structure (e.g. same amounts and caps) will be included in the subcontracts in the event Provisional Acceptance is achieved prior to the Schedule Guarantee and/or the performance of the LM2500 GTGs is better than the Performance Guarantees. |
| 11 | Minimum Performance Guarantees | 5.0% on both output and heat rate on each of the LM2500 GTGs. No minimum performance guarantees are provided on the LM6000 GTG. In the case performance fails to meet the minimum performance guarantees during the initial testing period then ProEnergy will have up to 90 additional days to correct and retest the equipment provided applicable schedule liquidated damages are paid. At the end of the 90 day period if the minimum performance guarantees are not met then ProEnergy will remove the defective equipment from the site and ProEnergy will refund the monies received with respect to the defective equipment. |
| 12 | Local Taxes | ProEnergy will be responsible for local municipal and income taxes assessed with respect to its scope of work. |
| 13 | Permits and Licenses | All permits and licenses will be obtained and paid for by either EDC or Derwick. |
| 14 and 15 | Customs Clearance; Import Duties, Fees and Taxes | EDC will be responsible for obtaining all customs clearance and for paying all import duties, fee and taxes. |
| 16 | Social Responsibility Tax | ProEnergy understands that a social responsibility tax based on 2.5% of the total contract value will be assessed with respect to its scope of work under the subcontracts provided the parties agree to no reduction in the contract price (e.g. see No. 21 below). The tax assessed on the US$ portion of the contract will be based on the official Bolivar to US$ exchange rate of 2.15 and the Owner will deduct this tax from the Bolivar portion of the payments only. |
| 17 | Applicable Law | ProEnergy agrees with Venz. law as the controlling law under the subcontracts. |
| 18 | Arbitration | ProEnergy agree that the site for arbitration shall be in Caracas Venz. and that Venz. law will be the governing law so long as it is stipulated that the International Chamber of Commerce (ICC) will be the institution carrying out the arbitration according to its rules of arbitration. |
| 19 | Limit of Liability | 50% of the aggregate subcontract price. |
| 20 | National Content | ProEnergy cannot agree on any stipulated percent of local content. |
| 21 | Contract Price Reduction | ProEnergy does not agree to any reduction to its contract price as previously quoted to the parties. |
| 22 | Payment Schedule | See No. 7 above. |
| 23 | Options | ProEnergy agrees that the previously quoted options will not be included as part of its work under the subcontracts. |
| 24 | Turnkey Scope of Supply | ProEnergy will perform its work and provide all services, equipment, parts, and material in accordance with its previously submitted technical scope document (TSD). The TSD will be attached to and reference in the subcontracts. With respect to the LM6000 GTG ProEnergy will perform the work in accordance with its TSD but makes no warranty whether such equipment is complete or otherwise will function or operate properly. |
| 25 | Site Conditions | Any adjustment to the contract price or schedule for unforeseen site conditions will be governed by Section 3.15 in the draft contract previously provided to Derwick by ProEnergy. |
| 26 | Wood Group Logo | ProEnergy fails to find any reference to Wood Group in its proposal but agrees to revise as necessary. |
| 27 | Project Schedule | See No. 9 above. |
| 28 | Painting of LM6000 Package | ProEnergy agrees to paint and place logos on the LM6000 GTG in similar fashion to the LM2500 GTGs. |
| 29 | Contract Finalization | ProEnergy agrees that all contract terms (including those summarized above) need to be resolved and agreed to as quickly as possible in order to finalize and sign the contracts. |