ENGINEERING, PROCUREMENT AND CONSTRUCTION SERVICES AGREEMENT

by and between

Electricidad de Caracas

as Owner

and

DERWICK – PROENERGY CONSORTIUM

as Contractor

Dated as of MAY __, 2009

TABLE OF CONTENTS

ARTICLE 1 DEFINITIONS AND CONSTRUCTION

1.1.	Definitions

1.2.	Rules of Construction

ARTICLE 2 RELATIONSHIP OF OWNER, CONTRACTOR AND SUBCONTRACTORS

2.1.	Status of Contractor

2.2.	Subcontractors

2.3.	Subcontract Provisions

ARTICLE 3 CONTRACTOR’S RESPONSIBILITIES

3.1.	Scope of Work

3.2.	Tools

3.3.	Compliance with Drawings

3.4.	Contractor’s Personnel and Labor Relations

3.5.	Governmental Authorization and Contractor Assistance

3.6.	Control of the Work

3.7.	Cleanup

3.8.	Safety and Emergencies

3.9.	Compliance with Applicable Laws

3.10	Books and Records

3.11	Taxes and Fees

3.12	Access and Inspections; Correction of Defects

3.13	Storage and Security

3.14.	Out of Scope Construction; Cooperation

3.15.	Hazardous Substances, Archaeological Discoveries and Ground Risk

3.16.	Notice Obligation

3.17.	Traffic and Special Loads

3.18.	Waterborne Traffic

3.19.	Site Survey and Geotechnical Study

3.20.	Performance Bond

ARTICLE 4 OWNER’S RESPONSIBILITIES

4.1.	Owner Assistance to Contractor

4.2.	Owner’s Services

4.3.	Payment

4.4.	Access to Site, Rights of Way

4.5.	Governmental Authorizations

4.6.	Grid Coordination

4.7.	Owner’s Representative

4.8.	Divergences from Applicable Law

4.9.	Owner Delay

4.10.	Compliance with Laws

4.11.	Taxes and Duties

4.12.	Subcontractors

4.13.	Notice Obligation

4.14.	Spare Parts

ARTICLE 5 COMMENCEMENT OF WORK

5.1.	Commencement of Work

5.2.	Progress Reports and Consultation

ARTICLE 6 CHANGES AND CHANGE ORDERS

6.1.	Changes

6.2.	Owner Changes

6.3.	Contractor Changes

6.4.	Information Supplementing Change Order Request

ARTICLE 7 CONTRACT PRICE; PAYMENTS TO CONTRACTOR

7.1.	Contract Price

7.2.	Payment of Contract Price

7.3.	Payment of Subcontractors

7.4.	Interest and Disputed Invoices

7.5.	Inspection of Records

ARTICLE 8 TITLE AND RISK OF LOSS

8.1.	Title

8.2.	Risk of Loss

ARTICLE 9 INSURANCE

9.1.	Contractor’s Insurance

9.2.	Owner’s Insurance

9.3.	Certificates and Cancellations

9.4.	Failure to Pay

9.5.	Miscellaneous

ARTICLE 10 COMPLETION

10.1.	Substantial Completion

10.2.	Final Completion

10.3.	Completion Certificates

10.4.	Punchlist

ARTICLE 11 WARRANTY

11.1.	General Warranty

11.2.	Warranty Period

11.3.	Remedy

11.4.	Owner Equipment

11.5.	Warranty Exclusions

11.6.	No Implied Warranties

ARTICLE 12 SCHEDULE GUARANTY; LIQUIDATED DAMAGES AND BONUS

12.1.	Schedule Guaranty

12.2.	Liquidated Damages

12.3.	Bonus

ARTICLE 13 LIMITATION OF LIABILITY

13.1.	Maximum Liability

13.2.	Consequential Damages

13.3.	Releases Valid in All Events

13.4.	Liquidated Damages Not Penalty

13.5.	Exclusive Remedies

13.6.	Liability of Related Persons

ARTICLE 14 REPRESENTATIONS OF CONTRACTOR AND OWNER

14.1.	Contractor Representations

14.2.	Owner Representations

ARTICLE 15 DEFAULT, TERMINATION AND SUSPENSION

15.1.	Default by Contractor

15.2.	Default by Owner

15.3.	Suspension of Work

ARTICLE 16 FORCE MAJEURE

16.1.	Force Majeure

16.2.	Excused Performance

16.3.	Performance Continuation

16.4.	Change Order Consequences of Force Majeure

16.5.	Suspension of the Work, Resumption of Performance

16.6.	Termination for Force Majeure

16.7.	Payment on Termination

ARTICLE 17 INDEMNITIES

17.1.	Contractor Indemnity

17.2.	Owner Indemnity

17.3.	Notice

17.4	Conduct and Administration of Claims

ARTICLE 18 DISPUTE RESOLUTION

18.1.	Arbitration

18.2	Submission to Jurisdiction

18.3	Applicable Law; Waiver of Punitive Damages

18.4	Continuation of Services

ARTICLE 19 CONFIDENTIAL INFORMATION

19.1.	Confidential Information

19.2.	Notice Preceding Compelled Disclosure

19.3.	Definition of “Confidential Information"

19.4.	Remedies

ARTICLE 20 MISCELLANEOUS PROVISIONS

20.1.	Governing Law

20.2.	Notice

20.3.	Assignment

20.4.	No Unlawful Payments

20.5.	Miscellaneous

EXHIBIT A	TECHNICAL SCOPE DOCUMENT (TSD)

EXHIBIT A-1	TSD FOR LM2500 GAS TURBINES

EXHIBIT A-2	TSD FOR LM6000 GAS TURBINES

EXHIBIT B	PAYMENT SCHEDULE

EXHIBIT B-1	PAYMENT SCHEDULE FOR LM2500 GAS TURBINES

EXHIBIT B-2	PAYMENT SCHEDULE FOR LM6000 GAS TURBINES

EXHIBIT C	INSURANCE

ENGINEERING, PROCUREMENT AND CONSTRUCTION SERVICES AGREEMENT

THIS ENGINEERING, PROCUREMENT AND CONSTRUCTION SERVICES AGREEMENT (this “Contract”), dated as of May __, 2009 (the “Effective Date”), between Electricidad de Caracas (“Owner”), and the Derwick – ProEnergy Consortium (“Contractor”).

PRELIMINARY STATEMENTS

- A.	Owner intends to build, own and operate a 130 MW dual fuel electric power generation facility, commonly known as the TACOA Power Project located at or near ___________________ consisting of one pre-owned GE LM6000 PD, one GE LM6000 PC and two LM2500 PE simple-cycle combustion turbine generators purchased and supplied by Owner as owner furnished equipment, (the “Facility”).

- B.	Contractor has significant expertise in the design, engineering, procurement, construction, commissioning, start-up and testing of power generation facilities.

- C.	Owner desires to have Contractor provide certain design, engineering, procurement, construction, commissioning, start-up and testing services in connection with the building, commissioning, and startup of the Facility and Contractor desires to provide such services.

NOW THEREFORE, Owner and Contractor agree as follows:

# DEFINITIONS AND CONSTRUCTION

## Definitions.

Terms appearing herein with their first letter capitalized and without other definition shall have the meanings specified in this Section 1.1, unless the context requires otherwise.

“Affiliate” means, with respect to any Person, any other Person that (a) owns or controls, directly or indirectly, the first Person, (b) is owned or controlled by the first Person, or (c) is under common ownership or control with the first Person, where “own” means ownership of fifty percent (50%) or more of the equity interests or rights to distributions on account of equity of the Person and “control” means the power to direct the management or policies of the Person, whether through the ownership of voting securities, by contract, or otherwise.

“Aggregate Limit” has the meaning set forth in Section 13.1.

“Business Day” means any day other than a Saturday, a Sunday, or a day on which banks in Caracas, Venezuela are authorized or required by law to be closed.

“Change” means any change in the Scope of Work, Contract Price, Schedule, and any other addition, alteration, deletion or modification of the Work pursuant to this Contract.

“Change In Law” means the occurrence of any of the following events after the NTP Effective Date:  (a) repeal, amendment, modification, supplementation or replacement of any existing Governmental Authorization or Law affecting the Work, Contractor or any Affiliate or Subcontractor of Contractor in relation to the Work, (b) promulgation or enactment of any new Governmental Authorization or Law affecting the Work, Contractor, any Affiliate of Contractor or Subcontractor in relation to the Work, (c) cancellation or non-renewal or a change in the conditions applicable to any Governmental Authorization, (d) commencement of the effectiveness of any Law affecting the Work, Contractor, any Affiliate or Subcontractor in relation to the Work or imposition of a requirement for a Governmental Authorization that has not yet entered into effect or is not required at the NTP Effective Date, (e) change in the manner in which a Law or Governmental Authorization is enforced, applied or interpreted with respect to the Work, Contractor, any Affiliate or Subcontractor in relation to the Work, or in the enforcement, application or interpretation thereof, (f) after the date of grant of any of the Governmental Authorizations a change in the terms and conditions attaching to any such Governmental Authorization or the attachment of any new terms or conditions to such Governmental Authorization or any renewal thereof, or (g) any of the Governmental Authorizations not being granted on a timely basis on application therefore having been duly made.

“Change In Taxes” means the occurrence of any of the following after the NTP Effective Date that relates to Contractor Applicable Taxes other than corporate income taxes:  (a) the repeal, amendment, modification, supplementation or replacement of any existing Law, (b) the promulgation or enactment of any new Law, (c) commencement of the effectiveness of any Law; (d) the change in the manner in which any Law is enforced, applied or interpreted, or (e) a change in rate or amount of Taxes.

“Change Order” means an instrument effecting a Change that is (a) agreed between and executed by Owner and Contractor pursuant to Article 6 or (b) issued pursuant to the resolution of a dispute in accordance with Article 18, in each case setting forth the details of any Change or Changes effected by such instrument.

“Change Order Request” means a notice from the Owner to the Contractor issued pursuant to Section 6.2.1 or a notice from the Contractor to the Owner issued pursuant to Section 6.3.1, in each case setting forth the details of the Change or Changes requested.

“Confidential Information” has the meaning set forth in Section 19.3.

“Contract” means this Engineering, Procurement and Construction Services Agreement, including all exhibits, attachments, and schedules hereto, as amended, modified or supplemented from time to time in accordance with its terms.

“Contract Price” has the meaning set forth in Section 7.1.

“Contractor” has the meaning set forth in the Preamble to this Contract and is a private consortium made up of Derwick Associates, S.A., Panama company, and ProEnergy EPC Services, LLC, a U.S. company, both of which will be jointly and severally liable for the performance of the obligations of Contractor under the Contract.

“Contractor Applicable Taxes” has the meaning set forth in Section 3.11.1.

“Contractor Indemnitees” means Contractor, Subcontractors and each of their respective Affiliates, successors, assigns, officers, directors, employees and agents.

“Contractor Equipment” means all appliances or things of whatever nature required by Contractor and its Subcontractors for the performance of the Work, excluding the Equipment.

“Day” or “day” means a calendar day and shall include Saturdays, Sundays and holidays.

“Default Rate” means the lower of (a) the maximum  per annum  interest rate allowed by law or, (b) a per annum rate equal to the (i) the Prime Rate as in effect from time to time plus (ii) five percent (5%), calculated on the basis of a 360-day year and the actual number of days elapsed.

“Effective Date” has the meaning specified for such term in the Preamble to this Contract.

“Escrow Account” has the meaning set forth in Section 7.2.2.

“Facility” means the power generation plant and related facilities described in the Recitals above and as further described in Exhibit A including all equipment, materials and services furnished under this Contract.

“Final Completion” has the meaning set forth in Section 10.2.

“Final Completion Certificate” has the meaning set forth in Section 10.3.

“Force Majeure” has the meaning set forth in Section 16.1.

“Gas Turbine Equipment” means the GE LM6000 PD, GE LM6000 PC and two LM2500 PE simple-cycle combustion turbine generators supplied by Owner as part of the Owner Equipment.

“Good Industry Practice” or “GIP” means the exercise of that degree of skill, diligence and prudence that would reasonably and ordinarily be expected from a skilled and experienced contractor applying the standards generally adopted by contractors for the construction of independent (non-utility) power generation facilities of a type, location, condition and scale similar to the Facility and the Equipment, and taking into account the fast-track nature of the Schedule, unless the result of such exercise would violate any applicable Law.

“Governmental Authority” means all authorities of any nation, province, state, city, municipality, local government and any subdivision thereof, whether of an executive, legislative, judicial, administrative, military or police nature and any other Person under the direct or indirect control of any of the foregoing, including any court, tribunal, department, instrumentality, agency, board or commission and officials of any of the foregoing.

“Governmental Authorizations” means all permits, consents, decisions, licenses, clearances, approvals, no-action or no-objection certificates, certificates, confirmations or exemptions from, and all applications, notices and other filings with any Governmental Authority that are necessary for the design, engineering, procurement, construction, start-up, commissioning, testing, financing, ownership and operation of the Facility, including the performance of the Work.

“Guaranteed Completion Date” has the meaning set forth in Section 12.1.

“Hazardous Substances” means any substance or material regulated or governed by any Governmental Authority having jurisdiction as, or any substance, emission or material now or hereafter deemed by any Governmental Authority having jurisdiction to be, a “regulated substance”, “hazardous substance”, “toxic substance”, “pesticide”, “hazardous waste”, or any similar classification, including by reason of deleterious properties, ignitability, corrosivity, reactivity, carcinogenicity or reproductive toxicity.

“ICC” has the meaning set forth in Section 18.2.

“Indemnitee” has the meaning set forth in Section 17.4.

“Indemnitor” has the meaning set forth in Section 17.4.

“Law” means any constitution, charter, act, statute, law, ordinance, code, rule, regulation, order, treaty, decree, announcement or published practice or any interpretation thereof, or other action of any Governmental Authority, or specified standards or objective criteria contained in any applicable Governmental Authorization, or any decree, judgment or order of a court, or any engineering, construction, safety or electrical generation code applicable to the Work, the Facility or any part of either of them.

“Mechanical Completion” means the physical completion, except for Punchlist Items, of the Work so that the Owner Equipment and Contractor Equipment and related operating systems are ready for initial operation, adjustment and testing, in all such cases as may be necessary to permit the Facility to be started up, operated, adjusted and tested safely and without damage to the Facility, the Owner Equipment, the Contractor Equipment or any other property and without injury to any person.

“Month” or “month” means a calendar month (in accordance with the Gregorian calendar).

“NTP” has the meaning set forth in Section 5.1.1.

“NTP Effective Date” means the date upon which all conditions to the effectiveness of NTP have been satisfied or waived in accordance with Section 5.1.1.

“Operator” means Owner or its appointed designee.

“Out of Scope Work” has the meaning set forth in Section 3.14.

“Owner” has the meaning set forth in the Preamble to this Contract.

“Owner Delay” means any delay by Owner in performing or breach by Owner of its obligations set out in Article 4 and elsewhere in this Contract, regardless of any reason for such delay or breach other than a suspension of such obligation in accordance with Article 16 (Force Majeure).

“Owner Equipment” means all machinery, equipment, computer hardware and software, apparatus, materials, balance of plant equipment, and things of all kinds to be provided by Owner and that are to be incorporated into the Facility or to form a part of the Work to be delivered to Owner including but not limited to the Gas Turbine Equipment, and as further described in Section 4 and Exhibit A.

“Owner Indemnitees” means Owner, and its Affiliates, and each of their successors, assigns, officers, directors, employees and agents.

“Owner’s Representative” means the person designated by Owner in writing to Contractor.

“Party” means Owner or Contractor.

“Parties” means Owner and Contractor.

“Person” means any natural person, corporation, company, partnership (general or limited), limited liability company, business trust, or other entity or association.

“Prime Rate” means, at the time any determination thereof is to be made, the fluctuating rate per annum announced from time to time by Citibank N.A., New York and any successor thereto as its “prime rate” (or, if otherwise denominated, such bank’s reference rate for interest rate calculations on general commercial loans), which rate is not necessarily the lowest or best rate which such bank may at any time and from time to time charge any of its customers.  If such bank ceases to announce such a rate, then “Prime Rate” shall mean, at the time any determination thereof is to be made, the fluctuating per annum rate of interest then most recently reported in the Wall Street Journal as the “Prime Rate” (the base rate on corporate loans at large U.S. money center commercial banks) and if reported as a range, the interest rate shall be the mid-point of the range.

“Punchlist” has the meaning set forth in Section 10.4.1.

“Punchlist Item” means any uncompleted part of the Work that (considered individually or in the aggregate of all Punchlist Items) does not and will not adversely affect the performance of the Facility or the ability of Operator to operate the Facility safely and in the ordinary course of business in accordance with GIP.

“Punchlist Withholding” has the meaning set forth in Section 10.4.2.

“Related Persons” has the meaning set forth in Section 13.6.

“Replacement Contractor” has the meaning set forth in Section 15.1.2.

“Representatives” has the meaning set forth in Section 19.1.

“Schedule” has the meaning set forth in Section 5.1.2.

“Schedule Guaranty” has the meaning set forth in Section 12.1.

“Scope of Work” means the description of Work to be performed by Contractor as set forth in Section 3.1 and as further identified as those scope items to be provided by Contractor on Exhibit A.

“Site” means the real property described in the site survey to be furnished to Contractor by Owner.

“Site Variations” has the meaning set forth in Section 3.15.3.

“Subcontract” means an agreement between Contractor and a Subcontractor or a Subcontractor and any other Subcontractor for the performance of any portion of the Work.

“Subcontractor” means any subcontractor, vendor or supplier of equipment, materials or services to Contractor or any subcontractor or any Person engaged or employed by any such subcontractor, vendor or supplier in connection with the performance of any portion of the Work.

“Substantial Completion” has the meaning set forth in Section 10.1.

“Substantial Completion Certificate” has the meaning set forth in Section 10.3.

“Taxes” means any taxes, duties, imposts, fees, levies and similar charges imposed by Governmental Authorities, including income taxes, branch profits taxes or remittances, gross receipts taxes, withholding taxes, sales taxes, excise taxes, value added taxes, import duties or taxes, export duties or taxes, municipal taxes, consumption taxes, stamp taxes, superintendency or equivalent registration taxes, license fees, taxes on the movement of goods, assets taxes, capital taxes, taxes resulting from inflation accounting, profession taxes, works contract taxes and ad valorem taxes.

“USD, U.S. Dollars or $” means lawful currency of the United States of America.

“Warranties” means the express warranties provided by Contractor in Article 11.

“Warranty Period” has the meaning set forth in Section 11.2.

“Work” means all equipment and other structures, instruments, facilities, materials and services performed or otherwise to be delivered to Owner by Contractor pursuant to this Contract and all obligations, duties and responsibilities assigned to or undertaken by Contractor with respect thereto pursuant to this Contract.  In no event shall Work include any Owner Equipment or any materials or services of any kind or nature provided by or on behalf of Owner directly or indirectly with respect to the development, engineering, construction, startup and commissioning of the Facility, other than as contracted directly herein to be furnished by Contractor to Owner.

## Rules of Construction.

In this Contract:

##### the singular includes the plural and vice versa;

##### the masculine gender includes the female gender and vice versa;

##### the word “including” means including without limitation;

##### references to Articles, Sections and Exhibits are, unless the context otherwise requires, references to Articles of, Sections of and Exhibits to this Contract;

##### Article, Section and Exhibit headings are for ease of reference only;

##### Any reference to a statute shall be construed as a reference to such statute as the same may have been, or may from time to time be, amended or re-enacted; and

##### Unless otherwise provided herein, whenever a consent or approval is required by one Party from the other Party, such consent or approval shall not be unreasonably withheld or delayed.

# RELATIONSHIP OF OWNER, CONTRACTOR AND SUBCONTRACTORS

## Status of Contractor.

In performing the Work hereunder, Contractor shall at all times be an independent contractor and shall have sole responsibility for and control over the details and means and methods of performing the Work, subject to the other provisions of this Contract.

## Subcontractors.

Owner acknowledges and agrees that Contractor may have portions of the Work accomplished by Subcontractors.  Contractor shall cause all Subcontractors to perform their work in conformity with all relevant provisions of this Contract.  No contractual relationship shall exist between Owner and any Subcontractor with respect to the Work to be performed pursuant to this Contract, and no Subcontractor is intended to be or shall be deemed a third-party beneficiary of this Contract.  No Subcontractor, agent, or employee of Contractor shall be deemed to be the agent, subcontractor, representative or employee of Owner. Contractor agrees that it shall be as fully responsible to Owner for the acts and omissions of Subcontractors with respect to the Work as Contractor as it is for its own acts or omissions under this Contract.  Unless Owner expressly agrees in writing, Owner shall not be obligated to pay or see to the payment of any Subcontractor.  Entry into any Subcontract shall not relieve Contractor of any of its obligations to perform the Work in accordance with this Contract.

## Subcontract Provisions.

Contractor shall ensure that all of its Subcontracts between Contractor and any it’s Subcontractors are in writing.  Each Subcontract for any major Contractor Equipment shall provide that all Contractor’s rights, including all warranties and obligations of Subcontractor under such Subcontract, are assignable to Owner and its successors and assigns upon Owner’s written request, without further consent of Subcontractor following any termination of this Contract.

# CONTRACTOR’S RESPONSIBILITIES

## Scope of Work.

### General Description of Work.  Contractor shall complete the Work so that it complies with the requirements set forth in this Contract, including the requirements of Mechanical Completion, Substantial Completion and Final Completion.  In the event of any conflict or inconsistency between the requirements of this Contract and GIP, the requirements of this Contract shall prevail.  In the event of any conflict or inconsistency between the requirements of Exhibit A or any other provision of this Contract with respect to the Scope of Work, the requirements of Exhibit A shall prevail.

### Specific Responsibilities.  Without duplication of or limiting the generality of Section 3.1.1 or any other provision of this Contract, and except as set forth in Article 4, Contractor shall in accordance with the provisions of this Contract:

##### Provide the Scope of Work in accordance with the terms of this Contract;

##### subject to the provisions of Section 3.15 and Exhibit A, perform any required improvements to the Site necessary for the completion of the Work in accordance with this Contract;

##### provide all reasonable assistance to Owner in connection with the procurement, supply and transport, handling, and storage of any Owner Equipment and the Parties further agree that Owner is responsible for and shall handle and pay for the transportation of the Owner Equipment to the Site; and

##### provide Site management, Contractor Equipment, construction utilities and consumables, including lubricants, chemicals, construction consumables and construction equipment fuel necessary for the Work in accordance with this Contract except for those items to be furnished by Owner as set forth in Exhibit A.

## Tools. Contractor shall provide all tools necessary for completing the Work.

## Compliance with Drawings.	Contractor shall perform the Work in accordance with the drawings and documents furnished in connection with the Work or otherwise furnished by or on behalf of the Owner.

## Contractor’s Personnel and Labor Relations.

### Site Staff.  Contractor shall ensure sufficient suitably qualified and experienced personnel are at all times present at the Site to supervise and perform the Work at the Site.

### Key Personnel.  Contractor shall appoint suitably qualified and experienced personnel to fill the positions at the Site.   The person holding the post designated as “Project Manager” shall have full authority to act on behalf of Contractor for all purposes in connection with the performance and administration of this Contract, and such person shall have authority to agree to a Change Order, but shall not have authority to otherwise amend this Contract unless Contractor has given written notice to Owner of such express authority.  Contractor shall notify Owner of the normal workplace(s) of the person who holds the post designated as Project Manager, and such person shall receive all instructions related to Site activities given by or on behalf of Owner.  Whenever the Project Manager is absent from the Site, Contractor shall nominate a suitable person to act as his or her deputy.

### Labor Relations.  Contractor shall use all reasonable efforts in the employment of labor and Subcontractors (whether directly or indirectly employed) so as not to cause any conflict or interference with relations between the various trades or any delay in the performance of Contractor’s obligations.  Contractor shall be responsible for all labor relations matters of its employees and those of its Subcontractors relating to the Work and shall at all times use and cause its Subcontractors to use reasonable efforts to maintain harmony among their workforces.  Contractor at all times shall use and cause its Subcontractors to use reasonable efforts and judgment as an experienced contractor to adopt and implement policies and practices designed to avoid work stoppages, slowdowns, disputes and strikes.  Contractor reserves the right to hire non-union and/or non-prevailing wage labor to the extent permitted under applicable Laws.

3.4.4.	Hiring of Contractor Personnel.  If Owner hires, directly or indirectly through a third party, any personnel of Contractor in any capacity during or one (1) year after completion of the Work under this Contract, Owner agrees to pay a fee to Contractor equal to thirty-five percent (35%) of such personnel’s estimated annualized gross compensation for employment.  Estimated gross compensation includes estimates of commissions, bonuses, incentives, equity and salary.  This fee is due and payable within thirty (30) calendar days from the date such personnel commences employment with Owner.

## Governmental Authorizations and Contractor Assistance.

Contractor shall use reasonable efforts (including the provision of documents and information requested by Owner) to assist Owner in its efforts to obtain the Governmental Authorizations that Owner is required to obtain in connection with the construction, operations  and ownership of the Facility.

## Control of the Work.

Except as otherwise provided with respect to Owner’s actions under Sections 3.8.3 and 3.15, Contractor shall be solely responsible for all construction means, methods, techniques, sequences, and procedures in connection with the performance of the Work.

## Cleanup.

Contractor at all times shall keep the Site reasonably free from waste materials or rubbish caused by its activities. As soon as practicable after Substantial Completion, Contractor shall remove all of its waste material and rubbish from the Site.

## Safety and Emergencies.

### Precautions.  Contractor shall be solely responsible for the safety of its operations and the operations of each Subcontractor.  Contractor shall initiate and maintain reasonable safety precautions and programs designed to promote health and safety and prevent injury to persons or damage to property on, about or adjacent to the Site.  Contractor shall erect and maintain reasonable safeguards for the protection of workers and the public.  Contractor shall exercise reasonable efforts to eliminate or abate all reasonably foreseeable safety hazards created by or otherwise resulting from performance of the Work.

### Emergencies.  In the event of any emergency endangering life or property, Contractor shall take such action as may be necessary to deal with such emergency in accordance with GIP to prevent, avoid or mitigate injury, damage or loss and promptly shall notify Owner of any such emergency and the actions taken by Contractor.

### Owner Actions.  Whenever Contractor has not complied with its obligations set forth in Section 3.8.1 or 3.8.2, thereby creating an emergency requiring immediate action, then Owner may take reasonable precautions in accordance with GIP to deal with such emergency, but the taking of such action by Owner, or Owner’s failure to do so, shall not limit Contractor’s liability or its obligations under this Contract.  Contractor shall reimburse Owner for the reasonable costs incurred by Owner in taking such precautions.

## Compliance with Applicable Laws.

### Compliance and Indemnity.  Subject to the other provisions of this Section 3.9 (i) in the performance of this Contract and all Work hereunder, Contractor shall comply with all Laws applicable to the Work, and (ii) Contractor agrees to indemnify, defend and hold harmless Owner Indemnitees from and against any and all fines, penalties, related costs and expenses attributable to any failure of Contractor or any Subcontractor to comply with such applicable Laws in connection with the performance of the Work.

### Divergences from Applicable Law.  If Contractor becomes aware of any divergence between any applicable Law and the Scope of Work or Contractor’s performance of this Contract, it shall promptly give Owner written notice specifying the divergence and any corrections deemed appropriate for remedying such divergence.

### Changes in Law, Changes in Tax.  If and to the extent that any Change in Law or Change in Tax gives rise to a requirement for a Change or if Contractor otherwise incurs any increased cost due to Change in Law or Change in Tax, Contractor shall be entitled, in accordance with Article 6, to a Change Order to recover any direct costs reasonably incurred in mitigation or as a consequence of any such Change in Law or Change in Tax and to evidence other appropriate Changes in respect of any such Change in Law or Change in Tax; provided, however, no such Change Order shall be in duplication of any Change afforded Contractor for a Change in Law pursuant to Section 16.4.

## Books and Records.

Contractor shall keep and shall cause its Subcontractors to keep such books, records and accounts as may be necessary for compliance with Contractor’s obligations under this Contract, including those under Section 7.5.

## Taxes and Fees.

### Contractor shall be responsible within the Contract Price for the corporate income taxes imposed on Contractor (“Contractor Applicable Taxes”).

### If Contractor fails to pay when due any Contractor Applicable Taxes and Contractor’s failure to pay such Taxes will result in an economic loss for Owner, then unless Contractor has filed a written protest regarding the application of such Taxes with the relevant Government Authority, Owner, upon 10 days’ notice from Owner to Contractor, may pay such Taxes and shall be entitled to immediately recover from Contractor the amount paid together with all expenses incurred in connection therewith or to set off all such amounts against any sums owed by Owner to Contractor.

## Access and Inspections; Correction of Defects.

### Right to Inspect.  Subject to compliance with Contractor’s safety policies and precautions, and at Owner’s cost, Owner and its authorized representatives shall have the right to (a) maintain a reasonable presence at the Site and (b) upon reasonable advance notice to Contractor, have access at all reasonable times to any place where Work is being performed by Contractor or any Subcontractor to observe the Work, and upon notice from Owner, Contractor shall make arrangements and provide for such access.  All such Persons shall have the right to be present during the performance of the Work, and shall, by way of example and not limitation, have access to all test procedures, quality control reports and test reports and data.

### Correction of Defects.  Before Substantial Completion, Contractor shall, at its sole cost and expense, promptly correct any part of the Work that is defective or not in accordance with this Contract, regardless of the stage of its completion or the time or place of discovery of such errors.  In the event that any part of the Work is discovered to be in a defective condition or not conforming to this Contract after Substantial Completion, correction of such defective condition shall be governed by Article 11.

### Tear-Out.  Before Substantial Completion, Owner may request Contractor to tear out previously covered Work.  In the event Owner requests Contractor to tear out Work to permit Owner to inspect previously covered Work and such Work inspected is defective, then Contractor shall bear the cost of such tear-out, repair and replacement.  Except in the case of the prior sentence, Contractor shall be entitled to a Change Order in accordance with Article 6 pursuant to which Contractor shall be reimbursed for all additional costs reasonably incurred on account of, and schedule delays resulting from, such tear-out, and shall receive other appropriate Changes in respect of compliance with any request from Owner to tear out Work.

## Storage and Security.

Until Substantial Completion, Contractor shall warehouse or otherwise provide appropriate storage for all Contractor Equipment at or in the vicinity of the Site.  Owner shall be responsible for the security and protection of Contractor’s Equipment and Owner Equipment on the Site.  All Contractor Equipment that is stored at a location other than on the Site shall be segregated from other goods, and Contractor shall be responsible for the security and protection of all Contractor Equipment stored or warehoused off the Site.

## Out of Scope Construction; Cooperation.

Contractor acknowledges and accepts that Owner may engage other Persons to perform work or provide services in connection with the Facility that are not part of the Work but may be performed in whole or in part at or adjacent to the Site (the “Out of Scope Construction”). Contractor agrees to cooperate and use its reasonable efforts to coordinate performance of the Work with any Person performing Out of Scope Construction provided that (a) Contractor shall have no other liability or responsibility with respect to any Out of Scope Construction and (b) Contractor shall be entitled to a Change Order in accordance with Article 6 pursuant to which Contractor shall be entitled to appropriate Changes in respect of any additional costs reasonably incurred on account of such cooperation and any delay suffered as a result of interference with Contractor’s execution of the Work in accordance with this Contract.

## Hazardous Substances, Archaeological Discoveries and Ground Risk.

### Hazardous Substances of Owner, Archaeological Finds.  Upon the discovery of any Hazardous Substances on the Site that were not brought onto the Site by a Contractor Indemnitee during construction activities, including any Hazardous Substances that were existing on the Site at or before the NTP Effective Date, or upon the discovery of any article of value or antiquity or of archaeological or geotechnical interest, Contractor shall (a) promptly cease work in the affected area and direct its workers and Subcontractors not to remove or further disturb any such substances or articles; (b) promptly notify Owner of such discovery; (c) use all reasonable efforts to mitigate the effects of any such discovery to other areas of the Site, any Person and the performance of the remainder of the Work; and (d) follow any and all directions of Owner or its representatives with respect to such discoveries; provided, however, Contractor shall not under any circumstances be instructed or required to remediate any such existing Hazardous Substances.  Owner shall be responsible for the removal from the Site, or for otherwise making the Site safe in accordance with Laws applicable thereto, with respect to any such Hazardous Substances.  Contractor shall be entitled, in accordance with Article 6, to a Change Order to recover additional costs reasonably incurred, schedule delays resulting from, and to other appropriate Changes in respect of any the effects of any such substances or articles and Contractor’s compliance with its obligations under this Section 3.15.1 and/or Owner’s directions with respect to such discovery, in each case other than as a result of Contractor’s breach of its obligations under this Section 3.15.1.  Any such article of value or archaeological or geotechnical interest shall, as between Owner and Contractor, be deemed the property of Owner.

### Hazardous Substances of Contractor.  Prior to Substantial Completion, Contractor shall be responsible for the removal from the Site, or for otherwise making the Site safe in accordance with applicable Laws, with respect to any Hazardous Substances brought onto the Site by a Contractor Indemnitee during construction activities at the Site.  Owner shall notify the Contractor immediately upon the discovery of any such materials and shall provide such assistance as may be reasonably requested by the Contractor to facilitate the measures to be implemented by the Contractor pursuant to this Section 3.15.2.

### Site Conditions.  If during performance of the Work, Contractor encounters conditions at the Site other than those anticipated by Contractor as of the Effective Date or that are described in the site survey, geotechnical study or Sections 3.15.1 and 3.15.2 that increase Contractor’s cost or time for performance of the Work, which conditions include geological or geotechnical conditions, manmade underground obstructions or endangered animals or plants (the “Site Variations”), Contractor shall be entitled to a Change Order in accordance with the provisions of Article 6.  If and to the extent that any Site Variation gives rise to the requirement to make a modification to the Facility or to a Change in the Work or the schedule, manner or sequence of execution of the Scope of Work as described in the Specifications or if Contractor otherwise incurs any additional costs in respect of any Site Variation, Contractor shall be entitled, in accordance with Article 6, to a Change Order to recover any costs reasonably incurred and schedule delays suffered in mitigation of such Site Variations and to evidence other appropriate Changes in respect of such Site Variations.

## Notice Obligation.

Contractor shall give timely notice to Owner of any event or circumstance of which Contractor has knowledge that constitutes Owner Delay, Change in Law, or Force Majeure affecting Contractor’s ability to perform its obligations under this Contract.

## Traffic and Special Loads.

Contractor shall carry out the Work so as not to interfere unnecessarily or improperly with access to and use of public roads.  Contractor shall liaise with, and ascertain the requirements of, all Governmental Authorities in relation to vehicular access to and use of public roads and shall comply with those requirements.  Contractor shall use all reasonable means to prevent damage to any highway or bridge by any traffic of Contractor or any Subcontractor, and, in particular but without limitation, shall select routes, choose and use vehicles, and restrict and distribute loads so as to avoid damage to public highways and bridges.

## Waterborne Traffic.

Where the nature of the Work is such as to require the use by Contractor of waterborne transport, the provisions of Section 3.17 shall apply mutatis mutandis and be construed as though the terms “road”, “bridge” and “highway” include each lock, dock, terminal, sea wall or other structure related to a waterway and the term “vehicle” includes watercraft and shall have effect accordingly.

3.19.	Site Survey and Geotechnical Study.

Contractor shall have a survey and geotechnical study of the Site prepared by qualified and experienced professional surveying and engineering firms and provide a copy to Owner.

3.20.	Performance Bond

Within 30 days following the Effective Date, the Contractor shall deliver to the Owner a performance bond from a third party surety under which the surety agrees to perform Contractor’s obligations under this Contract should Contractor fail to do so.

# OWNER’S RESPONSIBILITIES

## Owner Assistance to Contractor.

Owner shall perform its covenants under this Contract, including the specific Owner responsibilities set forth in Exhibit A and this Article 4, in a timely manner and so as to cooperate with and assist Contractor in the performance of the Work.

## Owner’s Services.

In addition to its other obligations under this Contract, Owner shall, within the time schedule acceptable to Contractor, perform the obligations and provide the facilities, services, consumables and utilities as further identified as Owner’s responsibilities on Exhibit A.  In addition Owner shall provide and shall coordinate delivery of required fuel, and/or fuel delivery system to the Site no later than 10 days prior to the scheduled date for Mechanical Completion.  Owner shall also coordinate with local utilities and provide construction utilities (including construction water, construction electricity, telephone service and start-up and testing fuel) and shall provide suitable staging, laydown and Site groundwater discharge containment areas.  Owner shall be responsible for the timely delivery of the Owner Equipment to the Site so as to not delay or cause Contractor to incur additional costs in completing the Work.

## Payment.

Owner shall timely pay all sums required to be paid by it to Contractor pursuant to the terms of this Contract, in each case in accordance with the provisions of Article 7.

## Access to Site, Rights of Way.

Owner shall provide at Owner’s expense, commencing not later than the date required by Contractor, continuous, uninterrupted and unrestricted access to and use of the Site.  Owner shall continue to provide Contractor and Subcontractors with such access to the Site at Owner’s expense until Substantial Completion and thereafter as may be reasonably required to permit Contractor to complete the Punchlist Items and to effect clean up and removal activities pursuant to Section 3.7.  In addition, Owner will provide at Owner’s expense all easements or other rights of way required for such access to the Site and for performance of the Work.

## Governmental Authorizations.

Owner shall be responsible for obtaining (a) all of the Governmental Authorizations that are required in order for the Facility to be located, constructed and operated at the Site or that applicable Laws require to be issued in Owner’s name. Owner promptly shall deliver to Contractor copies of all such Governmental Authorizations.

## Grid Coordination.

Owner shall provide all necessary information and coordination with respect to the tie-in of the 69kv transmission lines to the Facility and shall arrange for the grid access, dispatch and export of electrical energy from the Facility in order for Contractor to fulfill its obligations under the Contract.

## Owner’s Representative.

The Owner’s Representative has been appointed as the Owner’s project manager in relation to the engineering, procurement and construction of the Facility and is authorized to act on behalf of Owner with respect to all matters pertaining to the terms of this Contract, with whom Contractor shall directly consult at all times and whose instructions, approvals, requests and decisions shall be binding upon Owner.  For the avoidance of doubt, any reference to Owner under this Contract shall also mean Owner’s Representative as it relates to any Change Orders, Change Order Requests, notices, communications, meetings, instructions, approvals, requests, and decisions of any kind or nature with or by the Owner.  Owner’s Representative shall have authority to agree to a Change Order, but shall not have authority to otherwise amend this Contract unless Owner has given written notice to Contractor of such express authority.

## Divergences from Applicable Law.

If Owner becomes aware of any divergence between any applicable Law or Governmental Authorization and the Scope of Work or any other provision of this Contract, Owner promptly shall give Contractor written notice specifying the divergence.

## Owner Delay.

In the event of any Owner Delay, Contractor shall be entitled to a Change Order pursuant to Article 6 under which Contractor shall be paid by Owner, on a monthly basis, in accordance with the invoicing and payment provisions set forth in Section 7.2, for any additional costs reasonably incurred on account of such Owner Delay.  In addition to reimbursement of additional costs incurred, Contractor shall be entitled to a Change Order pursuant to Article 6 that provides for appropriate Changes in respect of such Owner Delay.

## Compliance with Laws.

In the performance of its obligations under this Contract, Owner shall ascertain and comply with all Laws and Government Authorizations that relate to the Owner and the performance of its obligations hereunder.  Owner agrees to indemnify, defend and hold harmless Contractor and Contractor Indemnitees from and against any and all fines, penalties, related costs and expenses, including reasonable legal expenses and costs, attributable to any failure of Owner to comply with such Laws and Governmental Authorizations in connection with the performance of its obligations under this Contract.

## Taxes and Duties.

Owner shall be responsible for payment of (and such are not included in the Contract Price) all Taxes  other than those Contractor Applicable Taxes for which Contractor is responsible under Section 3.11.

## Subcontractors.

Owner shall not direct or manage any of the Subcontractors and shall communicate with the Subcontractors only through and in coordination with Contractor.

## Notice Obligation.

Owner shall give timely notice to Contractor of any event or circumstance that constitutes, or Owner reasonably believes will constitute, Owner Delay, Change in Law or Force Majeure affecting Owner's ability to perform its obligations under this Contract.

4.14	Spare Parts and Consumables.

Owner shall be responsible for the provision and storage of all spare parts and consumables necessary to operate the Facility once Substantial Completion is achieved.

# COMMENCEMENT OF WORK

## Commencement of Work.

### Issuance of Notice to Proceed.  Owner may deliver a written notice to proceed no later than thirty (30) days from the Effective Date (the “NTP”) that authorizes Contractor to commence performance of the full Scope of Work; provided that such NTP shall not be effective until each of the following conditions have been satisfied by Owner or waived in a writing signed by the Contractor:

##### the initial down-payment of the Contract Price has been paid by Owner and received by Contractor;

##### the insurance required to be obtained by Owner pursuant to Article 9 shall be in effect and Owner shall have delivered to Contractor the certificates required by Section 9.3.2;

##### Owner shall have furnished evidence reasonably satisfactory to Contractor that Owner has obtained those Governmental Authorizations described in Section 4.5 that are necessary for construction to proceed;

##### Owner shall have provided continuous and unrestricted access to and use of the Site;

##### Owner shall have demonstrated to Contractor’s satisfaction that Owner has access to sufficient financial and other resources to enable it to perform its obligations hereunder; and

##### Owner shall have delivered evidence reasonably satisfactory to Contractor that the representations of Owner in Section 14.2 are true and correct as of the date of NTP.

Upon the occurrence of the NTP Effective Date the Contractor shall commence the Scope of the Work and thereafter shall proceed diligently to perform such Work.

### Schedule.  The Schedule attached hereto as part of Exhibit A shall cover the engineering, procurement and completion of the Work.

### Revision and Updating.  Contractor shall promptly inform Owner of any proposed material change in the Schedule and shall furnish Owner with a revised schedule.  The Schedule shall be kept up to date, taking into account the actual progress of the Work, and shall be revised, if necessary, and included with the progress report required by Section 5.2.

## Progress Reports and Consultation.

### Progress Reports.  Commencing with the second month following the month in which NTP Effective Date occurs, Contractor shall submit to Owner, by the 16th day of each month, a written report on the progress of the Work through the end of the preceding month that shall include, at a minimum, a description of the progress of the Work, the status of the supply of goods, materials and equipment necessary for the completion of the Work, a comparison of the actual schedule of the Work with the Schedule, and an evaluation of problems and deficiencies and a description of any planned corrective action with respect thereto.  If Owner so directs, Contractor also shall at reasonable intervals conduct appropriate review meetings at mutually agreeable locations with representatives of Owner to review the status of the Work.  Contractor shall promptly notify Owner in writing if at any time Contractor has reason to believe that a material deviation in the Schedule will occur and Contractor shall specify in such notice or within a reasonable time thereafter any necessary corrective action.

### Additional Reports.  Should any material problem, emergency, strike, injury, work stoppage or legal problem be anticipated, or should any unanticipated event occur that might adversely affect Contractor’s ability to perform its obligations hereunder in a timely manner, in addition to all other reports required hereunder, Contractor shall promptly prepare a written significant event report detailing all available information and steps being taken to correct or mitigate the consequences of such problem or event and shall deliver the significant event report to Owner as soon as reasonably practicable.

# CHANGES AND CHANGE ORDERS

## Changes.

### Every Change shall be evidenced by a Change Order.

### Except to the extent a Change Order specifically evidences a Change, all provisions of this Contract shall apply to all Changes, and no Change shall be implied as a result of any other Change.

## Owner Changes.

### Owner may from time to time during the performance of the Work request the Contractor to make a Change provided that such Change:

##### is within the general scope of this Contract,

##### would not cause a violation of any applicable Law or Government Authorization,

##### is technically feasible,

##### would not have an adverse effect upon the Contractor’s liability under the Warranties, and

##### would not have an adverse effect upon Contractor’s ability to complete the Work so that, when the Facility is constructed in accordance with the terms of this Contract, the Facility will achieve the expected operational and performance criteria.

### Any Change requested by Owner pursuant to this Section 6.2 shall be the subject of a Change Order Request delivered by Owner to Contractor, and Contractor shall be entitled to receive an appropriate adjustment in the terms of this Contract in respect of such Change.

### Within 30 days following receipt of Owner’s Change Order Request in compliance with Section 6.2.1, Contractor shall supply the information required pursuant to Section 6.4 and propose a form of Change Order evidencing proposed Changes.

### Within 10 days following Owner’s receipt of the information required pursuant to Section 6.4, Owner shall, by notice to Contractor, either: (a) accept and execute Contractor’s proposed Change Order; (b) request reasonable additional information, documentation or cost detail to further assess the proposed Changes; (c) withdraw the Change Order Request or (d) subject to Section 6.2.5, direct Contractor to proceed with the Changes in the Work as set forth in the Change Order Request.

### If the Parties are unable to agree upon Owner requested Changes and the terms of the related Change Order within 30 days following the date on which the Contractor provided the information required by Sections 6.2.3 and 6.2.4(b), either Party may refer any dispute as to a Change Order Request under Section 6.2.1 for resolution in accordance with the provisions of Article 18.

## Contractor Changes.

### Upon Contractor’s submission of a Change Order Request and the information required in Section 6.4, Contractor shall be entitled to a Change Order evidencing appropriate Changes in respect of the occurrence of any event or circumstance constituting Change in Law and/or Change in Tax (pursuant to Section 3.9.3), uncovering of Work (pursuant to Section 3.12.3), Out of Scope Construction costs and/or delay (pursuant to Section 3.14), differing Site conditions (pursuant to Sections 3.15.1 and 3.15.3) or due to the findings under the survey or geotechnical study of the Site, Owner Delay (pursuant to Section 4.11), suspension of the Work (pursuant to Section 15.3), Force Majeure (pursuant to Section 16.4), and any other event or circumstance for which this Contract entitles Contractor to a Change.  Such Changes shall include any Change appropriate to reflect the effect of the event or circumstance referred to in this Section 6.3.1 upon any obligation or performance of Contractor under this Contract and shall include, as appropriate, Changes in Contract Price, Schedule, and Warranties, all in a manner that is commercially and technically reasonable and appropriate in light of the event or circumstance giving rise to the Change Order Request and the rights and obligations of the Parties under this Contract with respect to the Work.

### Within 10 days following receipt of Contractor’s Change Order Request pursuant to Section 6.3.1, a proposed form of Change Order and the other information required pursuant to Section 6.4, Owner shall by notice to Contractor either: (a) accept and execute the Contractor’s proposed Change Order; (b) request reasonable additional information, documentation or cost detail to further assess the Changes; or (c) reject the Change Order Request.

### If Owner rejects Contractor’s Change Order Request pursuant to Section 6.3.2 or if the Parties are otherwise in dispute over any such Change Order Request or any part thereof, then either Party may refer the dispute to resolution in accordance with the provisions of Article 18.

## Information Supplementing Change Order Request.

### Upon receipt of Owner’s Change Order Request that complies with Section 6.2.1, Contractor shall prepare and submit to Owner a form of proposed Change Order and a report indicating in reasonable detail (a) the Changes in the Schedule, Contract Price, and other aspects of the Work and the Contractor’s obligations to perform the Work in accordance with the Contract resulting from such Change Order Request, and (b) any other appropriate Changes sought by Contractor as a result of such Change Order Request, in each case accompanied, when available, by supporting documentation. If at such time it is impracticable to specify all Changes that Contractor may claim with respect to such event or circumstance, then Contractor shall provide Owner with periodic supplemental information to keep Owner informed of any change, development, progress or other relevant information concerning such event or circumstance and its effect.

### Within 30 days following initiation of any Contractor’s Change Order Request pursuant to Section 6.3.1, Contractor shall prepare and submit to Owner a form of proposed Change Order and a report indicating in reasonable detail: (a) a description of the event or circumstance giving rise to such Change Order Request, (b) the effect on the Schedule, Contract Price, and other aspects of the Work and Contractor’s ability to perform the Work in accordance with the Contract resulting from such event or circumstance, and (c) the Changes sought by Contractor as a result of such event or circumstance, in each case accompanied, when available, by supporting documentation.  If at such time it is impracticable to specify all Changes that Contractor may claim with respect to such event or circumstance, then Contractor shall provide Owner with periodic supplemental information to keep Owner informed of any change, development, progress or other relevant information concerning such event or circumstance and its effect.

### If, at any time after Contractor has provided to Owner the information required by Section 6.4.1 with respect to any Change Order Request from Owner pursuant to Section 6.2.2, Owner decides not to proceed with such Change Order Request, Owner shall pay to Contractor the costs reasonably incurred by Contractor as a result of proceeding with the Owner Change Request prior to notice to the Contractor of Owner’s decision (but excluding any cost or expense in preparing such information).

### If Owner disputes any Change that would extend all or any portion of the Schedule and the Contractor is ultimately determined to be entitled to such Change, Owner shall pay to Contractor, without limitation of any other rights hereunder, any additional costs reasonably incurred in respect of Contractor’s efforts to meet the Schedule prior to receiving such Change.

# CONTRACT PRICE; PAYMENTS TO CONTRACTOR

## Contract Price.

### Contractor agrees to perform the Work for the total lump sum amount of U.S.$_________________, except as may be adjusted according to the express terms of this Contract, to be paid in accordance with the payment terms set forth in Section 7.2 below and Exhibit B (the “Contract Price”).

## Payment of Contract Price.

### Initial Down-Payment.  On or before the NTP Effective Date the Owner shall wire the initial down-payment of the Contract Price to Contractor in the specified currencies identified on Exhibit B to the bank account or accounts designated in writing by Contractor.

### Escrow Account; Milestone Payments.  On or before the NTP Effective Date the Owner shall wire the full amount of the Contract Price in the specified currencies identified on Exhibit B, less the initial down-payment paid directly to Contractor under Section 7.2.1, to an escrow account in the name of a third party escrow agent to be agreed by the Parties (the “Escrow Account”).  Upon each milestone date set forth on Exhibit B the Contractor shall submit a request for payment along with an invoice for the corresponding milestone payment to the escrow agent, with a copy to the Owner, and the escrow agent shall thereupon wire said amount to Contractor’s bank account or accounts without delay, retainage or offset.  The fee charged by the escrow agent in setting up the escrow account and administering the disbursement of funds shall be share 50/50 by Owner and Contractor.  Any interest accruing on the escrow funds shall be for the account of Owner except for any period of time that Contractor is not timely paid on any milestone payment request.

### Final Payment.  Upon Final Completion, Contractor shall submit to Owner a statement summarizing and reconciling all previous invoices, payments and Change Orders and an affidavit that all payrolls, payroll taxes, liens, charges, claims, demands, judgments, security interests, bills for materials and equipment and other indebtedness in connection with the Works for which Contractor may in any way be responsible, have been paid or released, as the case may be, accompanied by a release and waiver of liens from Contractor.  Within 10 days of the receipt of such statement Owner shall pay Contractor the final payment of the Contract Price, including any Punchlist Retainage, in the event there are not sufficient funds in the Escrow Account to pay the final payment.

## Payment of Subcontractors.

Contractor shall promptly pay, in accordance with the terms and conditions set forth in the respective Subcontract, each Subcontractor the amount to which said Subcontractor is entitled.  Contractor shall, by an appropriate agreement with each Subcontractor, require each Subcontractor to make timely payments to its laborers, suppliers and subcontractors in a similar manner.

## Interest and Disputed Invoices.

Amounts not paid by either Party to the other when due under any provision of this Contract, including the provisions of this Article 7, shall bear interest from the date payment was originally due to and including the actual date of payment at the Default Rate.  If there is any dispute about any amount invoiced by Contractor, the amount not in dispute shall be promptly paid and any disputed amount that is ultimately determined to have been payable shall be paid with interest at the Default Rate from the date the item was payable to and including the actual date of payment.

## Inspection of Records.

###### Contractor shall maintain in accordance with generally acceptable accounting practices complete, accurate and up-to-date records, books and accounts relating to the performance of the Work, and as necessary to verify the incurring and payment of all costs and expenditures and performance of Contractor’s  obligations hereunder. Contractor shall retain all such books and records for two (2) years or longer, if required by Applicable Laws.  Owner or its designee shall have the right to carry out audit tasks of a financial, technical or other nature in relation to the performance of the Work upon not less than three  (3) days (or such shorter period if required by Applicable Law) prior notice to Contractor.  Contractor shall make available, at Contractor's home office location, to Owner or its designee, and Owner or its designee shall have the right to review, all contracts, purchase orders, settlements, books, records, and other documents relating to the Work, and Owner or its designee may make such copies thereof or extracts therefrom as Owner or such designee may deem appropriate.  Contractor shall use reasonable efforts to take, or cause to be taken, all actions, and to do, or cause to be done, all things reasonably required to be done, in connection with any financial report prepared by or on behalf of Owner, including preparing for or providing to Owner reports, certificates, schedules and opinions.  Any financial reporting required of Contractor shall be limited to the Work paid by Owner on a cost-reimbursable basis notwithstanding the foregoing terms of this Section 7.5.

# TITLE AND RISK OF LOSS

## Title.

### Warranty of Title.  Contractor warrants good title to all Work including the Contractor Equipment and warrants and guarantees that title, when it passes to and vests in Owner as described in this Section 8.1, will be free and clear of any and all liens, claims, charges, security interests, encumbrances and rights of other Persons arising as a result of any actions or failure to act of Contractor, its Subcontractors, or their employees or representatives.

### Title to Work. Title to all Work including the Contractor Equipment will pass to Owner upon performance, or in the case of equipment, materials and goods included as part of the Work, upon delivery of such equipment, materials or goods to the Site.

### Title to Drawings.  Title to drawings, designs, plans, specifications and like materials specifically prepared as part of the Work will remain with Contractor.  Contractor grants to Owner an irrevocable, non-exclusive, royalty-free license to use and reproduce Contractor’s and Subcontractor’s drawings, designs, plans, specifications and other design documentation to which Contractor has title or has the right to grant sub-licenses; provided, however, such licensing and use shall be solely at Owner’s risk and cost, without any liability to Contractor.

### Control of Software and Other Proprietary Material.  Owner recognizes that the software and other proprietary intellectual software and other intellectual property provided by Contractor to Owner as part of the Scope of Work carries with it certain restrictions on use and copying of such software and other intellectual property and that such software and other intellectual property will not be duplicated, used, printed, displayed, modified or disclosed or provided to a third party without Contractor’s express written authorization, provided that Owner shall have the right to assign the benefit of such software and other intellectual property and the license granted below to a purchaser of the Facility, or to any subsequent assignee of the same.  Contractor represents and warrants that it has all rights and licenses necessary for it to provide such software and other intellectual property to Owner as contemplated in this Contract and grants to Owner an irrevocable, non-exclusive and royalty-free license to use and reproduce such software and other intellectual property in connection with the construction and operation of the Facility.  Such license allows Owner only the limited right to use and reproduce the software and other intellectual property as contained herein and shall not convey any title to or ownership in the software and other intellectual property to Owner or any Person to whom Owner is permitted to assign its license.  Owner agrees to indemnify Contractor against any third-party claims made against Contractor resulting from unauthorized duplication, use, printing, display, modification or disclosure of such software and other intellectual property by Owner.

## Risk of Loss.

### Before Substantial Completion.  Notwithstanding passage of title as provided in Section 8.1, Contractor shall bear the risk of loss of and damage to, and shall be obligated to repair, replace, or reconstruct, all or any portion of the Work or Contractor Equipment that is procured by Contractor that is lost, damaged or destroyed prior to Substantial Completion.

### After Substantial Completion.  After Substantial Completion Owner shall bear the risk of loss of and damage to, and shall be obligated to replace, repair or reconstruct, any previously completed and turned-over Work and Contractor Equipment.

# INSURANCE

## Contractor’s Insurance.

### Required Coverages.  From the NTP Effective Date and thereafter until Substantial Completion, Contractor will obtain and maintain at its expense the insurance described on Exhibit C.

### Requirements of Contractor’s Insurance.  The insurance provided by Contractor pursuant to this Section 9.1 shall be primary as respects to the Owner and its respective directors, officers, representatives, agents and employees, and any other insurance obtained and maintained by Owner shall be excess of and shall not contribute with such insurance.  In addition, all such insurance (a) shall be with an insurance company or companies licensed to do business as required by applicable Law; (b) shall contain customary cut through provisions and waivers of subrogation and shall name Owner as an additional or named insured; and (c) shall include such other provisions and endorsements as are set forth on Exhibit C.

## Owner’s Insurance.

### Required Coverage.  As required by Section 5.1.1, from the NTP Effective Date and thereafter until the end of the Warranty Period, Owner shall obtain and maintain the insurance described in Exhibit C.

### Requirements of Owner’s Insurance.  The insurance provided by Owner pursuant to Section 9.2 shall be primary as respects Contractor, its Subcontractors and their respective directors, officers, representatives, agents and employees, and any other insurance obtained and maintained by Contractor or its Subcontractors shall be excess of and shall not contribute with such insurance.  In addition, all such insurance shall be with (a) an insurance company or companies licensed to do business as required by applicable Law; (b)  shall contain customary cut through provisions and waivers of subrogation and  shall name Contractor as an additional or named insured; and (c) shall include such other provisions and endorsements as are set forth on Exhibit C.

## Certificates and Cancellations.

### Contractor Certificates.  Contractor shall, on or prior to the NTP Effective Date and commencement of activities on the Site, deliver to Owner certificates of insurance evidencing compliance with the requirements of Section 9.1.

### Owner Certificates.  Owner shall, consistent with the timing set out in Section 9.2, deliver to Contractor certificates of insurance evidencing compliance with the requirements of Section 9.2.

### Notice of Cancellation. All policies of insurance to be secured and maintained hereunder shall provide, by endorsement or otherwise, that the other Party and any additional insured, where required in writing, shall be provided 30 days prior written notice of any material policy changes or cancellations (except 10 days for non-payment of premium), and that no such cancellation or change shall be effective without such notice.

### Notice of Loss, etc. Contractor shall immediately notify Owner regarding the occurrence of any of the following events: (a) any significant loss covered by a policy required to be maintained by this Article 9; (b) any significant dispute with an insurer; (c) the early cancellation of any policy; (d) the failure to pay any premium payment; (e) the failure, for any reason, to maintain any policy required to be maintained by this Article 9; and (f) any significant change in any insurance coverage contracted for by Contractor.

## Failure to Pay.

Irrespective of the requirements for insurance to be secured and maintained hereunder, the insolvency, bankruptcy or failure of any insurance company carrying insurance of any Party or the failure of any such insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Contract, including, without exception, the indemnity obligations of any Party.  Notwithstanding any provision to the contrary, in the event any claim is made against any insurance required to be maintained by Owner the Contractor shall not be obligated to perform or reperform its Work or portion thereof relating to said claim unless and until sufficient proceeds are collected and paid to Contractor in order to perform said Work or Owner has made other financial arrangements acceptable to Contractor.

## Miscellaneous.

### Non-waiver.  Failure of either Party to comply with the foregoing insurance requirements shall in no way waive its obligations or liabilities under this Contract or the rights of Owner hereunder against Contractor, or the rights of Contractor hereunder against Owner.

### Right to Insure.  Should either Party fail to provide or maintain any of the insurance coverage required under this Article 9, the other Party shall have the right to provide or maintain such coverage at the failing Party’s expense, either by direct charge or set-off.

### Subcontractor Insurance.  Before permitting any major Subcontractor to perform any Work, Contractor shall obtain a certificate of insurance from each such Subcontractor evidencing that such Subcontractor has obtained, from insurance carriers licensed to do business as required by applicable Laws, insurance in such amounts and against such risks as is prudent in light of the work to be performed by such Subcontractor, subject to the commercial availability of such insurance and commensurate with normal practices in the location where such Work is performed.

# COMPLETION

## Substantial Completion.

The Facility shall be considered substantially complete (“Substantial Completion”) upon the Contractor’s satisfaction of all the following conditions:

##### Mechanical Completion of the Facility has been achieved;

##### All performance tests which Contractor is required to carry out as part of its commissioning and startup Scope of Work under the terms of the Contract have been satisfactorily completed unless such tests cannot be carried out through no fault of Contractor; and

(c)	the Punchlist has been prepared by Contractor and delivered to Owner.

## Final Completion.

The Facility shall be considered to be finally complete (“Final Completion”) upon the Contractor’s satisfaction of the following conditions:

##### Substantial Completion has occurred and all Punchlist Items have been completed;

##### Contractor’s obligations under Section 3.7 (Cleanup) have been completed; and

##### Contractor has provided the release and waiver of liens pursuant to Section 7.2.2.

## Completion Certificates.

Upon achieving Substantial Completion, the Contractor shall deliver to Owner a certificate (the “Substantial Completion Certificate”), and upon achieving Final Completion, the Contractor shall deliver to Owner a certificate (the “Final Completion Certificate”),  The effective date of Substantial Completion and Final Completion shall be the day on which the requirements for Substantial Completion or Final Completion, as the case may be, have been completed, as evidenced by the Substantial Completion and Final Completion Certificates.

## Punchlist.

### Punchlist Preparation.  Prior to Substantial Completion, Owner and Contractor shall inspect the Work and Contractor shall prepare a listing of the outstanding Punchlist Items (the “Punchlist”), and provide it to Owner together with an estimate of the cost and time to complete or correct each such Punchlist Item.  Such Punchlist Items shall not be grounds for Substantial Completion not occurring or for Owner not accepting the Substantial Completion Certificate.  The draft Punchlist shall be prepared in accordance with Contractor’s quality assurance manual and submitted to Owner for review.  Owner shall review and comment on the Punchlist not later than five days after Owner’s receipt thereof, and Contractor shall issue a revised Punchlist to Owner that takes into account or responds to Owner’s comments not later than five days after Contractor’s receipt of such comments.

### Punchlist Withholding.  An amount equal to the estimated cost of correcting all outstanding Punchlist Items (the “Punchlist Withholding”) shall be withheld by Owner from the payment due to Contractor and retained until all the Punchlist Items are corrected.

### Correction of Punchlist Items.  Promptly after receipt by Owner of the revised Punchlist, Contractor and Owner shall agree upon a schedule for Contractor’s completion of the Punchlist Items that will allow Contractor to complete such Punchlist Items within a reasonable period of time without interfering with the operation of the Facility.  Owner shall provide Contractor reasonable access to the Facility to perform such Work in accordance with such schedule to the extent that such access does not unduly interfere with the operations of the Facility.

### Right of Waiver. Owner shall have the right, but shall have no obligation, to waive, defer or reduce any of the requirements stated in this Article 10 at any time.  However, Owner’s exercise of any rights hereunder shall apply only to such requirements as Owner may specify in writing and shall in no event relieve Contractor of any requirements or other obligations not so specified.

# WARRANTY

## General Warranty.

Contractor represents and warrants that it is and will be at all times during the term of this Contract duly qualified and capable of performing the Work in accordance with the terms of this Contract. Contractor warrants that:

##### the Work and Contractor Equipment shall be of good quality and shall be free of defects in materials and workmanship;

##### the Work shall be performed in accordance with GIP;

##### the Work shall conform in all material respects to the Scope of Work and all applicable Laws and Governmental Authorizations in effect at Substantial Completion.

## Warranty Period.

The warranty set forth in Section 11.1 shall extend for a period of 12 months following Substantial Completion (the “Warranty Period”).  The Warranty Period with respect to any Work that is repaired, replaced, modified or otherwise altered or corrected after Substantial Completion shall extend for 12 months from the date of completion of such repair, replacement, modification, correction or alteration, provided that in no event shall any Warranty Period extend beyond 24 months following Substantial Completion.

## Remedy.

Owner promptly shall give notice to Contractor of the discovery during the Warranty Period of any defect that constitutes a breach of Contractor’s warranties under Section 11.1.  Contractor shall correct or replace the applicable Work at no cost to Owner except that Owner shall be responsible for any and all import and export permits, duties, licenses, customs clearance and any Governmental Authorizations or Taxes associated with Contractor performing its warranty obligations.  Promptly after receipt by Contractor of such notice, Contractor and Owner shall agree upon a schedule for Contractor’s performance of its warranty obligations that will allow Contractor to complete such work within a reasonable period of time without unreasonably interfering with the operation of the Facility.  Owner shall provide Contractor with full and free access to the Facility to perform such warranty obligations in accordance with such schedule.   The remedies of Owner under Sections 11.1 and 11.2 are the exclusive remedies of Owner arising out of the warranties set forth in this Contract and any remedies to which Owner otherwise would be entitled at law arising out of such warranties are hereby excluded.  Notwithstanding another provision hereof or under applicable Law, Contractor’s liability for breach of warranty shall be limited to the correction or replacement of the defective portion of the Work, and Contractor shall have no other liability in connection with such breach to Owner.

## Owner Equipment.

The Parties acknowledge and agree that Contractor is not providing any warranty of any kind or nature with respect to any of the Owner Equipment or any other in connection with Contractor performing the Work.  Contractor agrees to provide all reasonable assistance to Owner in administering warranty claims with respect to the Owner Equipment or such other equipment, goods, parts, or materials furnished by Owner.

## Warranty Exclusions.

The duties, liabilities and obligations of Contractor under this Article 11 or otherwise do not extend to any repairs, adjustments, alterations, replacements or maintenance that may be required as a result of  normal wear and tear in the operation of the Facility, normal degradation in the performance of any equipment, or as a result of (a) improper repair or alteration by Owner or other Persons, (b) misuse, negligence or damage by Owner or other Persons, (c) excessive operation at peak capacity, frequent starting, type of fuel, detrimental air inlet conditions, or erosion, corrosion or material deposit of fluids  The warranty and remedies are further conditioned upon (i) the proper storage, installation, operation and maintenance of the equipment and conformance with the operation and instruction manuals provided by the suppliers and manufacturers and (ii) repair or modification pursuant to the instructions of the suppliers and manufacturers and as otherwise directed by Contractor.  Owner shall keep proper operation and maintenance records of the Facility during the warranty period and shall be submitted to Contractor upon request.

## No Implied Warranties.

THE EXPRESS WARRANTIES SET FORTH IN THIS CONTRACT ARE EXCLUSIVE AND NO OTHER WARRANTIES OF ANY KIND, WHETHER STATUTORY, WRITTEN, ORAL, EXPRESS OR IMPLIED (INCLUDING WARRANTIES OF FITNESS FOR A PARTICULAR PURPOSE OR MERCHANTABILITY AND IMPLIED WARRANTIES OF CUSTOM OR USAGE) SHALL APPLY.

# SCHEDULE GUARANTY; LIQUIDATED DAMAGES AND BONUS

## Schedule Guaranty.  Contractor agrees that Substantial Completion shall occur no later than December 15, 2009 provided that NTP is issued by Owner and all conditions set forth in Section 5.1.1 have been satisfied by Owner no later than May 18, 2009 (the “Guaranteed Completion Date”).  Contractor shall be granted a day-for-day extension to the Schedule, Schedule Guaranty, and the Guaranteed Completion Date for (i) each day that the NTP is not issued or any of the conditions set forth in Section 5.1.1 have not been satisfied by May 18, 2009, (ii) any delay in Owner funding the Escrow Account pursuant to Section 7.2.2 by May 18, 2009, (iii) any unexcused delay in Contractor receiving any of the payments of the Contract Price, and (iv) any Owner Delay.

## Liquidated Damages.

## Contractor shall pay to Owner as liquidated damages if Substantial Completion does not occur by the Guaranteed Completion Date due to the fault of Contractor as follows:

U.S.$3000 per day	Day 1-30 late

U.S.$7500 per day	Day 31-60late

U.S.$13,500 per day	Day 61 or more late

## In no event shall Contractor’s obligation to pay liquidated damages under this Section 12.2 exceed ten percent (10%) of the Contract Price.

## Payment of any applicable liquidated damages under this Section 12.2 shall be made by Contractor net ten (10) days from Owner’s invoice for said payment.

## Bonus.

## Owner shall pay to Contractor a bonus if Substantial Completion occurs prior to the Guaranteed Completion Date due to the efforts of Contractor as follows:

U.S.$3000 per day	Day 1-30 early

U.S.$7500 per day	Day 31-60 early

U.S.$13,500 per day	Day 61 or more early

## In no event shall Owner’s obligation to pay a bonus under this Section 12.3 exceed ten percent (10%) of the Contract Price.

## Payment of any applicable bonus under this Section 12.3 shall be made by Owner net ten (10) days from Contractor’s invoice for said payment.

# LIMITATION OF LIABILITY

## Maximum Liability.	Notwithstanding any provision of this Contract to the contrary, Contractor’s maximum aggregate liability to Owner arising out of or related to the Work, the Facility, or this Contract, and the performance, nonperformance and/or defective performance hereunder shall be an amount equal to 25% of the amount of the Contract Price (the “Aggregate Limit”) actually paid to Contractor, which limit applies to any and all liabilities of Contractor to Owner under or in connection with this Contract, including liability for liquidated damages, warranty and indemnity obligations, tort (including negligence and strict liability) and breach of contract (including any breach resulting in termination), and any and all other liabilities based on any legal or equitable theory or basis of recovery.

## Consequential Damages.

In no event shall Contractor or Owner be liable to the other, nor shall Contractor be liable to any of the Owner Indemnitees or Owner be liable to any of the Contractor Indemnitees, either individually or jointly and irrespective of whether alleged to be by way of indemnity, as a result of breach of contract, breach of warranty, tort (including negligence), strict liability, or any other legal or equitable theory, and whether arising before or after completion of the Work, for, and each of Contractor and Owner hereby waives any right to, damages that constitute consequential, incidental, special, indirect, or other damages of any consequential or remote nature whatsoever, including losses or damages caused by reason of unavailability of the Facility, shutdowns or service interruptions, loss of use, non-operation of the Facility or any Owner Equipment or Contractor Equipment, loss of power or cost of replacement power, loss of opportunity, profits or revenue, loss of contracts, cost of capital, inventory or use charges, cost of purchased or replacement power, loss of fuel, interest charges or claims of Owner’s customers, except to the extent such damages are included in liquidated damages under Article 12.

## Releases Valid in All Events.

Releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability, fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of any person whose liability is released, disclaimed or limited.

## Liquidated Damages Not Penalty.

Owner and Contractor acknowledge and agree that because of the unique nature of the Facility and the unavailability of a substitute facility, it is difficult or impossible to determine with precision the amount of damages that would or might be incurred by Owner as a result of Contractor’s failure to achieve the Schedule Guaranty.  It is understood and agreed by the Parties that (a) Owner shall be damaged by failure of Contractor to meet such obligations, (b) it would be impracticable or extremely difficult to fix the actual damages resulting therefrom, (c) any sums which would be payable under this Contract as liquidated damages are in the nature of liquidated damages, and not a penalty, and are fair and reasonable, (d) such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such failure, and shall, without duplication, be the sole and exclusive remedy and measure of damages with respect to any such failure by Contractor, and (e) the liquidated damages have been calculated by reference to the losses reasonably anticipated to be suffered by Owner if the Schedule Guaranty is not achieved.

## Exclusive Remedies.

OWNER AND CONTRACTOR INTEND THAT THEIR RESPECTIVE RIGHTS, OBLIGATIONS AND LIABILITIES AS PROVIDED FOR IN THIS CONTRACT SHALL BE EXHAUSTIVE OF THE RIGHTS, OBLIGATIONS AND LIABILITIES OF EACH OF THEM TO THE OTHER ARISING OUT OF, UNDER OR IN CONNECTION WITH THIS CONTRACT OR THE WORK, WHETHER SUCH RIGHTS, OBLIGATIONS AND LIABILITIES ARISE IN RESPECT OR IN CONSEQUENCE OF AN INDEMNITY OR WARRANTY OR BY REASON OF ANY BREACH OF CONTRACT OR OF STATUTORY DUTY OR BY REASON OF TORT (INCLUDING NEGLIGENCE AND STRICT OR ABSOLUTE LIABILITY) OR by reason of any other legal or equitable theory.  ACCORDINGLY, THE REMEDIES EXPRESSLY STATED IN THIS CONTRACT ARE INTENDED TO BE AND SHALL CONSTITUTE THE SOLE AND EXCLUSIVE REMEDIES OF THE PARTIES TO THIS CONTRACT FOR THE LIABILITIES OF SUCH PARTIES ARISING OUT OF OR IN CONNECTION WITH THE WORK OR THIS CONTRACT, NOTWITHSTANDING ANY REMEDY OTHERWISE AVAILABLE AT LAW OR IN EQUITY.  CONTRACTOR MAKES NO WARRANTIES OR GUARANTEES REGARDING THE TIME FOR COMPLETING THE WORK OR THE PERFORMANCE OF THE FACILITY OR THE EQUIPMENT, INCLUDING BUT NOT LIMITED TO, ANY GUARANTEES FOR OUTPUT, HEAT RATE, RELIABILITY, AVAILIABLITY, NOISE, OR EMISSIONS, EXCEPT AS OTHERWISE PROVIDED IN SECTION 12 ABOVE, AND OWNER HEREBY RELEASES CONTRACTOR FROM ANY AND ALL LIABILITY IN CONNECTION THEREWITH.

## Liability of Related Persons.

In the event either Owner or Contractor asserts a claim or claims against any of the other Party's partners, shareholders, Affiliates, and/or their directors, officers, agents, employees or Subcontractors (collectively, "Related Persons"), the aggregate recovery of the asserting Party pursuant to such claim or claims against a Party and its Related Persons shall, except to the extent prohibited by law, be limited by the waivers and disclaimers of liability, releases from liability, limitations on liability, indemnities, and exclusive remedy provisions set forth in this Contract, even in the event of the fault, negligence (in whole or in part), strict or absolute liability, or other basis of liability of any of the Related Persons.

# REPRESENTATIONS OF CONTRACTOR AND OWNER

## Contractor Representations.

Contractor represents and warrants that:

### Standing.   It is duly organized, validly existing and in good standing under the laws of its jurisdiction of incorporation, qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business or the performance of its obligations under this Contract.

### No Violation of Law; Litigation.  It is not in violation of any applicable Law, which violations, individually or in the aggregate, would materially and adversely affect its performance under this Contract.  There are no legal or arbitration proceedings or any proceeding by or before any court or Governmental Authority now pending or (to its best knowledge) threatened against it which, if adversely determined, could reasonably be expected to have a material adverse effect on its financial condition, operations, prospects or business as whole, or ability to perform all its obligations under this Contract.

### Governmental Authorizations.  It is (or will be prior to performing any Work for which such Governmental Authorization is required) the holder of all material Governmental Authorizations required to permit it to enter into and perform its obligations under this Contract.

### No Breach.  None of the execution and delivery of this Contract, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under its charter, bylaws or any material agreement or material instrument to which it is a party or by which it is bound or to which it or any of its respective assets are subject, or constitute a default under any such agreement or instrument.

### Authority to Act.  It has all necessary corporate power and authority to execute, deliver and perform its obligations under this Contract; its execution, delivery and performance of this Contract has been duly authorized by all necessary action on its part; and this Contract has been duly and validly executed and delivered by it and constitutes its legal, valid and binding obligation, enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar laws relating to the enforcement of creditors’ rights generally and by general equitable principles.

## Owner Representations.

Owner represents and warrants that:

### Business Organization.  It is duly organized and validly existing under the laws of its jurisdiction of formation, is qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business or the performance of its obligations under this Contract.

### No Violation of Law; Litigation.  It is not in violation of any applicable Law, which violations, individually or in the aggregate, would materially and adversely affect its performance under this Contract.  No legal or arbitration proceedings or any proceeding by or before any court or Governmental Authority are now pending or (to its best knowledge) threatened against it which, if adversely determined, reasonably could be expected to have a material adverse effect on its financial condition, operations, prospects or business, as a whole, or on its ability to perform all its obligations under this Contract.

### Governmental Authorizations.  It is the holder of all material Governmental Authorizations required to permit it to enter into and perform its obligations under this Contract.

### No Breach.  None of the execution and delivery of this Contract, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under, its charter, bylaws or any material agreement or material instrument to which it is a party or by which it is bound or to which it or its assets are subject, or constitute a default under any such agreement or instrument.

### Authority to Act.  It has all necessary partnership power and authority to execute, deliver and perform its obligations under this Contract; the execution, delivery and performance by Owner of this Contract has been duly authorized by all necessary action on its part; and this Contract has been duly and validly executed and delivered by Owner and constitutes the legal, valid and binding obligation of Owner enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar Laws relating to the enforcement of creditors’ rights generally and by general equitable principles.

# DEFAULT, TERMINATION AND SUSPENSION

## Default by Contractor.

### Termination for Contractor’s Inability to Perform.  If any proceeding is instituted against Contractor seeking to adjudicate Contractor as a bankrupt or insolvent and such proceeding is not dismissed within 30 days of filing, or if Contractor makes a general assignment for the benefit of its creditors, or if a receiver is appointed on account of the insolvency of Contractor, or if Contractor files a petition seeking to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts, or if Contractor is unable to pay its debts when due or as they mature, then Owner may terminate this Contract effective immediately upon giving written notice of such termination to Contractor.  Any such termination shall be without prejudice to any accrued rights, powers or remedies of either Party under this Contract.

### Termination for Contractor’s Failure to Perform.  If:

##### (a)	Contractor abandons the Work following NTP Effective Date; or

##### (b)	Contractor, despite previous warnings in writing from Owner, has wrongfully refused or has materially failed or neglected at any time to execute the Work in accordance with this Contract, or is failing to proceed with the Work with due diligence or is neglecting to carry out its other obligations under this Contract, in each case so as to affect materially and adversely the carrying out of the Work;

###### then, in the case of a default under Sections 15.1.2(a) or (b), provided Contractor fails to correct such condition within 30 days of receipt of written notice from Owner stating the nature of the condition and requiring Contractor to remedy the same or, if such default is not capable of being remedied within such 30 days, to diligently commence to correct such condition within 30 days of receipt of such written notice and to complete the correction within 90 days after receipt of such notice,

###### Owner may, after giving Contractor five Business Days’ notice thereof, so long as such default remains uncured, terminate this Contract, enter the Site, expel the Contractor therefrom, complete the Work or employ any other contractor (the “Replacement Contractor”), to complete the Work.  Any such termination shall be without prejudice to any accrued liability of Contractor under this Contract.

### Contractor Continuing Obligations.  If Owner elects to terminate this Contract pursuant to this Section 15.1, then as of the effective date of such termination, Contractor shall be released from any further obligation to perform the Work under this Contract and Contractor shall thereupon:

##### immediately discontinue the Work except for such Work as Owner may specify in the termination notice as may be reasonably necessary to preserve and protect Work already in progress and to protect the Owner Equipment and Contractor Equipment at the Site;

##### place no further orders or enter into Subcontracts for Work;

##### assist Owner in preparing an inventory of all the Owner Equipment and Contractor Equipment in use or in storage at the Site;

##### terminate all Subcontracts, except those Owner has designated to be assigned pursuant to Section 15.1.3(e);

##### assign to Owner or to any Replacement Contractor, title to all Work not already owned by Owner, together with all Subcontracts and other contractual agreements (including warranties) as may be designated by Owner;

##### assign to Owner or to any Replacement Contractor, to the extent assignable and further, subject to Section 8.1.3 and Section 8.1.4, all issued Governmental Authorizations, patents and other proprietary rights, if any, then held by Contractor pertaining to the Facility or the Work;

##### remove from the Site all Contractor Equipment that is not going to be taken over by the Owner; and

##### deliver to Owner all information prepared hereunder with respect to the Facility or Work as may be reasonably requested by Owner and which has been paid for by Owner, including all drawings, plans, specifications, studies, reports and other information prepared hereunder as of the date of termination for the completion and operation of the Facility.

### Owner’s Exclusive Remedy, Payment Obligations.  As soon as practicable after the Owner has terminated this Contract pursuant to this Section 15.1, the Owner shall deliver to Contractor a certificate setting forth all sums due to Owner by Contractor as of the date of termination and the value of the Work in place and materials on Site not included in prior payments to Contractor.  Any dispute by the Contractor of amounts set forth in such certificate shall be resolved pursuant to Section 18.1.  If Owner terminates this Contract pursuant to this Section 15.1, Owner shall not be liable to make any further payment to Contractor until after reaching the equivalent of Final Completion, whereupon Owner shall determine the total reasonable and necessary expenses incurred by Owner in connection with the termination of this Contract (including reasonable legal fees and expenses) and the completion of the Work (together the “Costs of Completion”), including all amounts charged by any Replacement Contractor to complete the Work in accordance with the Scope of Work and the terms of this Contract.

The Contractor shall be entitled to be paid by Owner with respect to any unpaid portion of the Contract Price attributable to the Work executed by Contractor prior to the date of termination, and the value of any unused or partially used materials on the Site furnished by Contractor which are taken over by Owner and have not already been paid for as part of the Contract Price paid to Contractor, and the costs, if any, incurred by Contractor in protecting the Work pursuant to Section 15.1.3(a), provided that any sums due to Owner from Contractor accruing prior to the date of termination shall be deducted from the amount to be paid to Contractor pursuant to the foregoing.    If the Costs of Completion exceed the balance of the Contract Price unpaid at the date of termination, then Contractor shall be liable for and shall pay to Owner upon written demand by Owner the amount of such excess, which shall constitute Owner’s sole and exclusive remedy for all damages associated with such termination pursuant to Section 15.1 and shall be subject to the Aggregate Limit.  Any such amount payable by Contractor may be deducted by Owner from any portion of the Contract Price or other amounts due to Contractor under this Section 15.1.4.

## Default by Owner.

### Termination for Owner’s Inability to Perform.  If any proceeding is instituted against Owner seeking to adjudicate Owner as a bankrupt or insolvent and such proceeding is not dismissed within 30 days of filing, or if Owner makes a general assignment for the benefit of its creditors, or if a receiver is appointed on account of the insolvency of Owner, or if Owner files a petition seeking to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts, or if Owner is unable to pay its debts when due or as they mature, then Contractor may terminate this Contract effective immediately upon giving written notice of such termination to Owner.  Any such termination shall be without prejudice to any accrued rights, powers or remedies of either Party under this Contract.

### Termination for Owner’s Failure to Perform.  If:

##### Owner fails to pay Contractor any amount due under any invoice within 10 days after the amount became due and payable,

##### Owner fails to observe or perform any of its material covenants or agreements contained in this Contract (other than for payments to Contractor), or

##### any material representation or warranty of Owner shall have been incorrect as of the date made and shall remain incorrect at the time in question,

###### then, provided Owner fails to correct such condition within 30 days of receipt of written notice from Contractor stating the nature of the condition and requiring Owner to remedy the same or, if such default is a default not capable of being remedied within such 30 days, to diligently commence to correct such condition within 30 days of receipt of such written notice and to complete the correction within 90 days after receipt of such notice,

###### Contractor may, after giving Owner five Business Days’ notice thereof, so long as such default continues uncured, terminate this Contract.  Any such termination shall be without prejudice to any accrued liability of Owner under this Contract.

### Contractor’s Remedies.  If this Contract is terminated pursuant to the provisions of this Section 15.2, the Contractor shall become entitled to receive an equitable amount in respect of the progress of the Work executed as at the date of termination.  In addition to such amount, the Contractor shall be entitled to receive, without duplication:  (A) the sum of (i) the amount of any expenditure reasonably incurred by Contractor in the expectation of the performance of this Contract subject to Contractor’s efforts to mitigate such expenditures, including amounts spent in respect of materials to be delivered to Owner that are not incorporated into the Work; (ii) the amount of any liabilities owing by Owner to Contractor as of the date of termination, and (iii) any expenditure reasonably incurred by Contractor  in consequence of the termination of this Contract (including reasonable legal fees and expenses), less (B) the amount of liabilities owing by Contractor to Owner as of the date of such termination.  Payments for termination under this Section 15.2 shall be due Contractor within 15 days of Owner’s receipt of a substantiated, itemized invoice and the delivery of any Work executed as of the date of termination.

### Removal of Contractor’s Equipment.  If this Contract is terminated pursuant to the provisions of Section 15.2.1 or 15.2.2, Contractor shall be entitled to remove immediately the Contractor Equipment and the temporary Work that is on the Site.

## Suspension of Work.

### Suspension of Work by Owner.

##### Owner may, at any time and from time to time and for any reason, by written notice to Contractor, suspend the carrying out of the Work or any part thereof.  Contractor shall, on such written notice of Owner, suspend the carrying out of the Work or any part thereof for such time and in such manner as Owner may require and shall during any such suspension properly protect and secure the Work in accordance with GIP.

##### Owner may at any time following a suspension give notice to Contractor to proceed with the Work previously suspended.

##### Upon receipt of any such notice to proceed, Contractor shall examine any Work that was adversely affected by the suspension and shall, at Owner’s expense, make good any deterioration of or damage to such Work that may have occurred during the suspension (unless resulting from any breach by Contractor of its obligations to protect and secure the Work) and, subject to Section 15.3.3, shall proceed with the Work previously suspended.

### Suspension of Work by Contractor.

##### Contractor may, by giving 15 days notice in writing to Owner, suspend the carrying out of the Work or any part thereof if Owner fails to pay Contractor any undisputed amount due under any invoice within 30 days after the amount becomes payable under this Contract, unless prior to the end of the 15 day notice period Owner has paid the overdue amount.  During any such suspension, Contractor shall properly protect and secure the Work in accordance with GIP.

##### Upon payment by Owner of such overdue amount, Contractor shall examine the Work affected by the suspension and shall, at Owner’s expense, make good any deterioration or damage to or of such Work that may have occurred during the suspension (unless resulting from any breach by Contractor of its obligations to protect and secure the Work) and, subject to Section 16.3.3, shall proceed with the Work previously suspended.

### Adjustment and Compensation for Suspension.  In the event of a suspension of the Work pursuant to this Section 15.3, Contractor and Owner shall negotiate in good faith to agree the level of staff and labor to be retained by Contractor on or near the Site and a monthly fee to be paid to Contractor by Owner during the period of any such suspension.  In the event that the Parties do not agree within 30 days following such suspension, the notice of suspension shall be treated as a Change Order Request delivered by Owner to Contractor pursuant to Section 6.2.1 and Contractor shall proceed to maintain staff and labor on or near the Site as requested by Owner subject to the provisions of Sections 6.2, including the conditions set forth in Section 6.2.5.  Upon receipt of notice to proceed pursuant to Section 15.3.1(b) or upon receipt of payment by Owner of any overdue amount pursuant to Section 15.3.2(b), as a condition to resuming the Work, Contractor shall be entitled to a Change Order pursuant to Section 6.3.1 to reflect any Changes appropriate in respect of such suspension.

# FORCE MAJEURE

## Force Majeure.

“Force Majeure” shall mean any events or circumstances, or any combination of events or circumstances, that are beyond the reasonable control of the affected party, that could not have been prevented by the exercise of reasonable skill and care, and that have, or any consequences thereof have, a material and adverse effect upon the performance by the affected party of its obligations under this Contract (including the cost and time for such performance) including the following:

##### Any act of war (whether declared or undeclared), invasion, armed conflict or act of foreign enemy, blockade, embargo, revolution, riot, religious strife or civil commotion;

##### Any sabotage, terrorism, general or organized objections, protests or unrest or the threat of any such acts;

##### Except to the extent that they constitute remedies or sanctions lawfully exercised by a Governmental Authority as a result of a breach by the affected party, its Subcontractors, servants or agents of applicable Laws, any act of state or other exercise of a sovereign or executive prerogative by any Governmental Authority, including expropriation, nationalization or compulsory acquisition and acts claimed to be justified by executive necessity;

##### Any explosion, chemical or radioactive contamination or ionizing radiation;

##### Any strike, work stoppage, slowdown or other industrial action or labor dispute, extending beyond the Site and any such actions that are not primarily motivated by the desire to influence the actions of the affected party so as to preserve or improve conditions of employment;

##### Any Change in Law, including the imposition after the NTP Effective Date  of export or import controls affecting the export or import of goods, materials, equipment or technical data for incorporation in the Facility or Work;

##### Any lightning, earthquake, tempest, flooding, fire, cyclone, hurricane, typhoon, tidal waves, whirlwind, storm, drought or lack of water and other unusual or extremely adverse weather or environmental conditions or action of the elements, meteorites, aircraft or objects falling from aircraft or other aerial devices, the occurrence of pressure waves caused by aircraft or other aerial devices traveling at supersonic speeds;

##### epidemic or plague;

##### act of God; and

##### to the extent that the same are caused by events or circumstances that are themselves a Force Majeure, shortage of labor; delay in delivery, loss or damage to materials or Equipment or Contractor’s Equipment in transit or on Site; delay in performance of a Subcontractor and breakdown of Equipment or Contractor’s Equipment.

## Excused Performance.

Except for the obligation to timely pay money for Work actually performed or for other payment obligations or liabilities hereunder, either Party shall be excused from the performance or delay in performance of its obligations hereunder (and shall not be considered to be in default with respect thereto) if and to the extent that its failure to perform or delay in the performance of each such obligation is due to Force Majeure, provided, that:

##### the affected Party gives the other Party written notice describing in reasonable detail, to the extent then available, the Force Majeure as soon as is reasonably practicable, but in no event later than ten (10) days after such Party first becomes aware of the occurrence or commencement of such Force Majeure; and

##### the suspension of performance is of no greater scope and of no longer duration than is reasonably required by the Force Majeure, including a reasonable recovery period within which to restart performance.

## Performance Continuation.

Upon the occurrence of any Force Majeure, Contractor shall use reasonable efforts to continue to perform its obligations under this Contract and to minimize the adverse effects of such circumstances.  Contractor shall notify Owner of the steps it proposes to take, including any reasonable alternative means for performance.

## Change Order Consequences of Force Majeure.

Upon the occurrence of any Force Majeure, Contractor shall be entitled to a Change Order pursuant to Article 6 under which Contractor shall be entitled to a day-for-day extension to the Schedule, Schedule Guaranty and Guaranteed Completion Date and reimbursed for all additional costs reasonably incurred by Contractor in performance of its obligations under Section 16.3 and shall receive appropriate Changes in respect of such Force Majeure.

## Suspension of the Work, Resumption of Performance.

Subject to Section 15.3.1 (Owner’s Suspension) and Section 16.4 (Change Order Consequences of Force Majeure), in the event of a suspension of the Work due to a Force Majeure, Contractor and Owner shall negotiate in good faith to agree the level of staff and labor to be retained by Contractor on or near the Site and a monthly fee to be paid to Contractor by Owner during the period of any such suspension.  In the event that the Parties do not agree within thirty days following such suspension, the continuing suspension shall be treated as a Change Order Request delivered by Owner to Contractor pursuant to Section 6.2.1, and Contractor shall proceed to maintain staff and labor on or near the Site as requested by Owner subject to the provisions of Section 6.2, including the conditions set forth in Section 6.2.5.  When a Party whose performance has been suspended due to Force Majeure becomes able to resume performance of its obligations under this Contract, such Party shall give the other Party written notice to that effect and shall promptly resume performance hereunder; provided, however, Contractor’s resumption of performance is further subject to the agreement and execution by both Parties of an appropriate Change Order pursuant to Section 16.4.

## Termination for Force Majeure.

Notwithstanding that Contractor may have become entitled to an extension of time in which to perform its obligations hereunder due to Force Majeure, if by virtue of Section 16.2 either Party shall have been  excused from the performance of any material obligation under this Contract for a continuous period of 12 months or performance of the Work shall have been suspended for two or more non-continuous periods that in the aggregate exceed 12 months occurring following NTP Effective Date, then either Party may at any time thereafter, provided such performance is still excused, by notice to the other terminate this Contract.  In the event of a termination under this Section 16.6, as of the effective date of termination, Contractor shall be released from any further obligation to perform the Work and Contractor shall thereupon:

##### immediately discontinue the Work except for such Work as may be reasonably necessary to preserve and protect Work already in progress and to protect the Owner Equipment and Contractor Equipment at the Site;

##### place no further orders or enter into Subcontracts for Work;

##### assist Owner in preparing an inventory of all Contractor Equipment and Owner Equipment in use or in storage at the Site;

##### terminate all Subcontracts, except those Owner has designated to be assigned pursuant to Section 16.6(e);

##### assign to Owner title to all Work not already owned by Owner, together with all Subcontracts and other contractual agreements (including warranties) as may be designated by Owner;

##### assign to Owner, to the extent assignable and further subject to Section 8.1.3 and Section 8.1.4, all issued Governmental Authorizations, patents and other proprietary rights, if any, then held by Contractor pertaining to the Facility;

##### remove from the Site all Contractor’s Equipment subject to the consent of Owner; and

##### deliver to Owner all information prepared hereunder with respect to the Facility or Work as may be reasonably requested by Owner and which has been paid for by Owner, including all drawings, plans, specifications, studies, reports and other information prepared hereunder as of the date of termination for the completion and operation of the Facility.

## Payment on Termination.

If this Contract is terminated pursuant to Section 16.6, Owner shall pay to Contractor the sum of the following:

##### An equitable amount in respect of the progress of the Work executed as of the date of termination and for the Contractor Equipment which will remain at the Site;

##### Any unpaid standby costs incurred by the Contractor to the date of termination;

##### Without duplication, the amount of any expenditure reasonably incurred by Contractor in the expectation of the performance of this Contract, including amounts spent in respect of materials to be delivered to Owner that are not incorporated into the Work; and

##### Without duplication, the amount of any expenditure reasonably incurred by Contractor in consequence of the termination of this Contract, including (i) amounts spent in performance of Contractor’s obligations under Section 16.6, and (ii) all reasonable costs of demobilization, including removal of any Contractor Equipment.

# INDEMNITIES

## Contractor Indemnity.

Contractor agrees to indemnify, defend and hold harmless Owner Indemnitees from and against any and all claims, demands, losses, damages, causes of action, suits, and liabilities (including all expenses of litigation, court costs and reasonable attorneys’ fees):

##### attributable to bodily injury (including death) of any person or property damage of third parties to the extent caused by the negligence or willful misconduct of any of the Contractor Indemnitees, or

##### attributable to any bodily injury (including death) or property damage (including property of Contractor, Owner and third parties) caused by any spill or release of Hazardous Substances for which Contractor is responsible under Section 3.15 other than any such spill or release caused by the negligence or willful misconduct of any Owner Indemnitee,

## Owner Indemnity.

Owner agrees to indemnify, defend and hold harmless Contractor Indemnitees from and against any and all claims, demands, losses, damages, causes of action, suits, and liabilities (including all expenses of litigation, court costs and reasonable attorneys’ fees):

##### attributable to bodily injury (including death) of any person or property damage of third parties to the extent caused by the negligence or willful misconduct of any of the Owner Indemnitees, or

##### attributable to bodily injury (including death) or property damage (including property of any Contractor Indemnitee and of third parties) caused by any Hazardous Substances for which Owner is responsible under Section 3.15 unless such injury or damage is caused by the negligence or willful misconduct of any Contractor Indemnitee.

## Notice.

Each Party shall promptly notify the other in writing of any claims which may be covered by the indemnities set forth in this Article 17.  Without limiting the generality of the foregoing, Owner shall notify Contractor in writing as soon as Owner shall receive notice of any claims of infringement of patents or other proprietary rights occurring in connection with Contractor’s performance of the Work.  In turn, Contractor shall timely notify Owner in writing of any claims which Contractor may receive alleging infringement of patents or other proprietary rights which may affect Contractor’s performance of the Work.

## Conduct and Administration of Claims.

The indemnifying Party, under Section 17.1, 17.2, or 17.3 (the “Indemnitor”) shall have sole charge and direction of conduct of the prosecution, defense and settlement of any suit or proceeding based on any claim, demand, loss, damage, cause of action, suit on liability for which Indemnitor is responsible under any such Section.  The indemnified Party (the “Indemnitee”) shall provide such assistance as the Indemnitor may reasonably require in such defense, and shall have the right to be represented in such defense by counsel of its own choice at its own expense.  If the Indemnitor fails to defend any such suit or proceeding, then following 15 days notice to Indemnitor of such election, the Indemnitee shall have the right, in its reasonable discretion, either to defend such suit or proceeding or to settle the claim which is the basis thereof, without further consent from the Indemnitor and without releasing the Indemnitor from its obligations under Sections 17.1, 17.2 and 17.3, and in either case the Indemnitor shall reimburse the Indemnitee for its expenses, costs and reasonable attorneys’ fees.  If any claim described in Section 17.3 is held to constitute an infringement of any patent or other proprietary rights and use of any Work is enjoined, Contractor shall at its own expense and at Contractor’s option (i) procure for Owner the right to continue to use the infringing Work, (ii) replace such Work with non-infringing equipment or process of equivalent utility and efficiency, or (iii) modify such Work so that it becomes non-infringing without affecting its utility or efficiency.

# DISPUTE RESOLUTION

## Arbitration.

Except for remedies regarding Confidential Information under Section 19.4, any claim, dispute or controversy arising out of or relating to this Contract or the breach, termination or repudiation thereof shall be resolved exclusively by submission to binding arbitration in either Houston, Texas or Panama City, Panama administered by the International Chamber of Commerce (“ICC”) in accordance with its rules then in effect, and the language of such arbitration shall be English.  There shall be three arbitrators, with each Party selecting one; the third arbitrator, who shall be the chairman of the panel and need not be a national of a country other than those of the Parties, shall be selected by the two arbitrators appointed by the Parties.  The claimant shall name its arbitrator in the demand for arbitration and the responding Party shall name its arbitrator within 30 days after receipt of the demand for arbitration.  The third arbitrator shall be named by the first two arbitrators within 30 days after the appointment of the second arbitrator.  Each arbitrator must be qualified by having at least 10 years’ experience in the construction and engineering of power generation facilities or in the electric utility industry.  Should any Party fail timely to name its arbitrator or should the first two arbitrators named fail timely to name a third arbitrator, any such arbitrator not timely named shall be appointed by the ICC.  The arbitration proceeding and all correspondence and documents submitted thereto shall be conducted and prepared in the English language.  The award of the arbitrators shall be based upon principles of law and shall be final and binding upon the Parties without the right of appeal to the courts.  Judgment on the award may be entered by any court having jurisdiction thereof.  The costs and expenses of the arbitration (including reasonable attorney’s fees) shall be borne by the losing Party, unless the arbitrators determine that it would be manifestly unfair to honor this agreement of the Parties and determine a different allocation of costs.

## Submission to Jurisdiction.

This Article 18 and any arbitral award hereunder shall be enforceable, and any action in aid of dispute resolution hereunder may be brought, in any federal or state court in the United States having jurisdiction, and the Parties each consent to the nonexclusive jurisdiction of, and to the laying of venue in, such court for such purpose.  Each Party irrevocably waives any objection to this venue on any ground, including that it is an inconvenient forum.

## Applicable Law; Waiver of Punitive Damages.

All procedural aspects of the agreement to arbitrate, including, but not limited to, the construction and interpretation of the agreement to arbitrate, the scope of the arbitrable issues, allegations of waiver, delay, or other defenses as to arbitrability, and the rules governing the conduct of the arbitration, shall be governed by and construed pursuant to the rules of the ICC.  In deciding the substance of any such claim, dispute or controversy, the arbitrators shall apply the substantive laws of the United States without reference to any rule thereof that would require the application of the law of another jurisdiction; provided, however, that the arbitrators shall have no authority to award punitive damages under any circumstances (whether it be exemplary damages, treble damages, or any other penalty or punitive type of damages) regardless of whether such damages may be available under any law, the Parties hereby waiving their right, if any, to recover punitive damages in connection with any such claims, disputes or disagreements.

## Continuation of Services.

Except as otherwise provided hereunder, pending final resolution of any dispute, whether or not submitted to arbitration hereunder, the Parties shall continue to fulfill their respective obligations under this Contract.

# CONFIDENTIAL INFORMATION

## Confidential Information.

From the Effective Date until two (2) years following Substantial Completion or the earlier termination of this Contract, neither Contractor, Owner nor any licensee of Owner pursuant to Section 8.1.4 shall disclose any Confidential Information other than to its Representatives, to the arbitrators in any arbitration pursuant to Section 18.2 and to any court (with an appropriate protective order) in any litigation pursuant to Section 18.3 or Section 19.4.  “Representatives,” as used in this Contract, shall include Affiliates, Subcontractors, and their respective directors, officers, employees, auditors, and counsel. It is understood (a) that any Representative receiving Confidential Information shall be informed of the obligation of nondisclosure pursuant to this Contract and (b) Owner and Contractor each shall be responsible for any breach of this Contract by its Representatives.

## Notice Preceding Compelled Disclosure.

If Contractor, Owner or any Representative of either is requested or required (by oral question, interrogatory, request for information or documents, subpoena, civil investigative demand or other law or legal process) to disclose any Confidential Information, such Party will promptly notify the other Party of such request or requirement so that the other Party may seek an injunction, appropriate protective order or grant a waiver of compliance with the provisions of this Contract.  If, in the absence of an injunction, protective order or the receipt of a waiver hereunder, such Party is compelled by such law or legal process to disclose any Confidential Information, then such Party may disclose only such of the Confidential Information as is required, provided that if it exercises reasonable efforts to obtain an order or other reliable assurance that confidential treatment will be accorded to the disclosed Confidential Information, there shall be no liability for the disclosure of Confidential Information pursuant to this sentence.

## Definition of “Confidential Information”.

The term “Confidential Information” shall mean all written information relating to the Facility and furnished by one Party to the other after the Effective Date of this Contract. Confidential Information also shall include all written information generated by a Party or its Representatives that contains, reflects or is derived from furnished Confidential Information.  The term “written information” shall include information recorded or stored in a digital format on electronic, magnetic or optical media.  The following shall not constitute Confidential Information for purposes of this Contract: (a) information that is or becomes publicly available other than as a result of a disclosure in violation of this Contract, (b) information that already was known to the recipient prior to being furnished pursuant to this Contract, and (c) information that becomes available on a non-confidential basis from a source other than the disclosing Party if such source was not subject to any prohibition against transmitting the information to the recipient.

## Remedies.

Money damages would not be a sufficient remedy for any breach of the above provisions of this Article 19 and the disclosing Party shall be entitled to seek specific performance and injunctive relief as remedies for any such breach.  Such remedies shall not be deemed to be the exclusive remedies for any such breach, but shall be in addition to all other remedies available at law or in equity.  The Parties agree that any action or application for such remedies may be brought either in a federal or state court in the United States having jurisdiction, and the Parties each consent to the nonexclusive jurisdiction of, and to the laying of venue in, such court for such purpose.  Each Party irrevocably waives any objection to this venue on any ground, including that it is an inconvenient forum.

# MISCELLANEOUS PROVISIONS

## Governing Law.

This Contract shall be governed by, construed and enforced in accordance with, the laws of the United States (without giving effect to the principles thereof relating to conflicts of laws).  The Parties further agree that the United Nations Convention on the International Sale of Goods does not apply to this Contract.

## Notice.

Any notice, demand, offer, correspondence, email, or other written instrument required or permitted to be given pursuant to this Contract shall be in writing signed by the Party giving such notice and shall be in the English language and shall be hand delivered or sent by registered letter or telefax (subject to confirmation of receipt) to the address or telefax number set forth below.

To Owner:

Electricidad de Caracas

_________________________

_________________________

_________________________

Attn: _____________________

Telefax: __________________

To Contractor:

ProEnergy EPC Services LLC

2031 Adams Road

Sedalia, Missouri 65301

Attn: Jeff Canon

Telefax: 660-829-1160

and

Derwick Associates, S.A.

_________________________

_________________________

_________________________

Attn: _____________________

Telefax: __________________

Each Party to this Contract shall have the right to change the place to which notice shall be sent or delivered by similar notice sent in like manner to the other Party.  The effective date of a notice issued pursuant to this Contract shall be as of the addressee’s receipt of such notice.

## Assignment.

Except as set forth hereinafter in this Section 20.3, this Contract may be assigned only with the prior written consent of the other Party to this Contract.  Contractor may assign this Contract to any Affiliate of Contractor; provided that such Affiliate assumes Contractor’s obligations under this Contract and Contractor unconditionally guarantees the performance of such Affiliate’s obligations under this Contract.  Any purported assignment not in compliance with this Section 20.3 shall be void and without force or effect.

## No Unlawful Payments.

Contractor and Owner each covenants and agrees not to act in violation of the U.S. Foreign Corrupt Practices Act, and in connection therewith, shall not directly or indirectly receive, authorize, make, or promise to make any offer, payment, or gift of anything of value that would violate the laws of the United States of America, or the laws of the country or countries in which any of the Work is performed, to or for the use or benefit of (a) any official, candidate for political office, or employee of any agency or instrumentality of any government, political party, public international organization, or any other Person, or (b) any Person, while knowing that all or a portion of such money or thing of value will be directly or indirectly offered, given, or promised to any official, candidate for political office, or employee of any agency or instrumentality of any government, political party, public international organization, or any other Person.

Contractor agrees to indemnify, defend and hold harmless Owner Indemnitees from and against any and all fines, penalties, related costs and expenses, including reasonable legal expenses, attributable to any failure of Contractor (including its Subcontractors and their officers, directors, and representatives) to comply with this Section 20.4.  Owner agrees to indemnify, defend and hold harmless Contractor Indemnitees from and against any and all fines, penalties, related costs and expenses, including reasonable legal expenses, attributable to any failure of any of the Owner Indemnitees or any direct or indirect owners of or investors in Owner to comply with this Section 20.4.

## Miscellaneous.

### Entire Agreement.  This Contract contains the entire understanding of the Parties with respect to the subject matter hereof and reflects the prior agreements and commitments with respect thereto.  There are no other oral understandings, terms or conditions and neither Party has relied upon any representation, express or implied, not contained in this Contract.  All communications, whether in writing or oral, between the Parties shall be in the English language.

### Amendments.  No change, amendment or modification of this Contract shall be valid or binding upon the Parties hereto unless such change, amendment or modification shall be in writing and duly executed by both Parties hereto.

### Joint Effort.  Preparation of this Contract has been a joint effort of the Parties and the resulting document shall not be construed more severely against one of the Parties than against the other.

### Captions.  The captions contained in this Contract are for convenience and reference only and in no way define, describe, extend or limit the scope of intent of this Contract or the intent of any provision contained herein.

### Severability.  The invalidity of one or more phrases, sentences, clauses, sections or articles contained in this Contract shall not affect the validity of the remaining portions of the Contract so long as the material purposes of this Contract can be determined and effectuated. If any material provision is held to be invalid, the Parties agree to negotiate an equitable amendment to the provisions of this Contract to give effect to the underlying purposes of the invalid portion or provisions of this Contract.

### No Waiver.  Any failure of any Party to enforce any of the provisions of this Contract or to require compliance with any of its terms at any time during the pendency of this Contract shall in no way affect the validity of this Contract, or any part hereof, and shall not be deemed a waiver of the right of such Party thereafter to enforce such provisions or require compliance with such terms.

### Successors and Assigns.  This Contract shall be binding upon and shall inure to the benefit of the Parties hereto and their successors and permitted assigns.

### Obligations.  Nothing contained in this Contract shall be construed as constituting a joint venture or partnership between Contractor and Owner.

### Further Assurances.  Contractor and Owner agree to provide such information, execute and deliver any instruments and documents and to take such other actions as may be necessary or reasonably requested by the other Party that are not inconsistent with the provisions of this Contract and that do not involve the assumptions of obligations other than those provided for in this Contract, in order to give full effect to this Contract and to carry out the intent of this Contract.

### 20.5.10	Performance of Obligations.  If an obligation to be performed under this Contract falls due on a day other than a Business Day, the obligation shall be due on the next Business Day.

### Exhibits, Schedules.  Subject to Section 20.5.12, all exhibits and schedules referenced in this Contract shall be incorporated into this Contract by such reference.

### Priority.  In the event of any conflict or inconsistency between the body of this Contract and the exhibits, attachments and schedules incorporated herein or any other incorporated or associated documentation, the terms and conditions of this Contract shall control notwithstanding such incorporation.

### Counterparts.  This Contract may be signed in any number of counterparts and each counterpart shall represent a fully executed original as if signed by both Parties.

### 20.5.14 Survival, Termination of Obligations.  The indemnities set forth in this Contract shall survive the completion of the Work and any termination of this Contract; provided, however, that on the earlier of the date two years following (i) Substantial Completion or (ii) the termination of this Contract, all liability of Owner and Contractor under this Contract shall fully terminate and expire except for any liability for claims that are the subject of litigation or other proceedings pending on such date.

IN WITNESS WHEREOF, Owner and Contractor executed this Contract as of the date first written above.

Owner:

ELECTRICIDAD DE CARACAS

By:___________________

Name:_________________

Title:__________________

Contractor:

DERWICK – PROENERGY CONSORTIUM

By;	DERWICK ASSOCIATES, S.A.

- By:_______________________

Name:_____________________

Title:______________________

By:	PROENERGY EPC SERVICES LLC

- By:_______________________

Name:_____________________

Title:______________________

EXHIBIT A

TECHNICAL SCOPE DOCMENT (TSD)

EXHIBIT A-1

TSD FOR LM2500 GAS TURBINES

EXHIBIT A-2

TSD FOR LM6000 GAS TURBINES

EXHIBIT B

PAYMENT SCHEDULE

EXHIBIT B-1

PAYMENT SCHEDULE FOR LM2500 GAS TURBINES

EXHIBIT B-2

PAYMENT SCHEDULE FOR LM6000 GAS TURBINES

EXHIBIT C

INSURANCE

1.0.	Contractor’s Insurance

1.1	Workers' Compensation and Employers' Liability Insurance.  Contractor shall (i) maintain workers' compensation insurance as required by the law of the jurisdiction where the Work is performed, and (ii) maintain employers' liability insurance with a $1,000,000 minimum limit per accident.

1.2	Commercial General Liability Insurance.  Contractor shall procure and carry commercial general liability insurance on a claims made or occurrence basis against claims for personal injury (including bodily injury and death) and property damage.  Such insurance shall provide coverage for products-completed operations, blanket contractual, premises/operation, explosion, collapse and underground hazard coverage, broad form property damage, broad form contractual liability, personal injury insurance, independent contractors liability, hostile fire liability and include a severability of interests or cross liability clause.  The policy shall provide for a $2,000,000 minimum limit per occurrence and $2,000,000 minimum limit in the aggregate.

1.3	Automobile Liability Insurance.  Contractor shall procure and carry liability insurance against claims for personal injury (including bodily injury and death) and property damage covering all vehicles owned, leased or non-owned and hired by the Contractor, including loading and unloading, with a $1,000,000 minimum limit per occurrence.

  - Excess Liability Insurance.  Contractor shall procure and carry excess liability insurance on a claims made or occurrence basis against claims for personal injury (including bodily injury and death) and property damage and applying in excess of the limits of insurance prescribed for the policies required in Sections 1.1 (ii), 1.2, and 1.3 .  Such insurance shall provide coverage for products-completed operations, blanket contractual, premises/operation, explosion, collapse and underground hazard coverage, broad form property damage, broad form contractual liability, personal injury insurance, independent contractors liability, hostile fire liability and include a severability of interests or cross liability clause.  The policy shall provide for a $5,000,000 minimum limit per occurrence and $5,000,000 minimum limit in the aggregate.

2.0	Owner’s Insurance

2.1	Builders “All Risk” Insurance.  Prior to the commencement of any construction activities and continuing until Substantial Completion, the Owner shall procure and maintain from an insurance provider reasonably acceptable to the Contractor, and keep in force a policy or policies (which shall not be cancelable) of builder's "all risk" insurance with respect to the construction of the Facility written on a commercially recognized policy form, providing coverage for the Equipment and Facility in a minimum amount equal to the "full insurable value" of the Owner Equipment, Contractor Equipment and Facility, including any additional costs which are normally insured under such policy.  For purposes of this Section 2.1, "full insurable value" shall mean the full replacement value of the Owner Equipment, Contractor Equipment and the Facility upon completion of construction of the Facility.  The insurance coverage shall include boiler and machinery insurance on a comprehensive basis including coverage against damage or loss caused by earth movement (including but not limited to earthquake, landslide, subsidence and volcanic eruption), flood and hurricanes, and coverage against damage or loss caused by turbine and machinery accidents and operational and performance testing, commissioning and start-up, with extended coverage, and providing coverage for transit, including ocean marine transit, if applicable, with sublimits sufficient to insure the full replacement value of the property or equipment removed from the  Site and while located away from the Site.

Such insurance shall (i) not include any coinsurance provision; (ii) provide for increased cost of construction and loss to undamaged property as the result of enforcement of building laws; (iii) include costs for removal of debris; (iv) include extended maintenance coverage for a minimum period of twelve (12) months following Substantial Completion; and (v) include an extension or otherwise provide coverage for physical damage to the Facility including physical damage to assets at the Site relating to the phased-in operational exposures during the construction term.  The property damage coverage shall not contain an exclusion for freezing, mechanical breakdown, resultant loss or damage caused by faulty workmanship, design or materials.

2.2	Workers' Compensation and Employers' Liability Insurance. Owner shall (i) maintain workers' compensation insurance as required by the law of the jurisdiction where the Work is performed, and (ii) maintain employers' liability insurance with a $1,000,000 minimum limit per accident.

2.3	Commercial General Liability Insurance.  Owner shall procure and carry commercial general liability insurance on a claims made or occurrence basis against claims for personal injury (including bodily injury and death) and property damage.  Such insurance shall provide coverage for products-completed operations, blanket contractual, premises/operation, explosion, collapse and underground hazard coverage, broad form property damage, broad form contractual liability, personal injury insurance, independent contractors liability and hostile fire liability with a $2,000,000 minimum limit per occurrence and $2,000,000 minimum limit in the aggregate.

2.4	Automobile Liability Insurance.  Owner shall maintain liability insurance against claims for personal injury (including bodily injury and death) and property damage covering all vehicles owned, leased or non-owned and hired by the Owner, including loading and unloading, with a $1,000,000 minimum limit per occurrence.

2.5	Excess Liability Insurance.  Owner shall procure and carry excess liability insurance on a claims made or occurrence basis against claims for personal injury (including bodily injury and death) and property damage and applying in excess of the limits of insurance prescribed for the policies required in Section 2.2(ii), 2.3 and 2.4.  Such insurance shall provide coverage for products-completed operations, blanket contractual, premises/operation, explosion, collapse and underground hazard coverage, broad form property damage, broad form contractual liability, personal injury insurance, independent contractors liability and hostile fire liability with a $5,000,000 minimum limit per occurrence and $5,000,000 minimum limit in the aggregate.