## CO Log
CHANGE ORDER LOG
Project Name: | Tacoa Power Plant
Project Number: | T-9003- A&B
Client: | Derwick Associates
Revision Date: | October 18th, 2010
Change Order Number | Date Submitted | Description | Type | Portion in VEBF's | Portion in USD
T-9003A-CO-000 | 2010-06-01 | Calgary Unit Inspection and Repaired. | T&M | 0 | 369431
T-9003A-CO-001 | 2010-06-01 | Relocation of Liquid Fuel Offloading Station | Fixed Price |  | 42188
T-9003A-CO-002 | 2010-06-01 | Lay down area for material delivery | Fixed Price | 348147 | 19650
T-9003A-CO-003 | 2010-06-01 | Delay in drawing review by Asincro | Fixed Price |  | 25313
T-9003A-CO-004 | 2010-06-01 | Delay in getting Manuals fo the LM 6000 by Asincro | Fixed Price |  | 25313
T-9003A-CO-005 | 2010-06-01 | Delay in receiving plant existing drawing from Asincro | Fixed Price |  | 16850
T-9003A-CO-006 | 2010-06-01 | Delay in appoval for high line relocation | Fixed Price |  | 20250
T-9003A-CO-007 | 2010-06-01 | Delay by Asincro for not having IFC Drawings | Fixed Price |  | 19125
T-9003A-CO-008 | 2010-06-01 | Relocate LM 6000 Gas compressors | Fixed Price | 375921 | 47653
T-9003A-CO-009 | 2010-06-01 | Existing Oil Line removal | Fixed Price | 521980 | 64969
T-9003A-CO-010 | 2010-06-01 | Addition of GSU Protection Panel to 2500 Units | Fixed Price | 416500 | 293194
T-9003A-CO-011 | 2010-06-01 | Road around units 100 and 200 per Asincro / EDC request | Fixed Price | 632986 | 100406
T-9003A-CO-012 | 2010-06-01 | Hot tap into the main Gas line | Fixed Price | 360269 | 27844
T-9003A-CO-013 | 2010-06-01 | Routing and Spec changes to LM2500 13.8 KV Feeder Cable from the GTG breakers to EDC GSU transformers | Fixed Price | 828100 | 1061000
T-9003A-CO-014 | 2010-06-01 | LM 6000 69KV Feeder and Inter Tie with the EDC Transmission Line | Fixed Price | 557375 | 599236
T-9003A-CO-015 | 2010-06-01 | LM 6000 Gas Compressor Instrumentation Upgrade | Fixed Price |  | 86438
T-9003A-CO-016 | 2010-06-01 | Extra Work Support to Improve COD date | T&M | 22026100 | 2549102
T-9003 A-CO-16A | 2010-09-01 | Extra Work Support - LM2500 Operations and Maintenace March15th to October 8th | T&M |  | 1248865
T-9003B-CO-017 | 2010-06-01 | Movement of Magallenes/Arrecifes Power Lines | Fixed Price | 2294837.86
T-9003A-CO-018 | 2010-06-01 | Gas Filled line Removal | Fixed Price | 0
T-9003A-CO-019 |  | Foundation for new transformer at existing Tacoa Plant | Fixed Price | 0
T-9003A-CO-020 |  | Addition of Southeast Containment wall | Fixed Price | 2751114.12
T-9003A-CO-021 |  | Suppor to Derwick for GSUs 1/2 Dressing Up | Fixed Price
T-9003A-CO-022 |  | Client requested existing GSUs be refurbished | Fixed Price | 831414 | 22813
T-9003A-CO-023 |  | Assemble Client provided GSU | Fixed Price
T-9003A-CO-024 |  | GE field Service Technican to site | T&M |  | 18400
T-9003B-CO-025 | 2010-09-19 | Supply 2 New fuel Tanks | Fixed Price | 1789700 | 226040
T-9003B-CO-026 | 2010-09-19 | Temporary Communications from Barra 3 to Sub 2 | Fixed Price | 745000 | 154910
T-9003B-CO-027 |  | Additional Demin Water for Unit 200
T-9003A&B-CO-028 | 2010-09-19 | Addition of North wall | Fixed Price | 20883311 | 485290
T9003A&B-CO-029 |  | LM2500 Engine repairs due to truck | Fixed Price |  | 1247229
T903A&B-CO-030 |  | Main Control Room additions | Fixed Price | 1240313 | 100406
T9003A&B-CO-031 |  | Extension of project | Fixed Price |  | 1576875
T9003A&B-CO-032
T9003A&B-CO-033
Total |  |  |  | 56603067.98 | 10448790
Current Status Legend:
| Approved | Client has approved Change Order. PES to proceed with scope.
| Rejected - Resubmit | Client has rejected change order. PES to resubmit with additional support
| Rejected - Withdrawn | Client has rejected change order. PES to perform work, will not resubmit Change Order.
| Rejected - Do Not Proceed | Client has instructed ProEnergy not to perform this scope
| Submitted | Change Order is in Client's hands for approval
| Pending | PES is preparing Change Order
| Variance | PES has identified a potential Change Order scope for internal review. Not yet on Change Order Paper