TABLE OF CONTENTS

INTRODUCTION

1.0	PROJECT DESCRIPTION

2.0	ORGANIZATION

3.0	REPORTING PROCEDURES

4.0	PROJECT MEETINGS

5.0	PROJECT FILES

6.0	DRAWING APPROVAL

7.0	MATERIAL AND PROCUREMENT PROCEDURES

8.0	QUALITY ASSURANCE / QUALITY CONTROL

9.0	COMMISSIONING, STARTUP, TESTING, AND TURNOVER

10.0	PERFORMANCE TESTING

11.0	OPERATOR TRAINING

INTRODUCTION

The following Project Procedures Manual has been prepared as an information resource for the ProEnergy EPC Services’ Project Team and the Owner’s Representatives.  This manual defines the actual steps or procedures which will be followed in bringing this project to fruition in a timely manner.  These procedures have been developed over several years and offer a proven methodology in implementing projects.

1.0	PROJECT DESCRIPTION

The Project encompasses the engineering, procurement, construction, commissioning and training for the installation of two (2) General Electric Model LM2500 PE Gas Turbine Generators including additional auxiliary and balance of plant equipment.  ProEnergy EPC Services will supply a turnkey power plant in accordance with the Tacoa Power Project Technical Scope Document.  ProEnergy EPC Services will provide installation, commissioning, testing and training.  ProEnergy EPC Services is to bring the site at finish grade, and install all concrete foundations.

2.0	ORGANIZATION

The overall project organization, depicting the relationship of all parties, is set forth in Figure 2.1 on the following page.

Owner / Owner’s Rep

Project Technical Consultants

WT Stewart – Technical Director

JD Patten – Electrical / I&C

Project Manager

TBD

Administrative

TBD

Start Up

Manager

TBD

Construction Manager

TBD

Scheduler

TBD

Project Engineer

TBD

DCS

TBD

QA/QC

TBD

Inspectors

TBD

Equipment

Erection

Superintendent

TBD

Civil

TBD

Mechanical

TBD

Electrical

TBD

I & C

TBD

Figure 2.1 Organization Chart

3.0	REPORTING PROCEDURES

3.1	General

This section addresses project communications, and reports.  All documents should include the project title, ProEnergy EPC Services’ project number, and date the document was sent or received.  One copy of all correspondence will be sent to the ProEnergy EPC Services’ project file.

3.2	Letters, Emails and Facsimiles

During all phases of the project, letters to the Owner’s Representatives regarding contract and fiscal issues should be addressed to ______________________.  Letters regarding technical and project issues should be addressed to ________________________.

Letters to ProEnergy EPC Services should be addressed to the ProEnergy EPC Services’ Project Manager.  If possible, letters should cover only one subject.  Contract and fiscal issues should be copied to Mr. Kent McAllister.  Technical and project issues should be copied to Mr. W.T. Stewart Sr.

All ProEnergy EPC Services’ originated letters and facsimiles will be sequentially numbered.  All correspondence will be maintained in the project files.

3.3	Minutes of Meetings

It is ProEnergy EPC Services responsibility to prepare written minutes for all meetings.  Minutes must include date, subject(s), and attendees.  Copies should be made available to all attendees, Owner’s Representatives, ProEnergy EPC Services’ Project Team, and the Project file.

3.4	Transmittals

All drawings and specifications sent outside ProEnergy EPC Services’ office will be sent with a written transmittal.  The transmittal will include the date and a list of transmitted documents.  A copy of the transmittal along with the documents (if applicable) will be kept in the ProEnergy EPC Services’ Project file.

3.5	Reports

Internal reports to be generated during the Engineering and Construction Phases of the project are as follows:

3.5.1	Design and Procurement Phase

- Project Status Report					Weekly

- Material Procurement Status Report			Weekly

- Project Schedule						Weekly

3.5.2	Construction Phase

- Project Status Report					Weekly

- Daily Project Status Report				Daily

- Daily QA/QC Report					Daily

- Action List Update						Daily

3.5.3	External reporting to Owners as follows (Construction Phase):

- Project Status Report					Weekly

- Project Schedule						Weekly

  - Distribution List

| Name Address City, State Phone: Fax: Email: | Name Address City, State Phone: Fax: Email: |
| --- | --- |
| Name Address City, State Phone: Fax: Email: | Name Address City, State Phone: Fax: Email: |
| Mr. Kent McAllister Director Marketing and Operations ProEnergy EPC Services 907 S. Detroit, Suite 1140 Tulsa, OK 74120 Phone: 660-829-5100 FAX: 918-270-2939 kmcallister@proenergyservices.com | Mr. W.T. Stewart Sr. Technical Director ProEnergy EPC Services 907 S. Detroit, Suite 1140 Tulsa, OK 74120 Phone: 660-829-5100 FAX: 918-270-2939 Email: wtstewart@proenergyservices.com |

4.0	PROJECT MEETINGS

Weekly project team meetings will be held in ProEnergy EPC Services’ Tulsa office.  Meetings are tentatively scheduled for Tuesday.  Minutes of each meeting will be issued and distributed on Wednesday following each meeting.  The Project Status Report will be generated as a result of the weekly meeting.

During the Design and Procurement phase of the Project, the meetings will be held at ProEnergy EPC Services’ Tulsa office.  Upon commencement of the Construction phase, the meetings will be held at either the Tulsa office or the job site (whichever is more appropriate).  These meetings will include ProEnergy EPC Services site management, and Client representatives are invited.

During the Construction phase, there will be weekly Safety meetings at site along with the weekly project team meetings.  Daily Action List meetings will be held in the ProEnergy EPC Services’ Tulsa office or at site.

5.0	PROJECT FILES

A project file system will be maintained.  A copy of all pertinent project information will be kept in this file.

6.0	DRAWING APPROVAL

The following drawings will be submitted for client approval:

- Area Plot Plan

- Process Flow Diagram

- Process and Instrumentation Diagrams

- 138 kV One Line Diagram(s)

- 4.160 kV One Line Diagram(s)

- Control/Office Building Architecture Drawing

Any drawing not returned with comment and/or change within the above listed comment period will be considered approved.

7.0	MATERIAL AND PROCUREMENT PROCEDURES

This section details procedures that shall be implemented by the ProEnergy EPC Services purchasing department.

7.1	Purchasing Manager

The Purchasing or Project Manager is directly responsible for overseeing all purchasing operations for the project.  These duties include supervision of in-house and field purchases.  Appropriate signatures and approval are required for all purchase orders.

7.2	Purchase Requisitions

Purchase requisitions will be required on all major purchases on the project.  Purchase requisitions will be submitted with the signature of a project engineer from the appropriate discipline.

Each purchase requisition will include a complete description of the product(s).  It is the responsibility of the individual engineer and/or designer originating the Purchase Requisition to ensure that the specified equipment or material meets all project specifications.  The engineer/designer is also responsible for ensuring that the product or vendor is currently on the ProEnergy EPC Services Qualified Vendors List.

7.3	Purchase Orders

The Project Administrator will prepare a Purchase Order upon approval of a Purchase Requisition with appropriate signatures.  The Purchase Order will then be sent to the vendor.

7.4	Subcontracts

Subcontracts will be required on all procurements in which vendor labor is a significant element of the vendor’s onsite effort.

7.5	Material Handling

Once the purchase order has been issued, the Project Administrator/Expediter will maintain contact with the vendor until the material/service is received.  It is the responsibility of the Project Administrator/Expediter to arrange shipping, maintain a shipping update list, and ensure that all equipment and materials are delivered to the job site.

7.6	Shipping and Receiving Documents

Purchase orders will be tracked through receipt of the order.

7.7	Material Receiving Inspections

All materials and equipment will be inspected upon receipt at the job site.

7.8	Corrective Action Requests/Non-Conforming Material Reports

If receiving inspections reveal non-acceptable materials or equipment, either a Corrective Action Request or a Non-Conforming Material Report will be prepared.  Copies of either type of discrepancy reports are to be immediately forwarded to the ProEnergy EPC Services QA/QC Manager and the Purchasing Manager for disposition.

7.8.1	Corrective Action Request

Corrective Action Requests for material receipts are to be filled out if materials or equipment is received damaged or possessing factory defects which will necessitate repairs or replacement by the manufacturer.

7.8.2	Non-Conforming Materials Report

Non-Conforming Material Reports are to be filled out if inspection reveals non-compliance with specifications issued to a vendor.

8.0	QUALITY ASSURANCE / QUALITY CONTROL

8.1	QA/QC Plan

ProEnergy EPC Services will prepare a project specific quality assurance/quality control plan which will:

- Specify the types of inspections to be performed

- Specify the testing which will be performed

- Specify who will perform the inspections

- Specify who will perform the testing

- The standards or specifications to which the inspections will be made

8.2	QA/QC Testing

ProEnergy EPC Services will perform and/or witness all tests.  The testing will be documented.  The test documentation will provide the following:

- List of all tests to be performed

- Procedure for inspections and/or tests

- Acceptance criteria used

- Test result (accept or reject)

9.0	COMMISSIONING, STARTUP, TESTING, AND TURNOVER

ProEnergy EPC Services will conduct the commissioning and startup of the various systems which comprise the plant.  ProEnergy EPC Services’ staff will be assisted by vendor technical representatives and start-up personnel.  The commissioning and startup efforts will be conducted and coordinated by ProEnergy EPC Services.  ProEnergy EPC Services or the vendor will provide commissioning and startup procedures and turnover documentation on a system basis.

The commissioning and turnover process will be managed and coordinated by ProEnergy EPC Services staff.  The effort will be coordinated with the Owners and/or their representatives to facilitate witnessing of the commissioning and startup effort culminating in the turnover.

  - Major Engineered Systems

The major engineered systems consist of:

- LM2500 Gas Turbine Generator Packages

- Chilled Water System

- Fuel Gas Compressor System with Cooling Tower

  - Balance of Plant Systems

The Balance of Plant (BOP) systems include:

- Mechanical Systems

  - Natural Gas Fuel System

- Drain System

- Instrument Air System

- Oily Waste System

- Electrical Systems

- 138 kV System

- 4.160 kV System

- 480 VAC System

- 240 VAC System

- 125 VDC Systems

- Ground Grid

- Catholic Protection

- Civil

- Structural Steel

- Buildings

- Gas Compressor Shed

- Liquid Fuel Treatment Shed

- Water Treatment Building

- Control Systems

- BOP DCS

- Fuel Gas Compressor

- GTG

- Liquid Fuel System

  - Commissioning/Startup

Commissioning/startup will be performed by ProEnergy EPC Services’ staff augmented by Factory or Vendor representatives and/or technicians.  Commissioning will be scheduled with sufficient notice for all interested parties to facilitate witnessing of the commissioning process.

    - Major Engineered Equipment

ProEnergy EPC Services will coordinate the commissioning/startup of the major engineered equipment assisted by Factory Representatives or Technical Representatives. ProEnergy EPC Services will utilize the Manufacturers’ or Vendors’ commissioning procedures and documentation.

9.3.2	Balance of Plant Systems

ProEnergy EPC Services will perform the BOP equipment commissioning/startup.  ProEnergy EPC Services will generate/assemble the commissioning procedures and documentation (utilizing to the extent possible commercial off-the-shelf (COTS) documentation from the manufacturer and/or vendor).

  - Turn-Over

ProEnergy EPC Services will perform the turn-over. ProEnergy EPC Services will generate the turn-over documentation consisting of the commissioning and start-up documentation and pre-operational test records.  The turn-over will be scheduled with sufficient notice for all interested parties to facilitate the Owner’s participation in turn-over.

  - Documentation

Commissioning and Turnover Documents will be developed for the all major BOP equipment systems.

10.0 	PERFORMANCE TESTING

Performance testing will demonstrate that the completed project meets or exceeds all guaranteed performance criteria established in the TSD and the contract for this project.  Performance test procedures will be generated under separate cover.  The following project-mandated parameters will be confirmed under Performance Testing.

- Plant Performance Protocol

- Parasitic Load Test

11.0	OPERATOR TRAINING

ProEnergy EPC Services will provide training utilizing Vendor Technical Representatives for operation and maintenance of the following systems:

- Gas Compressors

Training will include selected training on the individual control systems on the systems noted above.  Training will also include Operations and Maintenance training on the individual equipment systems.  Preventative maintenance, troubleshooting procedures and corrective maintenance procedures will be covered in these training sessions.

ProEnergy EPC Services will utilize the plant DCS system for BOP training.  A training manual will be developed for use in the DCS training and can be used as a system reference guide following training.  DCS training will cover all areas of Operator control and monitoring, and will include the mechanical and electrical equipment listed in section 9.2.

The Operator Training will include training in the interface between BOP DCS and the individual system controls noted.  Reference materials for Operation and Maintenance procedures will be found in the Operation and Maintenance Manuals supplied as part of this project.