Electricidad de Caracas LM2500 Tacoa Power Plant Technical Scope Document

8.0            PROJECT SCHEDULE

Please find on the following pages ProEnergy EPC Services’ Typical Project Schedule for the installation of a (2) unit LM2500 Plant.

Section 8.0 Project Schedule

1-1

Revision 0 March 16, 2009

| EDC / TACOA Project LM2500 Simple Cycle Project Project Executive Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | e | Task Name |  | Duration | Start | Finish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | st 20 |  |  |  |  |  | ember 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 009 June 2009 July 2009 Augu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 09 Sept |  |  |  |  |  | 09 October 2009 November 2009 December 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Week 1 | Week 2 Week 3 Week 4 Week 5 Week 6 Week 7 Week 8 |  |  |  |  |  |  |  |  |  | Week 9 Week 10 Week 11 Week 12Week 13 Week 14 Week 15 Week 16 Week 17 Week 18 |  |  |  |  |  |  |  |  |  |  |  |  | Week 19 Week 20 Week 21 |  |  |  | Week 22 | Week 23 | Week 24 Week 25 |  |  | Week 26 | Week 27 Week 28 Week 29 Week 30 |  |  |  |  | Week 31 |
|  |  | EDC / TACOA Project - 2 Unit LM2500 Site |  | 215 days | Mon 5/18/09 | Fri 12/18/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | m | Initial Date |  | 1 day | Mon 5/18/09 | Mon 5/18/09 | ^ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Milestone Dates (Key Dates) |  | 109 days | Mon 5/18/09 | Thu 9/3/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | m | Initial Date |  | 1 day | Mon 5/18/09 | Mon 5/18/09 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | m | Backfeed Power Available |  | 1 day | Tue 9/1/09 | Tue 9/1/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  | Natural Gas Available |  | 1 day | Wed 9/2/09 | Wed 9/2/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  | Raw Water Available |  | 1 day | Thu 9/3/09 | Thu 9/3/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | i,, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | m | Telephone & Internet Service Available |  | 1 day | Wed 7/1/09 | Wed 7/1/09 |  |  |  |  |  |  |  | i. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | m | Construction Power Connection Available |  | 1 day | Wed 7/1/09 | Wed 7/1/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | m | Construction Permit |  | 1 day | Wed 7/1/09 | Wed 7/1/09 |  |  |  |  |  |  |  | i |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  | Payment milestones |  | 191 days | Mon 5/18/09 | Tue 11/24/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  | Project Kickoff |  | 1 day | Mon 5/18/09 | Mon 5/18/09 | a |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  | Milestone 1 - Civil Works GTG foundation poured |  | 1 day | Sun 7/12/09 | Sun 7/12/09 |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  | MileStone 2 - Gas Turbine set on Foundation |  | 1 day | Sat 8/1/09 | Sat 8/1/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | +1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  | Milestone 3 - Gas Turbine Erection complete |  | 1 day | Fri 8/21/09 | Fri 8/21/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ►n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  | Milestone 4 - Mechanical Complete |  | 1 day | Mon 10/5/09 | Mon 10/5/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  | Milestone 5 - Electrical Complete |  | 1 day | Mon 10/5/09 | Mon 10/5/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  | Milestone 6 - Precommissioning complete |  | 1 day Wed 11/4/09 Wed 11/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mi |  |  |  |  |  |  |  |
| 19 |  | Milestone 7 - Plant commissioning and Testing complete |  | 1 day | Tue 11/24/09 | Tue 11/24/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |
| 20 |  | Engineering |  | 64 days | Tue 5/19/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 |  | Conceptual & Major Equipment Specs |  | 10 days | Tue 5/19/09 | Thu 5/28/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 |  | Site Survey |  | 2 days | Fri 5/29/09 | Sat 5/30/09 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 |  | Soil Borings |  | 10 days | Sun 5/31/09 | Tue 6/9/09 |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 |  | Civil and foundation engineering |  | 21 days | Wed 6/10/09 | Tue 6/30/09 |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | m | Issue Foundation for Construction Drawings |  | 2 days | Wed 7/1/09 | Thu 7/2/09 Tue 7/7/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 |  | Detailed Engineering |  | 40 days | Fri 5/29/09 |  |  |  | ► |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 27 | m | Bulk Material Specs and PO's |  | 20 days | Mon 6/22/09 | Sat 7/11/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | m | Issue for Construction Drawings |  | 2 days | Mon 7/20/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 |  | Procurement |  | 64 days | Fri 5/29/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 30 |  | Buildings |  | 12 wks | Fri 5/29/09 | Mon 7/27/09 |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | m | BOP Mechanical |  | 1 mon | Sun 7/12/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 | m | BOP Electrical |  | 1 mon | Sun 7/12/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33 |  | Transportation |  | 30 days | Wed 7/1/09 | Thu 7/30/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 34 | m | GTG Package 100 |  | 30 days | Wed 7/1/09 | Thu 7/30/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 35 | m | GTG Package 200 |  | 30 days | Wed 7/1/09 | Thu 7/30/09 |  |  |  |  |  |  |  |  |  | r |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Construction 126 days Mon 6/1/09 |  |  |  | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 37 | a | Mobilize to Site 14 days Mon 6/1/09 |  |  |  | Sun 6/14/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project: EDC - TACOA LM2500 Projec Date: Thu 4/23/09 |  |  |  |  |  |  |  |  |  |  |  | ternal Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Deadline ^ 1? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Split Mile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Page 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| EDC / TACOA Project LM2500 Simple Cycle Project Project Executive Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | e | Task Name |  | Duration | Start | Finish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 009 June 2009 July 2009 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | August 2009 September 2009 October 2009 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | November 2009 |  |  | December 2 |  |  |  |  |
|  |  |  |  |  |  |  | Week 1 Week 2 Week 3 |  |  | Week 4 Week 5 Week 6 |  |  | Week 7 |  | Week 8 |  | Week 9 Week 10 |  |  |  | Week | 11 Week 12Week 13 Week 14 |  |  |  |  | Week 15 Week 16 Week 17 |  |  |  | Week 18 Week 19 Week 20 Week 21 |  |  |  |  | Week 22 Week 23 |  | Week 24 Week 25Week 26 Week 27 Week 28 |  |  |  |  |  | Week 29 |  | Week 30Week 31 |  |
| 38 |  | Civil Work |  | 17 days | Mon 6/15/09 | Wed 7/1/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 39 |  | Site Preparation |  | 10 days | Mon 6/15/09 | Wed 6/24/09 |  |  |  |  | >¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 40 |  | Excavation & Grading |  | 7 days | Thu 6/25/09 | Wed 7/1/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 41 | E | Install Perimeter Fence |  | 12 days | Mon 6/15/09 | Fri 6/26/09 |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 42 |  | Power Island Foundations |  | 15 days | Thu 7/2/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 43 |  | GTG 100 |  | 10 days | Thu 7/2/09 | Sat 7/11/09 |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 44 |  | GTG 200 |  | 10 days | Thu 7/2/09 | Sat 7/11/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 45 |  | GSU 100 |  | 5 days | Sun 7/12/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 46 | ffl | GSU 200 |  | 5 days | Sun 7/12/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 47 |  | BOP Foundations |  | 15 days | Thu 7/2/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 48 | U | Unit Building |  | 10 days | Thu 7/2/09 | Sat 7/11/09 |  |  |  |  |  |  |  | ► |  |  | . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 49 | m | Substation |  | 10 days | Thu 7/2/09 | Sat 7/11/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 50 | m | Substation Bldg |  | 5 days | Sun 7/12/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 51 |  | Pipe Racks |  | 5 days | Sun 7/12/09 | Thu 7/16/09 |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 52 |  | Building Erection & Fit-out |  | 10 days | Sun 7/12/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  | n | » » |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 53 |  | Unit Building |  | 10 days | Sun 7/12/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 54 |  | Erect Substation Bldg |  | 5 days | Fri 7/17/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 55 |  | Erect GTG 100 |  | 85 days | Sun 7/12/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 56 |  | Equipment Erection |  | 40 days | Sun 7/12/09 | Thu 8/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 |  | Generator |  | 10 days | Sun 7/12/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 58 |  | Gas Turbine |  | 10 days | Wed 7/22/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 59 |  | Air Inlet & Filter |  | 10 days | Wed 7/22/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 60 |  | GT Roof Panel Assy & Installation |  | 10 days | Sat 8/1/09 | Mon 8/10/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | <i |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 61 |  | GT Combustion Filter Assy & Installation |  | 10 days | Tue 8/11/09 | Thu 8/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 62 |  | Electrical Installation |  | 45 days | Fri 8/21/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 63 |  | Mechnical Installation |  | 45 days | Fri 8/21/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 64 |  | Erect GTG 200 |  | 85 days | Sun 7/12/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 65 |  | Equipment Erection |  | 40 days | Sun 7/12/09 | Thu 8/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 66 |  | Generator |  | 10 days | Sun 7/12/09 | Tue 7/21/09 |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 67 |  | Gas Turbine |  | 10 days | Wed 7/22/09 Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 68 |  | Air Inlet & Filter |  | 10 days | Wed 7/22/09 | Fri 7/31/09 |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 69 |  | GT Roof Panel Assy & Installation 10 days |  |  | Sat 8/1/09 | Mon 8/10/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | •j |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 70 |  | GT Combustion Filter Assy & Installation |  | 10 days | Tue 8/11/09 | Thu 8/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 71 | m | Electrical Installation |  | 45 days | Fri 8/21/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | L |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 72 | m | Mechnical Installation |  | 45 days | Fri 8/21/09 | Sun 10/4/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | " 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 73 |  | BOP Installation |  | 75 days | Thu 7/2/09 | Mon 9/14/09 |  |  |  |  |  |  |  | t |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 74 |  | Commissioning and Startup |  | 45 days | Mon 10/5/09 | Wed 11/18/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project: EDC - TACOA LM2500 Projec Date: Thu 4/23/09 |  |  |  |  |  |  |  |  |  |  | ternal Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Deadline ^J^ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Split Mile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Page 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| EDC / TACOA Project LM2500 Simple Cycle Project Project Executive Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | e | Task Name |  | Duration | Start | Finish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 009 Ju |  |  |  | e 2009 |  | July 2009 August 2009 Sep |  |  |  |  |  |  |  |  |  |  |  | ember 2009 |  |  |  | Week 21 | October 2009 |  |  |  | November 2009 |  |  |  |  | December 2 |  |  |  |  |
|  |  |  |  |  |  |  | Week 1 Week 2 Week 3 |  |  | Week 4 | Week 5 | Week 6 Week 7 Week 8 Week 9 Week 10 |  |  |  |  | Week 11 Week 12Week 13 Week 14 |  |  |  | Week 15 Week 16 Week 17 |  |  |  | Week 18 | Week 19 Week 20 |  |  |  | Week 22 Week 23 Week 24 Week 25Week 26 Week 27 |  |  |  |  |  |  |  |  | Week 28 | Week 29 |  | Week 30Week 31 |  |
| 75 |  | BOP Commissioning |  | 20 days | Mon 10/5/09 | Sat 10/24/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 76 |  | GTG 100 Pre-Commissioning |  | 15 days | Mon 10/5/09 | Mon 10/19/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 77 | m | Mechanical |  | 15 days | Mon 10/5/09 | Mon 10/19/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 78 | H | Electrical |  | 15 days | Mon 10/5/09 | Mon 10/19/ 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 79 |  | GTG 200 Precommissioning |  | 15 days | Tue 10/20/09 | Tue 11/3/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | « , |  |  |  |  |  |  |  |  |  |  |  |  |
| 80 | m | Mechanical |  | 15 days | Tue 10/20/09 | Tue 11/3/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | J |  |  |  |  |  |  |  |  |  |
| 81 | m | Electrical |  | 15 days | Tue 10/20/09 | Tue 11/3/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | » |  |  |  |  |  |  |  |  |  |  |  |  |
| 82 |  | GTG 100 Commissioning |  | 15 days | Wed 11/4/09 | Wed 11/18/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 83 |  | GTG 200 Commissioning |  | 15 days | Wed 11/4/09 | Wed 11/18/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 84 |  | Sync to Grid |  | 2 days | Thu 11/19/09 | Fri 11/20/09 Fri 11/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 85 |  | GTG 100 Available |  | 2 days | Thu 11/19/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |
| 86 |  | GTG 200 Available |  | 2 days | Thu 11/19/09 | Fri 11/20/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ► |  |  |  |  |  |  |
| 87 |  | Performance Testing |  | 3 days | Sat 11/21/09 | Mon 11/23/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 88 |  | GTG 100 |  | 3 days | Sat 11/21/09 | Mon 11/23/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | J |  |  |  |  |
| 89 |  | GTG 200 |  | 3 days | Sat 11/21/09 | Mon 11/23/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -•u- |  |  |  |  |  |
| 90 |  | Project Clean-up & demobilization |  | 30 days | Thu 11/19/09 | Fri 12/18/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project: EDC - TACOA LM2500 Projec Date: Thu 4/23/09 |  |  |  |  |  |  |  |  |  |  | ernal Ta |  |  |  | Deadline 4/7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Task ¦ j Prog Split Mile |  |  |  |  | ^^^^^^^^^^W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | stone A |  | Project Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Page 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |