## Recap
ProEnergy EPC
Job Description: |  | "2 GE Fr VII EA's for Corprolec w/ 230KV Sub, Diesel and Demin Pipeline, and Tanks"
Revised Concrete, Pipelines, and Tanks
(1,000'S)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
[16 empty] | Manhours | Manhours
I. Balance of Plant | [7 empty] | US | [7 empty] | US | 1.25 | Local in $ | Bs cost
| 1.0 Civil - Structual | [8 empty] | Dismantle | Shipping | BOP Equipment | Engineering | Construciton | Start Up
|  | 1.1 Site Preparation |  |  |  | 202.2222 | [12 empty] | 758333
|  | 1.2 Excavation - Fill |  |  |  | 259.6444 | [9 empty] | #REF! | #REF! |  | 1133000
|  | 1.3 Concrete Foundations |  |  |  | 2115.7 | [9 empty] | 705.2333 | 881.5417 |  | 2997242
|  | 1.4 Concrete Pilings |  |  |  | 1053.5 | [10 empty] | 0 |  | 827750
|  | 1.5 Paving Asphalt - Concrete |  |  |  | 743.7778 | [10 empty] | 0 |  | 626167
|  | 1.6 Gravel - Sand |  |  |  | 326.6204 | [10 empty] | 0 |  | 668981
|  | 1.7 Structual Steel |  |  |  | 368.5 | [10 empty] | 0
|  | 1.8 Fencing |  |  |  | 45 | [9 empty] | 0 | 0 |  | 250000
|  | 1.9 Architectual Treatment |  |  |  | 0 | [10 empty] | 0
|  | 1.9 Evaporation Pond |  |  |  | 0 | [10 empty] | 0
[6 empty] | 5114.9648 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0 | 5114.9648
0
| 2.0 Buildings | [15 empty] | 0
|  | 2.1 Various Bldgs |  |  |  | 118.5 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 118.5 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0
0
| 3.0 Mechanical | [15 empty] | 0
|  | 3.1 Major Mechanical Equipment |  |  |  | 5680 |  | 5680 | 7156.8 |  |  | 7156.8 |  |  |  |  | 0
|  | 3.2 Pipe, Valves and Fittings Material |  |  |  | 1775 |  | 1775 | 2236.5 | [7 empty] | 0
|  | 3.3 Mechanical Subcontractor |  |  |  | 2341.548 | [11 empty] | 2341.548 | 1525700
|  | 3.4 Pipe, Valves and FTG Labor |  |  |  | 1166.4 |  |  | 1469.664 |  |  |  |  | 1469.664 |  | 40150 | 50187.5 | 1166.4 | 1502775
|  | 3.5 Underground Drain Piping and Labor |  |  |  | 145 | [11 empty] | 145
0
[6 empty] | 0 |  | 0 | [9 empty] | 0
[6 empty] | 11107.948 | [10 empty] | 0
0
| 4.0 Electrical | [15 empty] | 0
|  | 4.1 Major Electrical Equipment |  |  |  | 860 |  | 860 | 1083.6 |  |  | 1083.6 |  |  |  |  | 0
|  | 4.2 Substation Equipment |  |  |  | 150 |  | 150 | 189 |  |  | 189 |  |  |  |  | 0
|  | 4.3 Cable, Conduit, and Tray |  |  |  | 2000 |  | 2000
|  | 4.4 Plant Electrical Subcontractor |  |  |  | 1653.5178 | [11 empty] | 1653.5178 | 1175340
|  | 4.5 Substation Subcontractor |  |  |  | 25.6608 |  |  | 32.3326 |  |  |  |  | 32.3326 |  | 30930 | 38662.5 | 25.6608 | 50000
|  | 4.6 Cable, Conduit, and Tray Labor |  |  |  | 935.55 |  |  | 1178.793 | [6 empty] | 480 | 600 | 935.55 | 665000
[6 empty] | 5624.7286 | [10 empty] | 0
0
| 5.0 Instrumentation | [15 empty] | 0
|  | 5.1 Cems |  |  |  | 0 | [10 empty] | 0
|  | 5.2 Plant Instrumentation |  |  |  | 250 |  | 250 | [8 empty] | 0
|  | 5.3 Instrumentation Subcontractor |  |  |  | 71.6364 | [9 empty] | 1340 | 1675 | 71.6364 | 125000
0
[6 empty] | 321.6364 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0
0
| 6.0 DCS, Tel, Public Add, System and Documentation | [15 empty] | 0
|  | 6.1 Hardware |  |  |  | 320 | [10 empty] | 0
|  | 6.2 Software |  |  |  | 171 | [10 empty] | 0
[6 empty] | 491 |  | 491 | 618.66 |  |  |  |  | 618.66 |  |  | 0
0
0
| 7.0 Plant Erection | [15 empty] | 0
|  | 7.1 Plant Erection |  |  |  | 2064.4114 | [9 empty] | 64360 | 80450 | 2064.4114 | 2445680
0
[6 empty] | 2064.4114 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0
0
| 8.0 Equipment Rental | [15 empty] | 0
|  | 8.2 Plant Equipment Rental |  |  |  | 1737 | [10 empty] | 0 | 1737 | 2500000
0
[6 empty] | 1737 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0
0
| 9.0 Painting |  |  |  |  | 275 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  | 275
0
| 10.0 Transportation | [15 empty] | 0
|  | 10.1 BOP US Frt |  |  |  | 453.5 |  | 453.5 | [8 empty] | 0
|  | 10.2 Ocean Frt BOP |  |  |  | 0 | [10 empty] | 0
|  | 10.3 Inland Frt BOP |  |  |  | 600 |  | 600 | [8 empty] | 0
[6 empty] | 1053.5 |  |  | #VALUE! |  | #VALUE! | [5 empty] | 0
0
0
| 11.0 Site Costs |  |  |  |  | 522.5 |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  | 0 | 522.5 | 2000000
0
| 12.0 Engineering | [15 empty] | 0
|  | 12.1 EPC Eng Labor |  |  |  | 1010 |  | 1010 | [8 empty] | 0
|  | 12.2 Local Eng |  |  |  | 165 | [10 empty] | 0 | 165
|  | 12.3 Eng Travel & Per Diem |  |  |  | 189 |  | 189 | [8 empty] | 0
[6 empty] | 1364 |  |  | #VALUE! |  |  |  | #VALUE! |  |  |  | 0
0
| 13.0 Project Management | [15 empty] | 0
|  | 13.1 Project - Inspectors - Commissioning Lab |  |  |  | 2930 |  | 2930 | [7 empty] | 38240 | 38240
|  | 13.2 Travel & Per Diem |  |  |  | 1242 |  | 1242 | [8 empty] | 0
[6 empty] | 0 | [10 empty] | 0
0
[6 empty] | 4172 |  |  | #VALUE! | #VALUE! |  |  |  | #VALUE! |  |  | 0
0
| 14.0 Technical Reps | [15 empty] | 0
|  | 14.1 GTG Tech Rep |  | 260 | 2200 | 572 |  | 572 | [8 empty] | 0
|  | 14.2 Fire Water |  | 0 | 2000 | 0 | [10 empty] | 0
|  | 14.3 Gas Compressor |  | 0 | 2000 | 0 | [10 empty] | 0
|  | 14.4 Evap Cooler Pkg |  | 0 | 2000 | 0 | [10 empty] | 0
|  | 14.5 Water Treatment |  | 0 | 2000 | 0 | [10 empty] | 0
|  | 14.6 Commissioning / Start |  | 120 | 2000 | 240 |  | 240 | [8 empty] | 0
|  | 14.7 Controls Rep |  | 100 | 2500 | 250 |  | 250 | [8 empty] | 0
0
[6 empty] | 1.062 |  |  | #VALUE! | [5 empty] | #VALUE! |  | 0
0
| 15.0 Project Tests | [15 empty] | 0
|  | 15.1 Soils Compaction |  |  |  | 35 | [10 empty] | 0 | 35
|  | 15.2 Concrete Testing |  |  |  | 80 | [10 empty] | 0 | 80
|  | 15.3 X Ray |  |  |  | 80 | [10 empty] | 0 | 80
|  | 15.4 Plant Performance and Reliability |  |  |  | 200 |  | 200 | [8 empty] | 0
|  | 15.5 Noise Emission Tests | [14 empty] | 0
|  | 15.6 Protective Relays |  |  |  | 30 |  | 30 | [8 empty] | 0
[6 empty] | 425 |  |  | #VALUE! |  |  |  |  | #VALUE! | #VALUE! |  | 0
0
| 16.0 Legal |  |  |  |  | 75 |  | 75 | 94.5 | 47.25 |  |  |  | 47.25 |  |  | 0
0
| 17.0 Insurance | [15 empty] | 0
|  | 17.1 Project Insurance |  |  |  | 500 |  | 500 | 630 | 315 |  |  |  | 315
| 18.0 Dismantling |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | [5 empty] | #REF! | #REF!
| 19.0 Project Contingency/Risk | [6 empty] | 1000 | 0.043864
| 19.1 GT Performance Contingency | [6 empty] | 1000
| 20.0 Sales Tax |  |  |  |  | 0 |  |  |  | #VALUE! | #VALUE! | 8429.4 | #VALUE! | #VALUE! | #VALUE!
|  | BOP Cost US Dollars | [5 empty] | 21497.5
|  | BOP Cost Local Contractor in US Dollars | [6 empty] | 0 | [8 empty] | 16413.1892 | 19250968
21497.5
| 21.0 Commissions |  | BOP 3% | Plugged |  | 1300 |  | 1300 | 1604
0
|  |  |  | BOP Sales cost |  |  |  | 22797.5 | #VALUE!
|  |  |  | Mark Up |  |  |  | 15000
|  |  |  | BOP Sales Price |  |  |  | 37797.5
|  |  |  | Dual Fuel Conversion |  |  |  | 6000
|  |  |  | Kaled |  |  |  | 8000
|  |  |  | Total Sales Price |  |  |  | 51797.5 | [10 empty] | 19780000

## 1.1 Site Prep
|  |  | SITE PREP | [6 empty] | 1.1
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [5 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [5 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [5 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
Nol |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | Bs Cost | Bs Total
1 | Site |  |  | 700 | 650 | 1 | 455000 | 16851.8519 | 12 | 202222.2222 | 45 | 758333.3333
2
3 | [9 empty] | 0
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
202.2222

## 1.2 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 1.2
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [6 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [6 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [6 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
Nol |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | BS Cost | Bs Total
1 | Bldg Area
| Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
| Control/Office/Maint |  |  |  | 120 | 60 | 1 | 7200 | 266.6667 | 12 | 3200 | 55 | 14666.6667
| Water Treatment Area |  |  |  | 60 | 50 | 1 | 3000 | 111.1111 | 12 | 1333.3333 | 55 | 6111.1111
| Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 55
| Pwr Blk Utility GTG's |  |  |  | 350 | 150 | 2 | 105000 | 3888.8889 | 12 | 46666.6667 | 55 | 213888.8889
| Substation GSU's |  |  |  | 80 | 30 | 3 | 7200 | 266.6667 | 12 | 3200 | 55 | 14666.6667
| Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 55
| Liquid Fuel Unloading Shed |  |  |  | 60 | 30 | 1 | 1800 | 66.6667 | 12 | 800 | 55 | 3666.6667
[10 empty] | 12 |  | 55
2 | Main Plant Area |  |  |  | 650 | 600 | 1 | 390000 | 14444.4444 | 12 | 173333.3333 | 55 | 794444.4444
3 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 55
4 | Substation Area |  |  |  | 0 | 0 | 1 | 0 | 0 | 12 | 0 | 55
5 | [11 empty] | 55
6 | Concrete Ditch along North Side |  |  |  | 700 | 10 | 6 | 42000 | 1555.5556 | 20 | 31111.1111 | 55 | 85555.5556
7
8
9 | [12 empty] | 1133000
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
|  |  | Total Cost of Excavation and Fill | [7 empty] | 259.6444

## 1.3 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 1.3
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [7 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [7 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [7 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | BS Cost | Bs Total
1 | POWER ISLAND
| GT Turbine |  |  | 2 | 68 | 20 | 7 | 19040 | 705.1852 | 600 | 423111.1111 | 850 | 599407.4074
| GT Generator |  |  | 2 | 28 | 19 | 9 | 9576 | 354.6667 | 600 | 212800 | 850 | 301466.6667
| Exhaust Stack |  |  | 2 | 35 | 35 | 6 | 14700 | 544.4444 | 600 | 326666.6667 | 850 | 462777.7778
| Air Intake |  |  | 2 | 43 | 5 | 2 | 860 | 31.8519 | 600 | 19111.1111 | 850 | 27074.0741
| Leg A |  |  | 2 | 27 | 7 | 3 | 1134 | 42 | 600 | 25200 | 850 | 35700
| Leg B |  |  | 2 | 27 | 7 | 3 | 1134 | 42 | 600 | 25200 | 850 | 35700
| Base |  |  | 2 | 25 | 14 | 4 | 2800 | 103.7037 | 600 | 62222.2222 | 850 | 88148.1481
| Emergency Gen Base |  |  | 0 | 16 | 8 | 2 | 0 | 0 | 600 | 0 | 850 | 0
| Black Start Gen Base |  |  | 0 | 25 | 12 | 3 | 0 | 0 | 600 | 0 | 850 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 850 | 0
|  |  |  | Price: 600 | 850 | 0
|  |  |  | Price: 600 | 850 | 0
2 | BALANCE OF PLANT |  |  | Price: 600 | 850 | 0
| Gas Valve Module |  |  | 2 | 12 | 9 | 1 | 216 | 8 | 600 | 4800 | 850 | 6800
| PEECC Vault |  |  | 2 | 40 | 16 | 2 | 2560 | 94.8148 | 600 | 56888.8889 | 850 | 80592.5926
| Fin Fan L O Coolers |  |  | 2 | 60 | 30 | 1.5 | 5400 | 200 | 600 | 120000 | 850 | 170000
| Mech Elec Bldg Vault |  |  | 1 | 40 | 23 | 1.5 | 1380 | 51.1111 | 600 | 30666.6667 | 850 | 43444.4444
| Water Wash Skid |  |  | 1 | 19 | 9 | 2 | 342 | 12.6667 | 600 | 7600 | 850 | 10766.6667
| Exhaust Gas Blowers |  |  | 2 | 13.5 | 4 | 2 | 216 | 8 | 600 | 4800 | 850 | 6800
| Inlet Fogging Skid |  |  | 2 | 13 | 10 | 5 | 1300 | 48.1481 | 600 | 28888.8889 | 850 | 40925.9259
| Mist Elimenator Containment |  |  | 2 | 16 | 16 | 0.5 | 256 | 9.4815 | 600 | 5688.8889 | 850 | 8059.2593
| Mist Elimenator |  |  | 2 | 6 | 6 | 5 | 360 | 13.3333 | 600 | 8000 | 850 | 11333.3333
| Air Processing skid |  |  | 2 | 8 | 6 | 1 | 96 | 3.5556 | 600 | 2133.3333 | 850 | 3022.2222
| 15KV Switch Gear NEMA 3R |  |  | 2 | 17 | 9 | 1 | 306 | 11.3333 | 600 | 6800 | 850 | 9633.3333
| 15KV Breaker |  |  | 2 | 19 | 12 | 1 | 456 | 16.8889 | 600 | 10133.3333 | 850 | 14355.5556
| Sump Basin |  |  | 2 | 12 | 10 | 2 | 480 | 17.7778 | 600 | 10666.6667 | 850 | 15111.1111
| Waste Oil Storage Tank |  |  | 1 | 12 | 12 | 1 | 144 | 5.3333 | 600 | 3200 | 850 | 4533.3333
| Oily Water Separator |  |  | 1 | 30 | 15 | 2 | 900 | 33.3333 | 600 | 20000 | 850 | 28333.3333
| Fire Water Pump Skid |  |  | 0 | 35 | 15 | 2 | 0 | 0 | 600 | 0 | 850 | 0
| Instrument air Compressor |  |  | 2 | 10 | 8 | 1 | 160 | 5.9259 | 600 | 3555.5556 | 850 | 5037.037
| Pipe Rack Stanchons |  |  | 28 | 2.5 | 2.5 | 3 | 525 | 19.4444 | 600 | 11666.6667 | 850 | 16527.7778
| 15 LV Cable Stanchons |  |  | 10 | 2.5 | 2.5 | 3 | 187.5 | 6.9444 | 600 | 4166.6667 | 850 | 5902.7778
| Water Treatment Plant |  |  | 0 | 60 | 40 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| DFO 1000cum Tank |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 600 | 45000 | 850 | 63750
| DFO 7000cum Tank |  |  | 1 | 65 | 65 | 1 | 4225 | 156.4815 | 600 | 93888.8889 | 850 | 133009.2593
| Area Light Poles |  |  | 0 | 3 | 3 | 4 | 0 | 0 | 600 | 0 | 850 | 0
| Demin Water Pump skid |  |  | 1 | 8 | 6 | 1 | 48 | 1.7778 | 600 | 1066.6667 | 850 | 1511.1111
| Demin Stg Tanks 21MGal |  |  | 6 | 15 | 15 | 1 | 1350 | 50 | 600 | 30000 | 850 | 42500
| Demin Forwarding Pumps |  |  | 2 | 8 | 6 | 1 | 96 | 3.5556 | 600 | 2133.3333 | 850 | 3022.2222
| 4160 V Aux Transformers |  |  | 2 | 12 | 12 | 1 | 288 | 10.6667 | 600 | 6400 | 850 | 9066.6667
| 480 V Aux Transformers |  |  | 2 | 10 | 10 | 1 | 200 | 7.4074 | 600 | 4444.4444 | 850 | 6296.2963
| CO2 Tanks |  |  | 4 | 11 | 7 | 1 | 308 | 11.4074 | 600 | 6844.4444 | 850 | 9696.2963
| Cable Trenches / Power Blk |  |  | 2 | 90 | 12 | 1 | 2160 | 80 | 600 | 48000 | 850 | 68000
| Cable Trenches Utilities |  |  | 1 | 250 | 12 | 1 | 3000 | 111.1111 | 600 | 66666.6667 | 850 | 94444.4444
| Diesel Unloading Shed |  |  | 0 | 60 | 25 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Fuel Forwarding Skid |  |  | 4 | 10 | 8 | 1 | 320 | 11.8519 | 600 | 7111.1111 | 850 | 10074.0741
| Fuel Heater Skid |  |  | 2 | 20 | 15 | 1 | 600 | 22.2222 | 600 | 13333.3333 | 850 | 18888.8889
| Fuel Tank |  |  | 0 | 65 | 65 | 1 | 0 | 0 | 600 | 0 | 850 | 0
3 | BUILDINGS |  |  | Price: 600 | 850 | 0
| Control Bldg/Office |  |  | 0 | 75 | 60 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Warehouse/Maintenance |  |  | 0 | 80 | 60 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Water Treatment Bldg |  |  | 0 | 60 | 40 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Gas Compressor Bldg |  |  | 0 | 120 | 45 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Electrical Bldg |  |  | 1 | 42 | 20 | 1 | 840 | 31.1111 | 600 | 18666.6667 | 850 | 26444.4444
| Pwr Blk Utility Bldg's |  |  | 0 | 30 | 20 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Substation Bldg |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 850 | 0
| Liquid Fuel Unloading |  |  | 0 | 40 | 60 | 1 | 0 | 0 | 600 | 0 | 850 | 0
| Pump Bldg |  |  | 1 | 40 | 30 | 1 | 1200 | 44.4444 | 600 | 26666.6667 | 850 | 37777.7778
| Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 850 | 0
|  |  |  | Price: 600 | 850 | 0
4 | SUBSTATION |  |  | Price: 600 | 850 | 0
| GSU Transformer |  |  | 1 | 14 | 23 | 6 | 1932 | 71.5556 | 600 | 42933.3333 | 850 | 60822.2222
| GSU Blast Wall |  |  | 1 | 67 | 32 | 1 | 2144 | 79.4074 | 600 | 47644.4444 | 850 | 67496.2963
| GSU Containment |  |  | 1 | 35 | 51 | 0.5 | 892.5 | 33.0556 | 600 | 19833.3333 | 850 | 28097.2222
| Containment Wall |  |  | 1 | 119 | 0.5 | 3.5 | 208.25 | 7.713 | 600 | 4627.7778 | 850 | 6556.0185
| (132)KV SF6 Circuit Breaker |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 600 | 5000 | 850 | 7083.3333
| (132)KV Disc Switch w/ Stand |  |  | 2 | 10 | 15 | 1 | 300 | 11.1111 | 600 | 6666.6667 | 850 | 9444.4444
| Dead End Tower |  |  | 2 | 15 | 10 | 3 | 900 | 33.3333 | 600 | 20000 | 850 | 28333.3333
| Transmission Line Poles |  |  | 1 | 5 | 5 | 20 | 500 | 18.5185 | 600 | 11111.1111 | 850 | 15740.7407
| Insulator Support Base |  |  | 12 | 2.5 | 2.5 | 3 | 225 | 8.3333 | 600 | 5000 | 850 | 7083.3333
| PT Support Base |  |  | 3 | 2.5 | 2.5 | 3 | 56.25 | 2.0833 | 600 | 1250 | 850 | 1770.8333
| Static Pole Base |  |  | 3 | 3 | 3 | 5 | 135 | 5 | 600 | 3000 | 850 | 4250
[12 empty] | 850 | 0
5 | Drainage Ditch |  |  | 1 | 650 | 20 | 0.5 | 6500 | 240.7407 | 600 | 144444.4444 | 850 | 204629.6296
|  |  | Total Cost of Foundations | Cubic: 3526.1667; Total: 2115.7 |  | 2997241.6667
[9 empty] | 705.2333 | mhrs @ 5mhr/cy

## 1.4 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 1.4
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [7 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [7 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [7 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description | [7 empty] | Cu | Price | Total
Nol |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price | Bs Cost | Bs Total
1 | Concrete Pilings
| Pilings GTG x _____ |  |  |  | 2 | 24 | 35 | 3 | 3 | 560 | 700 | 392000 | 550 | 308000
| Pilings Stack x _____ |  |  |  | 2 | 8 | 35 | 3 | 3 | 186.6667 | 700 | 130666.6667 | 550 | 102666.6667
| Pilings GSU x _____ |  |  |  | 1 | 9 | 35 | 3 | 3 | 105 | 700 | 73500 | 550 | 57750
| Pilings SF6 Brkr |  |  |  | 1 | 2 | 35 | 3 | 3 | 23.3333 | 700 | 16333.3333 | 550 | 12833.3333
| Pilings Modular Control Bldg & PDC |  |  |  | 3 | 6 | 35 | 3 | 3 | 210 | 700 | 147000 | 550 | 115500
| Pilings STG x _____ |  |  |  | 0 | 0 | 35 | 0 | 0 | 0 | 700 | 0 | 550 | 0
[13 empty] | 550 | 0
| 230 KV substation SF6 Breakers |  |  |  | 3 | 2 | 35 | 3 | 3 | 70 | 700 | 49000 | 550 | 38500
| 230 KV Disconnects |  |  |  | 6 | 2 | 35 | 3 | 3 | 140 | 700 | 98000 | 550 | 77000
| 230 KV Dead End Towers |  |  |  | 3 | 6 | 35 | 3 | 3 | 210 | 700 | 147000 | 550 | 115500
0
[12 empty] | 0 |  | 827750
0
0
0
0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
|  |  | Total Cost of Retaining Walls | [8 empty] | 1053500

## 1.5 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 1.5
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [6 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [6 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [6 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
Nol |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | Bs Cost | Bs Total
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
2 | Gen Removal Areas |  |  | 120 | 30 | 1 | 3600 | 133.3333 | 500 | 66666.6667 | 425 | 56666.6667
3 | Turbine Removal Areas |  |  | 120 | 30 | 1 | 3600 | 133.3333 | 500 | 66666.6667 | 425 | 56666.6667
4 | Entry Ways |  |  | 80 | 15 | 0.5 | 600 | 22.2222 | 500 | 11111.1111 | 425 | 9444.4444
5 | Walk ways |  |  | 220 | 6 | 0.5 | 660 | 24.4444 | 500 | 12222.2222 | 425 | 10388.8889
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 425 | 0
7 | [6 empty] | 0 | 0 |  | 0 | 425 | 0
8 | [6 empty] | 0 | 0 |  | 0 | 425 | 0
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 1600 | 20 | 0.7 | 22400 | 829.6296 | 500 | 414814.8148 | 425 | 352592.5926
12 | Parking Lot |  |  | 200 | 50 | 0.7 | 7000 | 259.2593 | 500 | 129629.6296 | 425 | 110185.1852
13 | [6 empty] | 0 | 0 |  | 0 | 425 | 0
14 | Underground Road Crossings | [5 empty] | 0 | 0 |  | 0 | 425 | 0
15 | "8 Each" |  |  | 160 | 6 | 2 | 1920 | 71.1111 | 600 | 42666.6667 | 425 | 30222.2222
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0 |  | 626166.6667
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
[7 empty] | 0 | 0 |  | 0
[7 empty] | 0 | 0 |  | 0
[7 empty] | 0 | 0 |  | 0
[7 empty] | 0 | 0 |  | 0
743.7778

## 1.6 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 1.6
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [7 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [7 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [7 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total
Nol |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price | Bs Cost | Bs Total
1
2 | Main Plant Area (less substa) |  |  | 1 | 650 | 600 | 0.5 | 195000 | 7222.2222 | 11988.8889 | 25 | 299722.2222 | 85 | 613888.8889
3 | [12 empty] | 85 | 0
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 25 | 0 | 85 | 0
5 | [12 empty] | 85 | 0
6 | Substation |  |  | 0 | 600 | 300 | 0.7 | 0 | 0 | 0 | 25 | 0 | 85 | 0
7 | [12 empty] | 85 | 0
8 | Road ways |  |  | 1 | 1400 | 25 | 0.5 | 17500 | 648.1481 | 1075.9259 | 25 | 26898.1481 | 85 | 55092.5926
9
10 | [13 empty] | 668981.4815
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
|  |  | Total Cost of Gravel | Total: 326.6204

## 1.7 Structural
STRUCTUAL STEEL
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [5 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [5 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [5 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | # of | Qty | Price | Total
Nol | [5 empty] | Lbs / Tons |  |  | Price
1 | Misc Pipe Rack supports etc. Gas Turbines | [5 empty] | 15 | 3500 | 52500
0
2 | 15 KV Cable Tray Stanchons | [5 empty] | 10 | 3000 | 30000
0
3 | GTG walkways and stairs | [5 empty] | 2 | 15000 | 30000
0
4 | Structual Steel for equip supports | [5 empty] | 0 | 0 | 0
5 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 1 | 15000 | 15000
6 | Steel Cover for Oily Catch Basin | [5 empty] | 1 | 3500 | 3500
7 | [6 empty] | 0 | 0 | 0
8 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 50000 | 50000
9 | Pipe Rack for DFO and Demin Pipelines 2500ft every 20ft | [5 empty] | 125 | 1500 | 187500
|  |  | Total Cost of Stuctual Steel | [5 empty] | 368.5 | 0

## 1.8 Fence
FENCING
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 3000 | 15 | 45000
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 0 | 19 | 0
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 0 | 14 | 0
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 0 | 3000 | 0
10 | Motor Operated Double Gate(s) |  |  |  |  | 0 | 7000 | 0
11 | Personnel Gate(s) |  |  |  |  | 0 | 500 | 0
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 0 | 10000 | 0
15
|  |  | Total Cost of Fencing |  |  |  |  | 45

## 2.1 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 2.1
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [5 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [5 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [5 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total
Nol |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price
1 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0
2 | Control/Office |  |  |  | 50 | 30 | 1500 | 65 | 97500
3 | Water Treatment |  |  |  | 0 | 40 | 0 | 45 | 0
4 | Electric Bldg |  |  |  | 0 | 30 | 0 | 45 | 0
5 | Warehouse/Maintenance |  |  |  | 0 | 50 | 0 | 45 | 0
6 | Substation Bldg |  |  |  | 0 | 15 | 0 | 40 | 0
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Forwarding |  |  |  | 15 | 20 | 300 | 35 | 10500
9 | Demin Forwarding |  |  |  | 15 | 20 | 300 | 35 | 10500
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 0 | 15 | 0 | 40 | 0
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
|  |  | Total Cost of Other Buildings | [5 empty] | 118.5

## 3.1 & 3.3 Mech Equip & Labor
MECHANICAL EQUIPMENT and Labor
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [9 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [9 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [9 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | Bs Cost | Bs Total
GTG
1 | GTG Type GE Frame VII EA's |  |  | 2 | 0 | 0 | 0 | 0 | 10 | 12 | 132 | 31680 | 29.16 | 923788.8 | 38 | 1203840
2 | Lube oils and Chemicals 2600 gal ea @ 6.50 |  |  | 2 | 40000 | 80000 | 3000 | 6000 | 10 | 2 | 1 | 40 | 29.16 | 1166.4 | 38 | 1520
3 | Exhaust Stack Modifications |  |  | 2 | 450000 | 900000 | 25000 | 50000 | 10 | 6 | 10 | 1200 | 29.16 | 34992 | 38 | 45600
4 | Exhaust Expansion Joint |  |  | 2 | 15000 | 30000 | 500 | 1000 | 10 | 0 | 15 | 0 | 29.16 | 0 | 38 | 0
| LO Fin Fans |  |  | 2 | 0 | 0 | 15000 | 30000 | 10 | 4 | 10 | 800 | 29 | 23200 | 38 | 30400
5 | Anchor Bolts/Fixators |  |  | 2 | 80000 | 160000 | 500 | 1000 | 10 | 0 | 15 | 0 | 29.16 | 0 | 38 | 0
6 | Grout |  |  | 2 | 100000 | 200000 | 3000 | 6000 | 10 | 4 | 6 | 480 | 39 | 18720 | 38 | 18240
7 | HRSG | [13 empty] | 38
8 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
9 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
10 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
11 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
10 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
11 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
12 |  |  |  | Total: 0 | 38 | 0
13 | SCR | [13 empty] | 38
14 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
15 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
16 | [14 empty] | 38
17 | STG | [13 empty] | 38
18 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
19 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
20 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
21 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
22 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
23 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
24 | [14 empty] | 38
25 | Inlet Air Conditioning System | [13 empty] | 38
26 | Inlet Chilling Package (Generator) |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
27 | Inlet Fogging System |  |  | 2 | 50000 | 100000 | 2000 | 4000 | 10 | 4 | 8 | 640 | 29.16 | 18662.4 | 38 | 24320
28 | Inlet Overspray System (Includes installation) |  |  | 0 | 427300 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 29.16 | 0 | 38 | 0
29 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
30 | Cooling Water Circulation Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
31 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
32 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
33 | [14 empty] | 38
34 | Fuel Gas Systems | [13 empty] | 38
35 | Fuel Gas compressor w/ Fin Fans |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
36 | Fuel Gas Regulator Skid |  |  | 2 | 240000 | 480000 | 1000 | 2000 | 10 | 4 | 3 | 240 | 29.16 | 6998.4 | 38 | 9120
37 | Fuel Gas Turbine Metering Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
37 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 2 | 380000 | 760000 | 5000 | 10000 | 10 | 4 | 5 | 400 | 29.16 | 11664 | 38 | 15200
38 | ESD Valve, ___" ___# |  |  | 1 | 25000 | 25000 | 500 | 500 | 10 | 2 | 1 | 20 | 29.16 | 583.2 | 38 | 760
39 | [14 empty] | 38
40 | Liquid Fuel Systems | [13 empty] | 38
41 | Unloading Pump Skid |  |  | 2 | 12000 | 24000 | 500 | 1000 | 10 | 3 | 3 | 180 | 29.16 | 5248.8 | 38 | 6840
42 | Metering Skid |  |  | 1 | 135000 | 135000 | 500 | 500 | 10 | 3 | 3 | 90 | 29.16 | 2624.4 | 38 | 3420
43 | Forwarding Pump Skid |  |  | 2 | 35000 | 70000 | 1000 | 2000 | 10 | 3 | 5 | 300 | 29.16 | 8748 | 38 | 11400
44 | Transfer Pump Skid |  |  | 0 | 25000 | 0 | 1000 | 0 | 10 | 3 | 3 | 0 | 29.16 | 0 | 38 | 0
45 | Fuel Heating |  |  | 0 | 85000 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 29.16 | 0 | 38 | 0
46 | Filters |  |  | 4 | 15000 | 60000 | 500 | 2000 | 10 | 2 | 2 | 160 | 29.16 | 4665.6 | 38 | 6080
47 | Centrifuge |  |  | 0 | 350000 | 0 | 30000 | 0 | 10 | 3 | 5 | 0 | 29.16 | 0 | 38 | 0
48 | Injection Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
49 | DFO Raw Storage Tank 7,000 cu m |  |  | 1 | 1200000 | 1200000 | 50000 | 50000 | 10 | 4 | 10 | 400 | 29.16 | 11664 | 38 | 15200
50 | DFO Day Storage Tank 1,000 cu m |  |  | 1 | 550000 | 550000 | 30000 | 30000 | 10 | 3 | 8 | 240 | 29.16 | 6998.4 | 38 | 9120
38
51 | Water Supply System | [13 empty] | 38
52 | Raw Water Storage Tank 500 M gal |  |  | 0 | 500000 | 0 | 20000 | 0 | 10 | 4 | 5 | 0 | 29.16 | 0 | 38 | 0
53 | Raw Water Supply Pumps |  |  | 0 | 12000 | 0 | 2000 | 0 | 10 | 2 | 2 | 0 | 29.16 | 0 | 38 | 0
54 | Raw Water Forwarding Pumps |  |  | 0 | 8000 | 0 | 1500 | 0 | 10 | 2 | 2 | 0 | 29.16 | 0 | 38 | 0
38
55 | Water Treatment System | [13 empty] | 38
56 | Multi Media Filter Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 29.16 | 0 | 38 | 0
57 | Water Wash Skid |  |  | 0 | 110000 | 0 | 5000 | 0 | 10 | 4 | 5 | 0 | 29.16 | 0 | 38 | 0
58 | Demin Treatment System |  |  | 0 | 700000 | 0 | 40000 | 0 | 10 | 4 | 20 | 0 | 29.16 | 0 | 38 | 0
59 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
60 | Demin water fiberglass tank |  |  | 6 | 25000 | 150000 | 2500 | 15000 | 10 | 4 | 6 | 1440 | 29.16 | 41990.4 | 38 | 54720
61 | Demin forwarding pumps (50%) |  |  | 4 | 18000 | 72000 | 500 | 2000 | 10 | 2 | 2 | 160 | 29.16 | 4665.6 | 38 | 6080
62 | Demin Filter Skid |  |  | 2 | 30000 | 60000 | 500 | 1000 | 10 | 2 | 1 | 40 | 29.16 | 1166.4 | 38 | 1520
63 | Demin Water Tank, SS 300M gal |  |  | 0 | 320000 | 0 | 15000 | 0 | 10 | 4 | 4 | 0 | 29.16 | 0 | 38 | 0
64 | [14 empty] | 38
65 | Waste Water and Oil Storage and Transfer | [13 empty] | 38
66 | Oily Water Separator |  |  | 1 | 65000 | 65000 | 5000 | 5000 | 10 | 4 | 5 | 200 | 29.16 | 5832 | 38 | 7600
67 | Oily Waste Tank 10000 gal |  |  | 1 | 10000 | 10000 | 2500 | 2500 | 10 | 4 | 2 | 80 | 29.16 | 2332.8 | 38 | 3040
68 | Waste Water Tank 10000 gal |  |  | 1 | 10000 | 10000 | 2500 | 2500 | 10 | 4 | 2 | 80 | 29.16 | 2332.8 | 38 | 3040
69 | Waste Oil and Water forwarding pumps w/ skid |  |  | 2 | 7000 | 14000 | 500 | 1000 | 10 | 2 | 1 | 40 | 29.16 | 1166.4 | 38 | 1520
70 | [14 empty] | 38
71 | Fire Control Systems | [13 empty] | 38
72 | Fire Water Pump Skids (Diesel / Electric) |  |  | 0 | 500000 | 0 | 5000 | 0 | 10 | 4 | 5 | 0 | 29.16 | 0 | 38 | 0
73 | Fire Water System, valves, hydrants, monitors |  |  | 1 | 125000 | 125000 | 10000 | 10000 | 10 | 4 | 15 | 600 | 29.16 | 17496 | 38 | 22800
| Foam System Large diesel tanks |  |  | 2 | 200000 | 400000 | 2500 | 5000 | 10 | 4 | 8 | 640 | 29.16 | 18662.4 | 38 | 24320
74 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 38 | 0
75 | Storm Water System | [13 empty] | 38
76 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
77 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
78 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
79 | [14 empty] | 38
80 | Other Systems | [13 empty] | 38
81 | Instrument Air Compressor Package, net (___) scfm |  |  | 0 | 85000 | 0 | 0 | 0 | 10 | 4 | 3 | 0 | 29.16 | 0 | 38 | 0
82 | Emergency Generator 300KW |  |  | 0 | 200000 | 0 | 1500 | 0 | 10 | 4 | 4 | 0 | 29.16 | 0 | 38 | 0
83 | Black Start Generator 2 MW |  |  | 0 | 0 | 0 | 5000 | 0 | 10 | 4 | 10 | 0 | 29.16 | 0 | 38 | 0
84 | [14 empty] | 38 | 0
85 |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 29.16 | 0 | 38 | 0
86 |  |  | Total Cost | Total: 5680; Frt: 240; Hours: 10 | 38 | 0
[12 empty] | 40150 |  | 1175.3692
[9 empty] | Total Manhours |  |  | 40150
|  |  |  | Hours: Times Prod Factor; Qty: 2; Qty: 80300; Rate: 29.16; Total: 2341.548 |  | 1525700
Price per hour based on a 50 hr week with all labor
burdens as follows:
[8 empty] | Local Hrly Cost |  | 15
[8 empty] | Labor Burden 35% |  | 5.25
20.25
[8 empty] | Contr Mark up 20% |  | 4.05
24.3
[8 empty] | 50hrs = x1.2 |  | 29.16
| BOP Pipe, Valves, and Fittings, Labor (Includes DFO & Demin PL) |  |  | Total: 1775; Frt: Pipe, Vlv, and Ftg Labor; Qty: 20000
|  |  |  | Hours: Productivity; Qty: 2; Qty: 40000; Rate: 29.16; Total: 1166.4 | 38 | 1520000
3045700
| Underground Drain Piping and Fittings - Labor |  |  | Total: 145

## 4.1 & 4.3 El Equip & Labor
ELECTRICAL EQUIPMENT and Labor
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [11 empty] | Date: |  | 2009-08-14
Customer: |  | Corprolec | [11 empty] | Quote No: |  | T-9005 C
Location: |  | Maracaibo, Venn | [11 empty] | Est By: |  | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
Nol | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | Bs cost | Bs total
Power Island Equipment
1 | Gas Turbine Generator GE Frame VII ea's |  |  |  |  | 2 |  |  |  |  | 10 | 10 | 132 | 26400 | 26.73 | 705672
2 | HRSG |  |  |  |  | 0 | [7 empty] | 0 | 26.73 | 0
3 | SCR |  |  |  |  | 0 | [7 empty] | 0 | 26.73 | 0
4 | STG |  |  |  |  | 0 | [7 empty] | 0 | 26.73 | 0
5 | STG Cooling Tower |  |  |  |  | 0 | [7 empty] | 0 | 26.73 | 0
6 | Chiller Package |  |  |  |  | 0 | [7 empty] | 0 | 26.73 | 0
7 | Water Treatment Package |  |  |  |  | 0 |  |  |  |  | 10 | 4 | 15 | 0 | 26.73 | 0
8 | [13 empty] | 0 | 26.73 | 0
9 | 15KV
10 | Generator Breaker(s) |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 400 | 26.73 | 10692
11 | Distribution Breaker(s) |  |  |  |  | 2 | 55000 | 110000 | 2500 | 5000 | 10 | 4 | 4 | 320 | 26.73 | 8553.6
12 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 26.73 | 0
13 | Cable Bus Duct |  |  |  |  | 2 | 200000 | 400000 | 3000 | 6000 | 10 | 5 | 8 | 800 | 26.73 | 21384
14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 26.73 | 0
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 26.73 | 0
16 | 5KV
17 | Distribution Breaker(s) |  |  |  |  | 0 | 60000 | 0 | 5000 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
18 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 26.73 | 0
10 | MCC's |  |  |  |  | 0 | 20000 | 0 | 0 | 0 | 10 | 1 | 1 | 0 | 101 | 0
11 | PDC Modifications |  |  |  |  | 1 | 75000 | 75000 | 3000 | 3000 | 10 | 5 | 10 | 500 | 26.73 | 13365
12 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
13 | 600V
14 | Distribution Panel(s) |  |  |  |  | 1 | 85000 | 85000 | 2500 | 2500 | 10 | 2 | 5 | 100 | 26.73 | 2673
15 | GTG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
16 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 26.73 | 0
17 | Liquid Fuel MCC |  |  |  |  | 1 | 20000 | 20000 | 2000 | 2000 | 10 | 3 | 2 | 60 | 26.73 | 1603.8
18 | BOP MCC(s) |  |  |  |  | 1 | 20000 | 20000 | 1000 | 1000 | 10 | 2 | 3 | 60 | 26.73 | 1603.8
19 | Water Treatment MCC(s) |  |  |  |  | 0 | 10000 | 0 | 500 | 0 | 10 | 2 | 3 | 0 | 26.73 | 0
20 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 26.73 | 0
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 26.73 | 0
22 | Aux Transformer(s)
23 | 15/5KV ___________ MVA |  |  |  |  | 2 | 0 | 0 | 5000 | 10000 | 10 | 3 | 5 | 300 | 26.73 | 8019
24 | 15/600V ___________ MVA |  |  |  |  | 0 | 80000 | 0 | 5000 | 0 | 10 | 3 | 4 | 0 | 26.73 | 0
| 15/600v Aux MVA |  |  |  |  | 1 | 0 | 0 | 5000 | 5000 | 10 | 3 | 5 | 150
25 | 600/120/208V ________ KVA |  |  |  |  | 1 | 5000 | 5000 | 500 | 500 | 10 | 2 | 2 | 40 | 26.73 | 1069.2
26 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
27 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
28 | Area Lighting
29 | Poles _______ High |  |  |  |  | 0 | 1500 | 0 | 250 | 0 | 10 | 4 | 2 | 0 | 26.73 | 0
30 | Floodlights _______ Watts |  |  |  |  | 0 | 450 | 0 | 100 | 0 | 10 | 1 | 0.2 | 0 | 26.73 | 0
31 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 26.73 | 0
33 | Other Systems
34 | UPS |  |  |  |  | 1 | 15000 | 15000 | 2000 | 2000 | 10 | 3 | 4 | 120 | 26.73 | 3207.6
35 | DC |  |  |  |  | 1 | 20000 | 20000 | 5000 | 5000 | 10 | 3 | 4 | 120 | 26.73 | 3207.6
36 | Cathodic Protection |  |  |  |  | 2 | 20000 | 40000 | 1500 | 3000 | 10 | 3 | 8 | 480 | 26.73 | 12830.4
37 | Lightning Protection |  |  |  |  | 2 | 15000 | 30000 | 1500 | 3000 | 10 | 3 | 8 | 480 | 26.73 | 12830.4
38 | [10 empty] | 10 | 0 | 0 | 0 | 26.73 | 0
39
40 | Temporary Electric |  |  |  |  | 1 | 40000 | 40000 | 2000 | 2000 | 10 | 2 | 30 | 600 | 26.73 | 16038
41 | Electrical Control Module |  |  |  |  | 0 | 65000 | 0 | 3000 | 0 | 10 | 4 | 6 | 0 | 26.73 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
43 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
44 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
45 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 26.73 | 0
|  |  | Total Cost of Electrical Equipment |  |  |  |  | 860 |  | 50 |  |  |  | 30930 |  | 822.7494
[14 empty] | 30930 |  |  | 38 | 1175340
[12 empty] | Productivity | 2 | 61860 | 26.73 | 1653.5178
Price per hour based on a 50 hr week with all labor
burdens as follows:
[13 empty] | Local Hrly Cost |  | 15
[13 empty] | Labor Burden 35% |  | 5.25
20.25
[13 empty] | Contr Mark up 20% |  | 4.05
24.3
[13 empty] | 45 hrs = 1.1 |  | 26.73
| Cable, Conduit and Tray - Labor | [6 empty] | 2000 |  |  | Labor |  |  | 17500 |  |  | 38 | 665000
[12 empty] | Productivity | 2 | 35000 | 26.73 | 935.55
[11 empty] | 4 | 2 | 45 | 0 | 93.0386 | 0
[11 empty] | 16 | 32 | 45 | 0 | 93.0386 | 0
Blended
51.05
17.8675
68.9175
13.7835
82.701
93.0386

## 4.2 & 4.4 Substa Eq & Labor
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [13 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [13 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [13 empty] | Est By:
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
Nol | [7 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | Main Power Transformer 345 KV, 200 MVA (All-in Price) | [5 empty] | 1 | 0 | 0 | 50000 | 50000 | 10 | 4 | 6 | 240 | 26.73 | 6415.2
2 | SF6 Circuit Breaker(s) _132 KV | [5 empty] | 1 | 0 | 0 | 2500 | 2500 | 10 | 4 | 3 | 120 | 26.73 | 3207.6
3 | Disconnect Switches _132_ KV | [5 empty] | 1 | 0 | 0 | 1000 | 1000 | 10 | 4 | 1 | 40 | 26.73 | 1069.2
4 | Station Post Insulators ____ KV | [5 empty] | 0 | 550 | 0 | 0 | 0 | 10 | 2 | 0.05 | 0 | 26.73 | 0
5 | Insulator Stanchons __21__ High | [5 empty] | 0 | 500 | 0 | 0 | 0 | 10 | 1 | 0.5 | 0 | 26.73 | 0
6 | Insulator Stanchons __13__ High | [5 empty] | 0 | 500 | 0 | 0 | 0 | 10 | 1 | 0.4 | 0 | 26.73 | 0
7 | Dead End Tower(s) | [5 empty] | 0 | 0 | 0 | 7000 | 0 | 10 | 0 | 5 | 0 | 26.73 | 0
8 | Alum Bus ______ Dia | [5 empty] | 0 | 18 | 0 | 3 | 0 | 10 | 1 | 0.08 | 0 | 26.73 | 0
9 | Alum Bus Conn's | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 26.73 | 0
10 | Alum Bus End Plugs _____ Dia | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.05 | 0 | 26.73 | 0
11 | Alum Bus Support Clamps | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 26.73 | 0
12 | Alum Bus "V" Conn's | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.08 | 0 | 26.73 | 0
13 | Static Wire Poles, ____ High | [5 empty] | 0 | 4000 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 26.73 | 0
14 | Area Lighting Poles, ____ High | [5 empty] | 0 | 1500 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 26.73 | 0
15 | Flood Lights, ______ Watts | [5 empty] | 0 | 450 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 26.73 | 0
16 | #4/0 Grounding Conductor | [5 empty] | 0 | 20000 | 0 | 0 | 0 | 10 | 2 | 20 | 0 | 26.73 | 0
17 | 3/4"x10'-0" Ground Rods & Clamps | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | .04 | 0 | 26.73 | 0
18 | #90 Cadweld Shots | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | .3 | 0 | 26.73 | 0
19 | Metering CT's & CPT's | [5 empty] | 0 | 50000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0 | 0
20 | Station Metering w/ In & Out Capabilities | [5 empty] | 0 | 50000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
21 | Station Protective Relay(s) | [5 empty] | 0 | 50000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
22 | Station RTU | [5 empty] | 0 | 40000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 26.73 | 0
23 | 125V DC System | [5 empty] | 0 | 25000 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 26.73 | 0
24 | Transmission Line Poles | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 2 | 0 | 26.73 | 0
25 | Transmission Line Strain Insulators | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 26.73 | 0 | 0
26 | Cable Bus, Type _____, Size _____ | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 6 | 0 | 26.73 | 0
27 | Main Power Transformer Oil, ______ Gal | [5 empty] | 1 | 75000 | 75000 | 10000 | 10000 | 10 | 2 | 2 | 40 | 26.73 | 1069.2
28 | Main Power Transformer Dress Out & Test | [5 empty] | 1 | 75000 | 75000 | 0 | 0 | 10 | 2 | 2 | 40 | 26.73 | 1069.2
29 | Fiber Optic Cable w/ Messenger Cable | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 26.73 | 0 | 0
30 | Misc Equip | [5 empty] | 0 | 200000 | 0 | 0 | 0 | 10 | 2 | 30 |  |  | 0
31
32 | Price per hour based on a 50 hr week with all labor |  |  |  | Total: 0
33 | burdens as follows: |  |  |  | Total: 0
34 |  |  |  |  | Total: 0
35 |  | Local Hrly Cost |  | 15 | Total: 0
36 |  | Labor Burden 35% |  | 5.25 | Total: 0
37 |  |  |  | 20.25 | Total: 0
38 |  | Contr Mark up 20% |  | 4.05 | Total: 0
39 |  |  |  | 24.3
40 |  | 60hrs = x1.1 |  | 26.73
41
42
43
44 |  |  |  |  | Total: 0
|  |  | Total Cost of Substation Equipment |  | Total: 150; Frt: 63.5; Qty: 480; Total: 12.8304
[13 empty] | Total Hours |  | 480
[13 empty] | Prod Factor | 2 | 960 | 26.73 | 25.6608

## 5.1 CEMS
CEM's
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Cems | Cost | Cost
1 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 120 | 0
2 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 130 | 0
3 | Installation Support |  |  |  |  | 0 | 18 | 0
|  |  | Total Cost of CEM's |  |  |  |  | 0

## 5.2 Instrument
PLANT INSTRUMENTATION
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [9 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [9 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [9 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total
Nol |  |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | Instrumentation for GTG |  |  |  | 2 | 75000 | 150000 | 10 | 4 | 10 | 800 | 26.73 | 21384
0
2 | Instrumentation for SCR |  |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 26.73 | 0
3 | Instrumentation for HRSG |  |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 62 | 0
4 | Instrumentation for Injection Water Treatment |  |  |  | 1 | 25000 | 25000 | 10 | 4 | 5 | 200 | 26.73 | 5346
5 | Instrumentation for Liquid Fuel System |  |  |  | 1 | 25000 | 25000 | 10 | 2 | 7 | 140 | 26.73 | 3742.2
6 | Instrumentation for gas metering |  |  |  | 1 | 50000 | 50000 | 10 | 4 | 5 | 200 | 26.73 | 5346
7 | Labor to Install CEMS |  |  |  | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 26.73 | 0
Price per hour based on a 50 hr week with all labor
burdens as follows:
|  | Local Hrly Cost |  | 15
|  | Labor Burden 35% |  | 5.25
20.25
|  | Contr Mark up 20% |  | 4.05
24.3
|  | 45hrs = x1.1 |  | 26.73
|  |  | Total Cost of Plant Instrumentation |  | Total: 250; Qty: 1340; Total: 35.8182
[9 empty] | Total Hours |  | 1340
[9 empty] | Prod Factor | 2 | 2680 | 26.73 | 71.6364

## 6.1 DCS Hard
DCS HARDWARE
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [6 empty] | Cost | Cost
1 | DCS Hardware |  |  |  |  | 1 | 225000 | 225000
0
0
2 | Lot of Misc interconnecting cables etc. |  |  |  |  | 2 | 15000 | 30000
3 | PBX Communications System |  |  |  |  | 1 | 15000 | 15000
0
4 | Loud Speaker System |  |  |  |  | 1 | 15000 | 15000
5 | Documentation |  |  |  |  | 1 | 35000 | 35000
|  |  | Total Cost of DCS Software |  |  |  |  | 320

## 6.2 DCS Soft
DCS SOFTWARE
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Hrs | Cost | Cost
1 | Software for DCS |  |  |  |  | 1800 | 75 | 135000
2 | Software for O & M Package |  |  |  |  | 600 | 60 | 36000
3 | Mark VI Download |  |  |  |  | 0 | 6000 | 0
|  |  | Total Cost of DCS Software |  |  |  |  | 171

## 7.1 Erection
PLANT ERECTION
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [7 empty] | Date: | 2009-08-14 |  |  | *.2
Customer: |  | Corprolec | [7 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [7 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  | No | Hours | Qty | Qty | Qty | Rate | Total
Nol |  |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | GTG Erection |  |  |  | 2 | 10 | 24 | 132 | 63360 | 21.384 | 1354890.24
2 | HRSG Erection |  |  |  | 0 | 10 | 10 | 60 | 0 | 21.384 | 0
3 | SCR Erection |  |  |  | 0 | 10 | 10 | 60 | 0 | 21.384 | 0
4 | Water Treatment and FW Systems |  |  |  | 0 | 6 | 6 | 30 | 0 | 21.384 | 0
5 | Liquid Fuel system |  |  |  | 0 | 6 | 6 | 20 | 0 | 21.384 | 0
6 | BOP Equip Erection |  |  |  | 1 | 10 | 10 | 10 | 1000 | 21.384 | 21384
7 | Gas Compressor Erection |  |  |  | 0 | 10 | 6 | 5 | 0 | 21.384 | 0
8 | Evap Cooling Erection |  |  |  | 0 | 10 | 4 | 4 | 0 | 21.384 | 0
9 | Fire Water Pump Skid |  |  |  | 0 | 10 | 4 | 4 | 0 | 21.384 | 0
10 | STG Erection |  |  |  | 0 | 10 | 12 | 36 | 0 | 21.384 | 0
11 | STG Cooling Tower |  |  |  | 0 | 10 | 8 | 8 | 0 | 21.384 | 0
Price per hour built up as follows:
Blended
|  | Local Hrly Cost |  | 12
|  | Lab Burden 35% |  | 4.2
16.2
|  | Contr Mark up 20% |  | 3.24
19.44
| For 45 hr / wk multiply by 1.1 |  |  | 21.384
|  |  | Total Cost of Plant Erection | [5 empty] | 64360 |  | 1376.2742 | Bs cost | Bs Total
[7 empty] | Total Hours |  | 64360 |  |  | 38 | 2445680
[7 empty] | Prod Factor | 1.5 | 96540 | 21.384 | 2064.4114

## 8.2 Equip rent
EQUIPMENT RENTAL
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [6 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [6 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [6 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total
Nol | [5 empty] | Units | Unit | Days | Per Day | Cost | Bs Cost | Bs Total
1 | GTG Equip Rental per ea GTG
| 1 ea 300 Ton Crane w/ operator |  |  |  |  | 2 | 40 | 80 | 4000 | 320000
| 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
| 1 ea 50 Ton Crane w/ operator |  |  |  |  | 2 | 120 | 240 | 2000 | 480000
| 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
| 2 ea Sky Tracs |  |  |  |  | 2 | 120 | 240 | 70 | 16800
| 2 ea Fork Lifts |  |  |  |  | 2 | 120 | 240 | 70 | 16800
| 1 ea Man Lift |  |  |  |  | 2 | 120 | 240 | 80 | 19200
| 2 ea Welders |  |  |  |  | 2 | 150 | 300 | 60 | 18000
2 | HRSG Erection
| 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
| 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
| 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
| 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
| 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
| 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
| 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
3 | SCR/CO
| 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
| 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
| 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
| 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
| 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
| 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
| 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
4 | STG
| 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
| 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
| 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
| 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
| 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
| 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
5 | STG Cooling Tower
| 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
| 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
| 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
6 | Fuel Gas Compressor Rental per Compr Skid
| 1 ea 150 Ton Crane w/ operator |  |  |  |  | 1 | 10 | 10 | 3000 | 30000
| 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
7 | BOP Equip Rental per ea GTG
| 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
| 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
| 1 ea 50 Ton Crane w/ operator |  |  |  |  | 1 | 40 | 40 | 2000 | 80000
| 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 180 | 180 | 1500 | 270000
| 2 ea Fork Lifts |  |  |  |  | 1 | 120 | 120 | 70 | 8400
| 2 ea Sky Tracs |  |  |  |  | 2 | 160 | 320 | 70 | 22400
| 2 ea Pick ups |  |  |  |  | 2 | 90 | 180 | 30 | 5400
| 1 ea Front End Loader / Back Hoe |  |  |  |  | 1 | 160 | 160 | 70 | 11200
8 | Substation Equip Rental (GSU Only)
| 1 ea 200 Ton Crane w/ operator |  |  |  |  | 2 | 10 | 20 | 4000 | 80000
| 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
| 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 120 | 120 | 1500 | 180000
| 2 ea Man Lifts |  |  |  |  | 1 | 120 | 120 | 80 | 9600
| 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
| 5 ea Welders |  |  |  |  | 2 | 120 | 240 | 80 | 19200
9 | Heavy Lift of GTG and Gen |  |  |  |  | 1 | 150000 |  |  | 150000
|  |  | Total Cost of Plant Equip Rental |  |  |  |  | 2490 |  | 1737

## 9.0 Paint
PLANT PAINTING
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Units | Cost | Cost
1 | Paint for GTG |  |  |  |  | 2 | 100000 | 200000
2 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0
3 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0
4 | Paint for Pipe Rack etc. |  |  |  |  | 2 | 25000 | 50000
5 | Paint for BOP Equipment |  |  |  |  | 1 | 25000 | 25000
6 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0
7 | Paint for Water Treatment |  |  |  |  | 0 | 15000 | 0
8 | Paint for Waste Water Treatment |  |  |  |  | 0 | 15000 | 0
9 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0
|  |  | Total Cost of Plant Painting |  |  |  |  | 275
0

## 10.0 Transportation
PLANT TRANSPORTATION
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Units | Cost | Cost
1 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 240 | 240
2 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 50 | 50
3 | Transportation Substation Equip |  |  |  |  | 1 | 63.5 | 63.5
4 | Transportation of GTG
5 | Transportation of SCR
6 | Transportation of HRSG
7 | Transportation of M isc Equip | [6 empty] | 100
|  |  | Total Cost of Plant Transportation |  |  |  |  | 453.5

## 11.0 Site Costs
SITE COSTS
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant | [6 empty] | Date: | 2009-08-14
Customer: |  | Corprolec | [6 empty] | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn | [6 empty] | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total
Nol | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost
1 | Monthly Site Costs
| Office Trailers |  |  |  |  | 4 | 10 | 900 | 36000
| Porta Potties |  |  |  |  | 4 | 10 | 150 | 6000
| Water and Ice |  |  |  |  | 4 | 10 | 500 | 20000
| Fed X |  |  |  |  | 1 | 10 | 300 | 3000
| Telephone |  |  |  |  | 1 | 10 | 2500 | 25000
| Office Supplies |  |  |  |  | 1 | 10 | 1000 | 10000
10
| Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 10 | 4000 | 40000
| Misc Items |  |  |  |  | 1 | 10 | 3000 | 30000
|  |  | Total Monthly Cost | [5 empty] | 170000
2 | Total Project Cost = Cost per Month Times Number of Mos
Plus the Project One Time Costs.
| Monthly Site Costs | [5 empty] | 1 | 170000 |  | 170000
| One Time Costs | [5 empty] | 0
| 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 150000
| Cad Station | [8 empty] | 10000
| Computers | [8 empty] | 15000
| Telephone System and Satalite Dish | [8 empty] | 15000
| Plotter | [8 empty] | 10000
| Fax Machine and Printers | [8 empty] | 2500
| Misc equip | [8 empty] | 150000
|  |  | Total Cost of Project Site Costs | [6 empty] | 522.5

## 12.1 Engineering
ENGINEERING
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Units | Cost | Cost
1 | Conceptual Engineering PEPC |  |  |  |  | 1 | 25000 | 25000
2 | Detailed Engineering per GTG |  |  |  |  | 2 | 350000 | 700000
3 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
4 | Detailed Engineering Liquid Fuel |  |  |  |  | 0 | 15000 | 0
5 | Detailed Engineering of Substation |  |  |  |  | 0 | 40000 | 0
6 | Detailed Engineering per Water Treatment |  |  |  |  | 0 | 35000 | 0
7 | Detailed Engineering for civil/structural |  |  |  |  | 1 | 225000 | 225000
8 | Documentation |  |  |  |  | 1 | 60000 | 60000
|  |  | Total Cost of Engineering |  |  |  |  | 1010

## 12.2 Local Engr-Arch
LOCAL ENGINEERING
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Units | Cost | Cost
1 | Soils & Environmental Eng |  |  |  |  | 1 | 15000 | 15000
2 | Civil Engineer |  |  |  |  | 1 | 50000 | 50000
3 | Mechanical Engineer |  |  |  |  | 1 | 50000 | 50000
4 | Electrical Engineer |  |  |  |  | 1 | 50000 | 50000
5 | Other |  |  |  |  | 0 | 0 | 0
|  |  | Total Cost of Local Engineering |  |  |  |  | 165

## 12.3 Engr Trav & per diem
ENGINEERING TVL AND PER DIEM
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Qty | Unit | Total
Nol | [5 empty] | Units | Cost | Cost
1 | [5 empty] | 0 | 0 | 0
2 | RT to Job Site |  |  |  |  | 12 | 2500 | 30000
3 | [5 empty] | 120 | 250 | 30000
4 | Days of Per Diem cost for Eng Days at Job Site |  |  |  |  | 300 | 180 | 54000
5 | [5 empty] | 0 | 100 | 0
6 | Auto Rental for Eng Days at Job Site |  |  |  |  | 300 | 150 | 45000
4 | Misc Travel Expentitures |  |  |  |  | 1 | 30000 | 30000
|  |  | Total Cost of Eng Tvl and Per Diem |  |  |  |  | 189

## 13.1 Proj Mgt Labor
PROJECT MANAGEMENT LABOR
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
160
Item |  | Description |  |  |  | No. | Cost | Total | hr/mo
Nol | [5 empty] | Mos | Per Mo | Cost
Project Mng't Home Office
1 | Project Mgr Months on Project |  |  |  |  | 10 | 17000 | 170000 | 1600
2 | Admin Mgr Months on Project |  |  |  |  | 10 | 7000 | 70000 | 1600
3 | Scheduler |  |  |  |  | 10 | 7000 | 70000 | 1600
4 | Purchasing Agent |  |  |  |  | 3 | 7000 | 21000 | 480
5 | Expediter |  |  |  |  | 1 | 5000 | 5000 | 160
6 | Home Office Logistic Coordinator |  |  |  |  | 6 | 12000 | 72000 | 960
Project at Job Site
7 | Secretary at Job Site |  |  |  |  | 9 | 6000 | 54000 | 1440
8 | Construction Mngr |  |  |  |  | 9 | 15000 | 135000 | 1440
9 | Contract Cost admin |  |  |  |  | 0 | 8000 | 0 | 0
10 | Mechanical Supervisor |  |  |  |  | 9 | 17000 | 153000 | 1440
11 | Electrical Supervisor |  |  |  |  | 9 | 17000 | 153000 | 1440
12 | Civil Supervisor |  |  |  |  | 8 | 17000 | 136000 | 1280
13 | Clerks |  |  |  |  | 14 | 5000 | 70000 | 2240
14 | Warehousemen |  |  |  |  | 14 | 4000 | 56000 | 2240
| site Engineer |  |  |  |  | 10 | 18000 | 180000 | 1600
15 | Draftsman |  |  |  |  | 6 | 9000 | 54000 | 960
16 | Security |  |  |  |  | 9 | 15000 | 135000 | 1440
17 | Safety |  |  |  |  | 9 | 12000 | 108000 | 1440
18 | QA/QC Mngr |  |  |  |  | 9 | 12000 | 108000 | 1440
|  |  |  | Total Proj Mgt Labor |  |  |  | 1750000 | 0
| US Electricians and Welders 6ea plus 6 ea 6 mos |  |  |  |  | 36 | 15000 | 540000 | 5760
19 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 8 | 15000 | 120000 | 1280
[8 empty] | 0 | 0
20 | Inspectors | [6 empty] | 0 | 0
| Civil - Structual __ ea ___ mos |  |  |  |  | 8 | 12000 | 96000 | 1280
| Mechanical __ ea ___ mos |  |  |  |  | 12 | 12000 | 144000 | 1920
| Electrical __ ea ___ mos |  |  |  |  | 12 | 12000 | 144000 | 1920
| Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 8 | 12000 | 96000 | 1280
0
21 | Training |  |  |  |  | 1 | 40000 | 40000
|  |  | Total Cost of Project Mgt Labor |  |  |  |  | 2930 | 38240

## 13.2 Proj MGT TVL Per
PROJECT MGT TVL AND PER DIEM
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | No. | Cost | Total
Nol | [5 empty] | Units | Per Unit | Cost
1 | [5 empty] | 0 | 0 | 0
2 | RT Fares to Job Site 15 @ 7 trips |  |  |  |  | 110 | 2500 | 275000
3 | [5 empty] | 0 | 2200 | 0
4 | [5 empty] | 0 | 1000 | 0
5 | Months of Per Diem at Job site (10 men 8 mos) |  |  |  |  | 150 | 3500 | 525000
6 | Months of Pick up Trucks (6ea 12 mos) |  |  |  |  | 160 | 1200 | 192000
7 | Misc Expenditures |  |  |  |  | 1 | 250000 | 250000
8 | [5 empty] | 0 | 0 | 0
9 | [5 empty] | 0 | 0 | 0
10 | [5 empty] | 0 | 0 | 0
11 | [5 empty] | 0 | 0 | 0
12 | [5 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
0
0
0
0
0
|  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  |  |  | 1242

## 15.0 Sales Tax
SALES TAXES
(1,000's)
Project Name: |  | ENELVEN 2ea Fr VII EA's Power Plant |  |  |  |  | Date: | 2009-08-14
Customer: |  | Corprolec |  |  |  |  | Quote No: | T-9005 C
Location: |  | Maracaibo, Venn |  |  |  |  | Est By: | WTS/DW/JD
Bid Due Date: |  | 2009-08-14
Item |  | Description |  |  |  | Total | State | Total
Nol | [5 empty] | Cost | Tax | Taxes
1 | Major Mechanical Equipment |  |  |  |  | 5680 | 0.0825 | 468.6
2 | Major Electrical Equipment |  |  |  |  | 860 | 0.0825 | 70.95
3 | Substation Equipment |  |  |  |  | 150 | 0.0825 | 12.375
4 | DCS Eqipment |  |  |  |  | 320 | 0.0825 | 26.4
5 | Instrument |  |  |  |  | 250 | 0.0825 | 20.625
|  |  | Total Cost of Plant Sales Taxes |  |  |  |  | 0