## Sheet1
Description | Qty. | Equipment | TSD | CP | O&M | LOC | To be invoice
Freight of 2 x Fr-7FA | 2 | Fr 7FA |  | X
La Raisa II | 2 | LM6000 | X | X
Barinas 1 | 2 | FT-4 |  | X |  |  | X
Morichal | 2 | LM6000 |  | X
Jose | 4 | RR Trent60 |  | X
Pigag II | 2 | FT-8 | X | X
COB-BARE (Petropiar) | 2 | FT-8 | X | X
Las Morochas | 1 | LM2500
La Guajira |  | 25 MW Wind Farm | X | X | X
PDVSA 2nd Order | 3 ea | FT-8 / RR Trent60 |  |  |  | X
Curapo | 2 | Fr 7FA | X | X | ?
El Furrial | 4 | RR Trent60 |  |  | X |  | X
GSU | 2 | Fr 7FA |  |  |  |  | X
GSU | 2 | LM6000 |  |  |  |  | X
Exhaust stack | 3 | Tacoa A&B |  |  |  |  | X

## Sheet2
Client | Project | Pending | Cost Impact (US$) | Cost Impact (BsF.) | Responsible
EDC | Tacoa A | Change orders. Not inclusive of the extra work under the accelerated mandate | 2100000 |  | Neil - Derwick
|  | Freight BOP |  |  | David W.
|  | Outstanding invoices | 4087580 |  | Brett - Derwick
| Tacoa B | Freight BOP |  |  | Neil - Derwick
|  | Outstanding invoices | 4507260 |  | Brett - Derwick
| La Raisa | Outstanding invoices | 6200000 | 9399012 | Brett - Derwick
|  | Change orders. Not inclusive of the extra work under the accelerated mandate | 4500000 | 4300000 | Craig - Derwick
|  | Freight BOP |  |  | Craig - Derwick
|  | Engineering on site |  |  | David W.
Scheduler
|  | Various attached * |  |  | David W.
| La Raisa II | Aqueduct | Cost plus | Cost plus
|  | Contract Signing - PES/Derwick |  |  | Scott
|  | Pending payment |  |  | Brett - Derwick
| Guarenas | Equipment payment |  |  | Joaquin-Derwick
|  | Change orders for xtras |  |  | JD-Derwick
|  | Addition of gas compressors |  |  | JD-Derwick
|  | Time lost due to EDC not clearing site material to allow unit 400 foundation works |  |  | JD-Derwick
|  | Change order (4th unit addition) |  |  | David W.
|  | Vepica |  |  | JD-Derwick
|  | Engineering on site |  |  | JD-Derwick
|  | Scheduler |  |  | JD-Derwick
Client | Project | Pending | Cost Impact (US$) | Cost Impact (BsF.) | Responsible
EDC | Curuapo | Contract |  |  | Scott
|  | Storage place |  |  | Mark-Derwick
|  | Equipment - HV -Cost | 3482914 |  | Bill-Derwick
|  | Freight payment | 3120000 |  | Mark-Derwick
CVG | Plant A | Outstanding invoices | 27800000 |  | Brett-Derwick
|  | Delta from budget to actual billings by consortium for primary foundations | 1200000 |  | Brett-Derwick
|  | Payments for milestone due | 32953250 |  | Brett-Derwick
|  | O&M |  |  | Joaquin
|  | Freight issues |  |  | DW
| Plant B | Outstanding invoices |  |  | Brett-Derwick
|  | Delta from budget to actual billings by consortium for primary foundations |  |  | Brett-Derwick
|  | Payments for milestone due | 15880000 |  | Brett-Derwick
|  | O&M |  |  | Joaquin
|  | Freight issues |  |  | Mark-Derwick
PDVSA | Barinas 1 | Comercial proposal | N/A | N/A | EPC
| Morichal | Comercial proposal | N/A | N/A
| Jose | Comercial proposal | N/A | N/A
| COB | TSD | None | None
|  | Comercial proposal | N/A | N/A
| Pigap | TSD | None | None
|  | Comercial proposal | N/A | N/A
Client | Project | Pending | Cost Impact (US$) | Cost Impact (BsF.) | Responsible
PDVSA | Las Morochas | Contract signing - PES/Derwick |  |  | Scott D
|  | Payment |  |  | Omar-Derwick
| El Furrial | Contract signing - PES/Derwick |  |  | Scott D
|  | Payment |  |  | Omar-Derwick
| Margarita | Contract signing - PES/Derwick |  |  | Tom-Derwick
|  | Payment |  |  | Brett Derwick
|  | Cost already incurred | 2000000 |  | Brett Derwick
| PDVSA II | LOC | 206946000 |  | Joaquin-Scott
Enelven | TZ-4 | LTSA | N/A | N/A | PTS
* Various:
1. Relocation of the Gas Metering Station
2. Relocation of the Liquid Fuel Offload Station
3. Increase in size of the Liquid Fuel Offload from (2) to (4) Trucks at a time
4. Relocation of the Office and Control Buildings
5. Change in design of all buildings from metal, pre-engineered to masonary block (Note: Buildings have already be purchased from Septagon)
6. Individual gas pipeline runs to each GT from the gas compressors instead of a header system as originally designed
7. All piping moved above ground instead of direct burial as originally designed
8. Fuel Tank leak detection
9. Concrete containment for Fuel Tanks instead an earthen burm as originally designed