Gas Turbine Inspection Estimated Hours

| Gas Turbine Outage Numbers |  |  |  |  |
| --- | --- | --- | --- | --- |
| Flange to Flange |  |  |  |  |
|  | CI | HG | Major | Travel Hours for T/A's |
| Frame 3 (H Model) |  |  |  |  |
| Hours | 3/12 hour shifts | 6/12 hour shift | 12/12 hour shift |  |
| Man Power | 4 men per shifts | 6 men per shifts | 8 men per shifts |  |
| T/A's | 1 per shift | 1 per shift | 1 per shift |  |
| Total Man Hours | 150 Hours | 450 Hours | 1200 Hours |  |
| T/A's Hours | 36 Hours | 72 Hours | 144 Hours | 32 Hours |
| Frame 5 (N,P,R Models) |  |  |  |  |
| Hours | 5/12 hour shifts | 12/12 hour shifts | 20/12 hour shifts |  |
| Man Power | 4 men | 6 men | 8 men |  |
| T/A's | 1 per shift | 1 per shift | 1 per shift |  |
| Total Man Hours | 240 Hours | 865 Hours | 1920 Hours |  |
| Supervision Hours | 60 Hours | 144 Hours | 240 Hours | 32 Hours |
| Frame 6 (B Model) |  |  |  |  |
| Hours | 6/12 hour shifts | 12/12 hour shifts | 25/12 hour shifts |  |
| Man Power | 4 men per shift | 6 men per shift | 8 men per shift |  |
| T/A's | 1 per shift | 1 per shift | 1 per shift |  |
| Total Man Hours | 300 Hours | 900 Hours | 2400 Hours |  |
| Supervision Hours | 72 Hours | 144 Hours | 300 Hours | 32 Hours |
| Frame 7 (A,B,C,E Models) |  |  |  |  |
| Hours | 8/12 hour shifts | 20/12 hour shifts | 40/12 hour shifts |  |
| Man Power | 6 men per shift | 8 men per shift | 10 men per shift |  |
| T/A's | 1 per shift | 1 per shift | 1 per shift |  |
| Total Man Hours | 576 Hours | 1920 Hours | 4800 Hours |  |
| T/A's Supervision Hours | 130 Hours | 280 Hours | 516 Hours | 32 Hours |
| Frame 7 (FA Model) |  |  |  |  |
| Hours | 10/12 hour shifts | 22/12 hour shifts | 46/12 hour shifts |  |
| Man Power | 7 men per shifts | 9 men per shift | 11 men per shift |  |
| T/A's | 1 per shift | 1 per shift | 1 per shift |  |
| Total Man Hours | 840 Hours | 2400 Hours | 6100 Hours |  |
| Supervision Hours | 120 Hours | 264 Hours | 552 Hours | 32 Hours |
| Hours do not include travel time. |  |  |  |  |