## Proposal Cost Analysis
Proposal Number:
Customer:
Project:
Length of Project | 21 | Hours/Day |  | 8 |  | Total Hours (ST) |  | 168
Length of Project | 21 | Hours/Day |  | 4 |  | Total Hours (OT) |  | 84
Setup/Dismantle | Qty | Rate | Billable | Hours |  |  | OT | Billable | Hours |  | Cost | Billable
Electrical Specialist |  | 61.255 | 80 |  |  |  | 91.8825 | 120 |  |  | 0 | 0
Mechanical Specialist | 2 | 61.255 | 80 | 16 |  |  | 91.8825 | 120 |  |  | 1960.16 | 2560
Rotating Equip Specialist |  | 61.255 | 80 |  |  |  | 91.8825 | 120 |  |  | 0 | 0
I&E Technician |  | 55.1295 | 75 |  |  |  | 82.6942 | 112.5 |  |  | 0 | 0
DCS Technician |  | 61.255 | 80 |  |  |  | 91.8825 | 120 |  |  | 0 | 0
Boiler Specialist |  | 61.255 | 80 |  |  |  | 91.8825 | 120 |  |  | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | SubTotal | 1960.16 | 2560
Direct Labor | Qty | Rate | Billable | Hours |  |  | OT | Billable | Hours |  | Cost | Billable
Electrical Specialist |  | 61.255 | 80 | 168 |  |  | 91.8825 | 120 | 84 |  | 0 | 0
Mechanical Specialist | 15 | 61.255 | 80 | 168 |  |  | 91.8825 | 120 | 84 |  | 270134.55 | 352800
Rotating Equip Specialist |  | 61.255 | 80 | 168 |  |  | 91.8825 | 120 | 84 |  | 0 | 0
I&E Technician |  | 55.1295 | 75 | 168 |  |  | 82.6942 | 112.5 | 84 |  | 0 | 0
DCS Technician |  | 61.255 | 80 | 168 |  |  | 91.8825 | 120 | 84 |  | 0 | 0
Boiler Specialist |  | 61.255 | 80 | 168 |  |  | 91.8825 | 120 | 84 |  | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | SubTotal | 270134.55 | 352800
Indirect Labor | Qty | Rate | Billable | Proj Hrs | Other Hrs |  | OT | Billable | Hours |  | Cost | Billable
Technical Advisor | 2 | 76.5687 | 100 | 168 |  |  | 114.8531 | 150 |  |  | 25727.1 | 33600
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | SubTotal | 25727.1 | 33600
Travel | Qty | Mob/Demob | Perdiem | AirFare | Mileage | Rental Car | Parking | Fuel/Fees | Hotel | Laundry | Cost | Billable
Rates |  | 200 | 31 | 300 | 0.405 | 300 |  |  | 50 | 70
Electrical Specialist | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
Mechanical Specialist | 15 | 3000 | 63000 | [5 empty] | 15750 | 1050 | 82800 | 91080
Rotating Equip Specialist | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
I&E Technician | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
DCS Technician | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
Boiler Specialist | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0
Technical Advisor |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[7 empty] | MU | 10% |  | SubTotal | 82800 | 91080
Comission Costs | Component | [9 empty] | Cost | Billable
Direct Labor | At 3% | [9 empty] | 8162.8413 | 8162.8413
Indirect Labor | At 4% | [9 empty] | 771.813 | 771.813
[10 empty] | SubTotal | 8934.6543 | 8934.6543
Subcontractors | Service Provided | [9 empty] | Cost | Billable
Sub 1 | Change 1st & 2nd Stage buckets | [9 empty] | 10000 | 11000
Sub 2 | Extra TA | [9 empty] | 28000 | 30800
Sub 3 | [11 empty] | 0
Sub 4 | [11 empty] | 0
Sub 5 | [11 empty] | 0
[7 empty] | MU | 10% |  | SubTotal | 38000 | 41800
Other Expenses | See Proposal - Division of Reponsibilites & Tools and Materials Worksheets | [9 empty] | Cost | Billable
Rental Equipment | See Other Expenses Worksheet | [9 empty] | 0 | 0
Internal ProE Equip | See Other Expenses Worksheet | [9 empty] | 0 | 0
Reports | e.g. End of Project w/data sheets | [9 empty] | 0 | 0
Pre-Outage Meeting | [11 empty] | 0
Post-Outage Meeting | [11 empty] | 0
Safety Training | [11 empty] | 0
Background Check | [11 empty] | 0
Drug Screening | [11 empty] | 0
0
0
0
0
0
Capital Expenses | See Other Expenses Worksheet (Not billable to the client) | [9 empty] | 0
[7 empty] | MU | 10% |  | SubTotal | 0 | 0
[9 empty] | Summary Total |  | 427556.4643 | 530774.6543
[6 empty] | Warrantly = 3% (Summary-(Commission+Travel)) |  |  |  |  | 10074.6543 | 10074.6543
Preparer | [9 empty] | Total | 437631.1186 | 540849.3086
Division Approval | [9 empty] | Gross Profit |  | 103218.19
Company Approval | [9 empty] | GP% |  | 19.08%

## Labor Rates
Project: | Associated Electric | Project #: | FS05-0293 | 2005-07-12 | 1
Proposal Basis (assumptions) |  |  |  | Days Per Week | Shifts
TRADE OR CLASSIFICATION | Bill Rate | Profit
Electrical Specialist | 80 | 18.745
Mechanical Specialist | 80 | 18.745
Rotating Equipment Specialist | 80 | 18.745
I&E Technician | 75 | 19.8705
DCS Technician | 80 | 18.745
Boiler Specialist | 80 | 18.745
Technical Advisor | 100 | 23.4312
TRADE OR CLASSIFICATION | BASE RATE – STRAIGHT TIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE S/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 3% | 1.5% | 6.86% | 22.51% | 0% | 0% | 22.51%
Electrical Specialist | 50 | 3.825 | 0.4 | 1.35 | 0 | 1.5 | 0.75 | 3.43 | 61.255 | 0 | 0 | 61.255
Mechanical Specialist | 50 | 3.825 | 0.4 | 1.35 | 0 | 1.5 | 0.75 | 3.43 | 61.255 | 0 | 0 | 61.255
Rotating Equipment Specialist | 50 | 3.825 | 0.4 | 1.35 | 0 | 1.5 | 0.75 | 3.43 | 61.255 | 0 | 0 | 61.255
I&E Technician | 45 | 3.4425 | 0.36 | 1.215 | 0 | 1.35 | 0.675 | 3.087 | 55.1295 | 0 | 0 | 55.1295
DCS Technician | 50 | 3.825 | 0.4 | 1.35 | 0 | 1.5 | 0.75 | 3.43 | 61.255 | 0 | 0 | 61.255
Boiler Specialist | 50 | 3.825 | 0.4 | 1.35 | 0 | 1.5 | 0.75 | 3.43 | 61.255 | 0 | 0 | 61.255
Technical Advisor | 62.5 | 4.7812 | 0.5 | 1.6875 | 0 | 1.875 | 0.9375 | 4.2875 | 76.5687 | 0 | 0 | 76.5687
TRADE OR CLASSIFICATION | BASE RATE – OVERTIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE O/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 5% | 2% | 6.86% | 25.01% | 0% | 22% | 47.01%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Other Expenses
Rental Equipment | Rate/day | # Days | Cost | Internal ProEnergy Equipment | Rate/day | # Days | Cost
Office Trailers |  |  | 0 | Work Trucks |  |  | 0
Furniture (Desks, Tables, Chairs) |  |  | 0 | Electrical Trailer |  |  | 0
File Cabinet |  |  | 0 | Instrument Trailer |  |  | 0
Refrigerator / Microwave /Coffee Pot |  |  | 0 | Office Trailer |  |  | 0
Port-A- Johns |  |  | 0 |  |  |  | 0
Portable Wash Sink Or Other Available |  |  | 0 |  |  |  | 0
Welding Machine |  |  | 0 | Mechanical Equipment |  |  | 0
Air Compressor |  |  | 0 | Tool Conex |  |  | 0
Fax Machine |  |  | 0 | Job Boxes |  |  | 0
Printer (BW / Color Laser) |  |  | 0 | Mobile Crane |  |  | 0
Water / Ice Delivery |  |  | 0 | Welder |  |  | 0
Oxygen / Acetylene / Argon |  |  | 0 | Air Compressor |  |  | 0
Expendables |  |  | 0 | Borescope |  |  | 0
Scaffolding |  |  | 0 |  |  |  | 0
Lighting Availably For Night Shift |  |  | 0 |  |  |  | 0
Alignment Equipment |  |  | 0 | Electrical Equipment |  |  | 0
High Torque Equipment |  |  | 0 | Meggar |  |  | 0
|  |  | 0 | Hy-Pot |  |  | 0
|  |  | 0 | IR Scanner |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 | Instrumentation Equipment |  |  | 0
|  |  | 0 | Dead Weight Tester |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0
Total |  |  | 0 | Total |  |  | 0
Capital Expenses (Not Billable) |  |  | Cost
Computers
Printers
Fax/Copier Machine
Other IT Expenses
Tools
Total |  |  | 0