- Table of Contents

1	PROENERGY SERVICES SITE MANAGEMENT AND VISITORS	2

2	CONTRACTORS ON SITE TODAY	2

3	DAILY OVERVIEW	2

4	CRITICAL ACTION ITEMS	2

5	MATERIALS & EQUIPMENT ISSUES	2

6	PLANNED ACTIVITIES TOMORROW	2

7	CONSTRUCTION EQUIPMENT	3

8	SAFETY ITEMS	3

9	ENGINEERING / DRAWING ISSUES	3

10	ADDITIONAL COMMENTS	3

# PROENERGY SERVICES SITE MANAGEMENT AND VISITORS

| Carlos Gaset |  |
| --- | --- |

# CONTRACTORS ON SITE TODAY

Company			   Direct Labor 	  Supervision    	  Management

| ProEnergy Services |  |  | 1 |
| --- | --- | --- | --- |
| Eripe Lamilara | 65 | 5 | 2 |
| Doca | 42 | 1 | 1 |
| Paciffic Rim | 4 | 5 | 1 |

# DAILY OVERVIEW

- Cutting and bending re-bar.

- Installing rebar generator foundation.

- Installing main post on fence.

- Iseven our tank contractor is setting up camp.

- Still pouring concrete warehouse foundation

- Excavating tank ring T-5401-A and B

# CRITICAL ACTION ITEMS

- Needed prints for #2 and 3 turbine foundations

- Need foundation prints for all three stacks

- Need prints for all three main transformers

# MATERIALS & EQUIPMENT ISSUES

- Still waiting for bricks for main containment fence, promise from last week.

# PLANNED ACTIVITIES TOMORROW

- Continue excavating Tank T-5401-A and T5401 B

- Installing conduit on turbine foundation.

- Continue cutting and bending re-bar for turbine foundation 2&3

- Work on turbine foundation

# CONSTRUCTION EQUIPMENT

- 1 – 50T crane

- 1 –  forklifts.

- 1 – Backhoe

- 1 – 20’ truck

- 4 air compressors

- Company Truck

- 2 generators

# SAFETY ITEMS

Nothing to notify.

# ENGINEERING / DRAWING STATUS

Drawing status

| Discipline | Required | Released for Construction | % Complete |
| --- | --- | --- | --- |
| Civil – Underground |  | 39 |  |
| Electrical |  | 30 |  |
| Piping |  | 0 |  |
| Mechanical |  | 110 ( all tanks ) |  |
| Instrument / Controls |  | 0 |  |

# ADDITIONAL COMMENTS

- Pacific Rim Engineering send us a letter with procedure to fill the tank rim with sand.

      - We are still experiencing power outages during the day and night.

      - The pouring of the warehouse floor was a disaster, after all day we did not finish the floor. The plan is to finish on Monday afternoon at 1PM to start again.