## AVANCE PLAN y REAL
PROYECTO IPC PLANTA TERMOELÉCTRICA JOSEFA CAMEJO PUNTO FIJO EDO. FALCON
AVANCE PLANIFICADO
INICIO: 08/06/2006
|  |  | Meses | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Descripción | Duración | Inicio | Fin | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01
IPC PLANTA TERMOELÉCTRICA JOSEFA CAMEJO | 505 días | 2006-06-08 09:00 | 2008-04-25 19:00 | 0% | 1% | 2% | 3% | 5% | 8% | 11% | 13% | 16% | 21% | 28% | 36% | 45% | 55% | 66% | 76% | 83% | 88% | 92% | 95% | 98% | 99% | 100%
INGENIERÍA INTEGRAL | 336 días | 2006-06-08 09:00 | 2007-08-22 17:00 | 0% | 2% | 6% | 10% | 18% | 27% | 37% | 44% | 49% | 55% | 66% | 81% | 90% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
PROCURA DE EQUIPOS | 422 días | 2006-06-08 09:00 | 2007-11-30 19:00 | 0% | 1% | 2% | 4% | 5% | 7% | 11% | 14% | 19% | 27% | 38% | 51% | 65% | 79% | 88% | 95% | 98% | 99% | 99% | 100% | 100% | 100% | 100%
CONSTRUCCIÓN | 476 días | 2006-06-08 09:00 | 2008-02-01 19:00 | 0% | 0% | 0% | 1% | 2% | 2% | 3% | 3% | 4% | 5% | 6% | 7% | 11% | 17% | 33% | 50% | 63% | 73% | 82% | 90% | 97% | 99% | 100%
COMMISSIONING O PRUEBAS EN CALIENTE | 80 días | 2008-01-24 09:00 | 2008-02-25 19:00 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 33% | 100%
PRUEBAS DE PERFORMANCE | 69 días | 2008-12-18 09:00 | 2008-03-06 19:00 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33% | 100%
AVANCE REAL
INICIO: 08/06/2006
|  |  | Meses | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Descripción | Duración | Inicio | Fin | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01
IPC PLANTA TERMOELÉCTRICA JOSEFA CAMEJO | 505 días | 2006-06-08 09:00 | 2008-04-25 19:00 | 4% | 5% | 9% | 12% | 14% | 15% | 17% | 19% | 20% | 20% | 24% | 27% | 35% | 38%
INGENIERÍA INTEGRAL | 336 días | 2006-06-08 09:00 | 2007-08-22 17:00 | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 45% | 50% | 64% | 65% | 66% | 45%
PROCURA DE EQUIPOS | 422 días | 2006-06-08 09:00 | 2007-11-30 19:00 | 2% | 2% | 9% | 14% | 16% | 18% | 20% | 21% | 21% | 22% | 26% | 32% | 50% | 72%
CONSTRUCCIÓN | 476 días | 2006-06-08 09:00 | 2008-02-01 19:00 | 0% | 2% | 2% | 3% | 3% | 3% | 4% | 5% | 7% | 9% | 11% | 11% | 12% | 13%
COMMISSIONING O PRUEBAS EN CALIENTE | 80 días | 2008-01-24 09:00 | 2008-02-25 19:00 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PRUEBAS DE PERFORMANCE | 69 días | 2008-12-18 09:00 | 2008-03-06 19:00 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Gráficos Ing, Proc y Constr
KEY TERMS: | SPANISH=ENGLISH
Avance= Progress
Avance Planificado= Planned Progress
Avance Real= Real progress
PJC= Project Josefa Camejo
ingenieria= Engineering
Procura= Management
Construccion= Construction
Fecha de Corte= Dates