## InformPresent
TECHNICAL REPORT
" PROJECT THERMOELÉCTRIC PLANT JOSEFA CAMEJO "
" PROJECT'S PROGRESS" |  |  |  |  | PERIOD 06-14 to 06-20-2007.
progress Summary and Dates
|  |  | Initial Date | Ending Date | Planned Progress | Actual Progress | Differential
| GENERAL PROJECT |  | 2006-08-06 | 2008-06-03 | 55% | 38% | -17%
| Engineering |  | 2007-08-02 | 30/8/2007 | 78% | 45% | -33%
| Procurement |  | 2006-01-03 | 30/11/2007 | 79% | 72% | -7%
| Constructión |  | 2006-08-06 | 2008-06-02 | 17% | 13% | -4%
Engineering
Activity |  | Products Delivered in the Period | [5 empty] | Cond
Elaboration and Delivery of Engineering Supplies |  | Waiting on new Engineering supplies
Management
Material or Equipment |  | tasks realized during this period | [5 empty] | Cond
Centrifugal Machines |  | Being organized in temporal warehouse in construction???Need to clarify this. | [5 empty] | Packed
Accessories A-3002/3 |  | Organizando en almacén temporal en obra | [5 empty] | Packed
Bar Ducts A-3001 |  | Organizando en almacén temporal en obra | [5 empty] | Packed
Construction
Activity |  | Realized Tasks | [5 empty] | % Progress
Foundation A-3001 |  | Preparing, transporting & installing steel framework and electric piping | [5 empty] | 30%
Foundation TQ 2201 (Diesel) |  | Steel framework ready, cleaning, placing steel and plank lining. | [5 empty] | 43%
Foundation TQ 2202 (Diesel) |  | Casting, framework removal, filling | [5 empty] | 90%
Foundation TQ 2203 (Diesel) |  | Poor casting, without activity | [5 empty] | 40%
Foundation TQ 2101 (Diesel) |  | Reinforcing Steel framework | [5 empty] | 43%
Foundation TQ 2102 (Diesel) |  | Cast installment, concrete filling, framework removal | [5 empty] | 72%
Foundation TQ 2103 (Diesel) |  | Building steel for reinforcement | [5 empty] | 33%
Foundation TQ 5401A (C/I) |  | Excavating | [5 empty] | 5%
Perimeter Fencing |  | Excavating quadrates for bolters and girders, making steel frames, filling bolters with concrete, setting up framework for pedestals and pouring of concrete in pedestals. | [5 empty] | 17%
Active Sub-Contractors
Identification |  | Activities or Assigned Tasks | [5 empty] | Date Started
Eripe-Lamilara Consortium |  | Construction of Foundations of Generating Islands and Foundations of the TQs | [5 empty] | 2006-12-01
Docca |  | Construction of Perimeter Fencing | [5 empty] | 2007-04-01
Orbis-Gerempro |  | Concluded tasks, removal of temporal offices and installations | [5 empty] | 2006-06-01
ISIVEN |  | Installation of offices and other temporal installations. | [5 empty] | 2007-06-01
Points of Attention
Identification |  | Description | [5 empty] | Cond
Engineering |  | Continue efforts to expedite delivery of products | [5 empty] | In Progress
Judibana's draining duct |  | To obtain financing and operational authorization for surveys and provisional jobs. | [5 empty] | Pending
Topographical surveys |  | Authorization to intervene on peripheral properties. | [5 empty] | Pending
Hydrologic Study |  | Approval, Financial Assignment and Designation of Executor | [5 empty] | Pending