1 – PROPOSAL FORM AND SUMMARY

- Pricing & Manpower (Firm Lump Sum – US Dollars)

1.1 	Base Scope:

| Inventory, removal from location as necessary and installation of the PWPS Equipment, except for the four items in 1.2.1.2 below. Per Unit | Removal Installation | $ 600,000.00 $ 554,141.00 |
| --- | --- | --- |
| The setting on the foundation, of the four major pieces of equipment: electric generator; two combustion turbine enclosures with gas generators and power turbines installed; and the control house. | Lump Sum | $ 39,295.00 |
| Installation of all interconnecting piping, instrumentation, supports and auxiliaries for all PWPS Equipment, including rigid piping, flexible tubing, hoses, specialty fittings, valves and specialty devices on the foundation | Lump Sum | $ 38,495.00 |
| Installation of the segregated phase bus duct, supports, and electrical cable tray, fittings, and supports for the PWPS Equipment | Lump Sum | $ 37,898.00 |
| Installation of the interconnecting cabling wires, and control cables for the PWPS Equipment. | Lump Sum | $ 37,898.00 |
| TOTAL PRICE OF WORK per Twin Pac |  | $1,307,727.00 |

    - Receiving, inventory, storage as necessary, removal from storage as necessary and installation of the PWPS Equipment (as defined in Exhibit A of the Contract for Equipment Installation Services), except for the four items in 4.2.3 below.

| 1.2.2.1 Total Days | # 20 Days |
| --- | --- |
| 1.2.2.2 Total Field Man Days | 80 MD |
| 1.2.2.3 Total Field Man Hours | 800 MH |

1.2.3	The loading and setting on the foundation, of the four major pieces of equipment that are currently located in the Project: electric generator; two combustion turbine enclosures with gas generators and power turbines installed; and the control house.

| 1.2.3.1 Total Days | # 5 Days |
| --- | --- |
| 1.2.3.2 Total Field Man Days | 30 MD |
| 1.2.3.3 Total Field Man Hours | 300 MH |

1.2.4	Installation of all interconnecting piping, instrumentation, supports and auxiliaries for all PWPS Equipment, including rigid piping, flexible tubing, hoses, specialty fittings, valves and specialty devices provided by PWPS.

| 1.2.4.1 Total Days | # 10 Days |
| --- | --- |
| 1.2.4.2 Total Field Man Days | 40 MD |
| 1.2.4.3 Total Field Man Hours | 400 MH |

1.2.5	Installation of the segregated phase bus duct, supports, and electrical cable tray, fittings, and supports for the PWPS Equipment

| 1.2.5.1 Total Days | # 5 Days |
| --- | --- |
| 1.2.5.2 Total Field Man Days | 15 MD |
| 1.2.5.3 Total Field Man Hours | 150 MH |

1.2.6	Installation of the interconnecting cabling wires, and control cables for the PWPS Equipment.

| 1.2.6.1 Total Days | # 12 Days |
| --- | --- |
| 1.2.6.2 Total Field Man Days | 36 MD |
| 1.2.6.3 Total Field Man Hours | 360 MH |

1.2.7	Installation of the interconnecting cabling wires, and control cables for the PWPS Equipment.

| 1.2.7.1 Total Days | # Days |
| --- | --- |
| 1.2.7.2 Total Field Man Days ***** SEE 1.2.6 ***** | MD |
| 1.2.7.3 Total Field Man Hours | MH |

**Note: All expansion bolts are assumed 7" long.

#### EXTRA EXPENSES

| COST OF PAYMENT BOND & PERFORMANCE BOND: |  |  | $30,000 |
| --- | --- | --- | --- |

| Supervision & Advise during the foundation pouring (Weekly charge plus expenses 10 Hrs/Day) |  |  | $ 9,000.00 |
| --- | --- | --- | --- |