|  |  |  |  |  |  | Morichal Generation Project |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Task Name Duration |  |  | Start |  | Finish Predecessors |  | 2011 |  |
|  |  |  |  |  |  | 3rd Quarter |  | 4th Quarter 1st Quarter | 2nd Quarter |
|  |  |  |  |  |  | Jul Aug Sep |  | Oct Nov Dec Jan Feb | Mar Apr |
| 1 | Morichal 167 days |  |  | Mon 8/2/10 |  | Tue 3/22/11 |  |  |  |
| 2 | Engineering 75 days |  |  | Mon 8/2/10 |  | Fri 11/12/10 |  |  |  |
| 3 | One-Line diagrams 5 days |  |  | Mon 8/2/10 |  | Fri 8/6/10 |  |  |  |
| 4 | Three-Line diagrams 10 days |  |  | Mon 8/9/10 |  | Fri 8/20/10 3 |  |  |  |
|  | Relay package schematics 10 days |  |  | Mon 8/23/10 |  | Fri 9/3/10 4 |  |  |  |
| 6 | Relay panel Layouts and wiring diagrams 15 days |  |  | Mon 9/6/10 |  | Fri 9/24/10 5 |  |  |  |
| 7 | Building Specs 2 days |  |  | Mon 9/27/10 |  | Tue 9/28/10 6 |  |  |  |
| 8 | Interconnect Wiring 15 days |  |  | Mon 9/27/10 |  | Fri 10/15/10 6 |  |  |  |
| 9 | Relay Settings 10 days |  |  | Mon 10/18/10 |  | Fri 10/29/10 8 |  |  |  |
|  | Relay Programs 10 days |  |  | Mon 11/1/10 |  | Fri 11/12/10 9 |  |  |  |
| 11 | Control House 70 days |  |  | Wed 9/29/10 |  | Tue 1/4/11 |  |  |  |
| 12 | Building fabrication 60 days |  |  | Wed 9/29/10 |  | Tue 12/21/10 7 |  |  |  |
| 13 | Shipping 10 days |  |  | Wed 12/22/10 |  | Tue 1/4/11 12 |  |  |  |
| 14 | Panel Fabrication 70 days |  |  | Mon 9/27/10 |  | Fri 12/31/10 |  |  |  |
|  | Panel fabrication 60 days |  |  | Mon 9/27/10 |  | Fri 12/17/10 6 |  |  |  |
| 16 | Shipping 10 days |  |  | Mon 12/20/10 |  | Fri 12/31/10 15 |  |  |  |
| 17 | Construction 28 days |  |  | Wed 1/5/11 |  | Fri 2/11/11 |  |  |  |
| 18 | Set Control house 1 day |  |  | Wed 1/5/11 |  | Wed 1/5/11 11 |  |  |  |
| 19 | Yard Civil work 5 days |  |  | Thu 1/6/11 |  | Wed 1/12/11 18 |  |  |  |
|  | Install Panels 2 days |  |  | Thu 1/6/11 |  | Fri 1/7/11 14,18 |  |  |  |
| 21 | Install Control Cables 5 days |  |  | Mon 1/10/11 |  | Fri 1/14/11 20 |  |  |  |
| 22 | Panel Wiring G1 20 days |  |  | Mon 1/17/11 |  | Fri 2/11/11 21 |  |  |  |
| 23 | Panel Wiring G2 20 days |  |  | Mon 1/17/11 |  | Fri 2/11/11 21 |  |  |  |
| 24 | TX-3 Wiring 2 days |  |  | Mon 1/17/11 |  | Tue 1/18/11 21 |  |  |  |
|  | TX-4 Wiring 2 days |  |  | Mon 1/17/11 |  | Tue 1/18/11 21 |  |  |  |
| 26 | CB H720 Wiring 2 days |  |  | Mon 1/17/11 |  | Tue 1/18/11 21 |  |  |  |
| 27 | CB H1020 Wiring 2 days |  |  | Mon 1/17/11 |  | Tue 1/18/11 21 |  |  |  |
| 28 29 31 32 33 34 36 | Commissioning/Testing 27 days Red Line Drawings G1 10 days Load Relay Programs G1 2 days Test Relays G1 10 days Functional test G1 15 days Red Line Drawings G1 10 days Load Relay Programs G1 2 days Test Relays G1 10 days Functional test G1 15 days |  |  | Mon 2/14/11 Mon 2/14/11 Mon 2/14/11 Wed 2/16/11 Wed 3/2/11 Mon 2/14/11 Mon 2/14/11 Wed 2/16/11 Wed 3/2/11 |  | Tue 3/22/11 Fri 2/25/11 17 Tue 2/15/11 17 Tue 3/1/11 30 Tue 3/22/11 31 Fri 2/25/11 17 Tue 2/15/11 17 Tue 3/1/11 30 Tue 3/22/11 31 |  |  |  |
| Project: schedule Date: Fri 7/16/10 |  | Task Split Progress |  |  | Milestone Summary Project Summary External Tasks External Milestone Deadline |  |  |  |  |
|  |  |  |  |  |  | Page 1 |  |  | Prepared by CEG |