## Storage
6C427 OUESTELEC - CENTRAX PACKING LIST AND STORAGE LOCATIONS | [24 empty] | = where 4 are not supplied
STORAGE NOTES
Centrax Section Code | ID | DESCRIPTION | Standard Packaging | Item Weight (Gross) kgs | Item Weight (Net) kgs | Dimensions (cms) |  |  | QTY | Total Vol. (m3) | Storage Footprint 4 Sets excluding access (m2) | Storage footprint per set (m2) | Formula showing whether or not sections have entered storage 1=Yes 0=No |  |  |  | Formula showing total storage footprint taken up so far (m2) | Formula showing storage footprint for 7001 | Formula showing storage footprint for 7002 | Formula showing storage footprint for 7003 | Formula showing storage footprint for 7004 | Estimated Total Footprint 4 Sets including access for inspection & maintenance (m2) | Point of Collection at availability date | Storage Location / Availability Date / Status |  |  |  | Special Handling Requirements
[6 empty] | Length | Width | Height | [15 empty] | PGS7001 | PGS7002 | PGS7003 | PGS7004
T001 - GT Baseplate Assembly
| 1 | PTS7001-4 (GT Packages 1-4 without roof modules) | SHRINKWRAPPED |  | 70895 | 1500 | 470 | 420 | 4 | 296.1 | 282 | 70.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 479.55 |  | Scales | Scales | Scales | Scales | Lifting bollards supplied but to be removed for shipping then re-attached during storage. Spreader beam required for lift. Check hook height.
| 2 | MECHANICAL HANDLING SKID | SHRINKWRAPPED SKID | 2182 | 2182 | 378 | 79 | 121 | 2 | 3.613 | 5.9724 | 2.9862 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11.0424 |  | Scales | X | Scales | X | None
| 3 | GT PACKAGE EXHAUST SECTION | CRATE | 2370 | 1031 | 410 | 310 | 211 | 4 | 26.818 | 50.84 | 12.71 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 66.24 | Centrax | Scales | Scales | Scales | 2009-07-31 | None
| 4 | GT BERTHING TOOL | CRATE |  | 580 | 206 | 86 | 76 | 1 | 1.346 | 1.7716 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | 3.4816 |  | Scales | X | X | X | None
| 5 | GT PACKAGE LOOSE PIPES | CRATE |  | 90 | 311 | 36 | 51 | 4 | 0.571 | 4.4784 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | 12.4184 |  | Scales | Scales | Scales | Scales | None
| 6 | SHIPLOOSE KITS | CRATE |  | 272 | 126 | 106 | 116 | 4 | 1.549 | 5.3424 | [10 empty] | 10.9824 |  | Scales | Scales | Scales | Scales
| 7 | INNER BLANKETS | CRATE |  | 98 | 106 | 71 | 79 | 4 | 0.595 | 3.0104 | [10 empty] | 7.5504 |  | Scales | Scales | Scales | Scales
T003 - GT Enclosure
| 1 | ROOF GUIDES | CASE | 1780 | 1500 | 700 | 120 | 100 | 4 | 8.4 | 33.6 | 8.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 51 | AAF-UK | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | None
|  | RUNWAY BEAMS | [19 empty] | 0
|  | MACHINERY DOOR CARRIAGE | [19 empty] | 0
|  | CYLINDER MOUNTING BRACKETS | [19 empty] | 0
| 2 | PACKAGE HARDWARE - SITE BUILD | CASE | 380 | 260 | 209 | 100 | 100 | 4 | 2.09 | 8.36 | 2.09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15.54 | AAF-UK | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | None
| 3 | CHAIN HOIST | CASE | 95 | 65 | 88 | 67 | 69 | 4 | 0.407 | 2.3584 | 0.5896 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6.4584 | AAF-UK | Scales | Scales | Scales | 2010-04-16 | None
| 4 | GEN VENT ACOUSTIC WEATHERSEAL | SHRINKWRAPPED PALLET | 480 | 383 | 421 | 180 | 150 | 4 | 11.367 | 30.312 | 7.578 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 43.332 | AAF-UK | Scales | Scales | Scales | 2010-04-16 | None
|  | INTAKE FLEXIBLE CONNECTION | [19 empty] | 0
|  | BLEED FLEXIBLE CONNECTION | [19 empty] | 0
| 5 | GT ENCLOSURE ROOF MODULES | SHRINKWRAPPED PIECE | 13210 | 13077 | 1483 | 476 | 124 | 4 | 87.533 | 282.3632 | 70.5908 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 322.5432 | AAF-UK | Scales | Scales | Scales | 2010-04-16 | Lift Beam Required & supplied below. Check hook height.
| 6 | SPREADER BEAM FOR GT ENCLOSURE ROOF | CASE | 375 | 375 | 474 | 29 | 54 | 2 | 0.742 | 2.7492 | 1.3746 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8.2792 | AAF-UK | Scales | 2010-04-16 | X | X | Required for GT roof module
| 7 | WIRE ROPE SLINGS & SHACKLES FOR ABOVE SPREADER BEAM | CASE | 463 | 341 | 190 | 190 | 55 | 2 | 1.986 | 7.22 | 3.61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11.52 | AAF-UK | Scales | 2010-04-16 | X | X | Required for GT roof module
T005 - GT Compressor Wash
| 1 | WATER WASH CART | WRAPPED |  | 102 | 140 | 50 | 120 | 1 | 0.84 | 0.7 | 0.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.9 | Centrax | 2010-04-23 | X | X | X | None
T006 - GT Lube Oil System
| 1 | LUBE OIL DEMISTER (Dollinger) | SHRINKWRAPPED SKID | 420 | 340 | 140 | 125 | 185 | 4 | 3.238 | 7 | 1.75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13.3 | Centrax | Scales | Scales | Scales | Scales | None
T007 - Gas Turbine and Coupling
| 1 | TRENT 60 DF WLE GAS TURBINES 1-4 | TBC - STAND/POD |  | 16500 | 570 | 267 | 287 | 4 | 43.679 | 60.876 | 15.219 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 156.456 |  | Centrax | Centrax | Centrax | Centrax | Spreader beam supplied from Rolls-Royce Check hook height - standard beam requires 6.8m min. hook height
| 2 | COUPLING (GT TO GENERATOR) | CASE |  | 2400 | 314 | 65 | 75 | 4 | 1.531 | 8.164 | 2.041 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16.744 |  | Scales | Scales | Scales | Scales | None
| 3 | GT INSTALLATION KIT (ENGINE SHIPLOOSE) | CASE |  | 230 | 206 | 101 | 67 | 4 | 1.394 | 8.3224 | 2.0806 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15.4624 |  | Scales | Scales | Scales | Scales | None
T009 - GT CO Turndown
| 1 | GT CO TURNDOWN KIT FOR ROOF MODULE | CRATE |  | 587 | 326 | 108 | 51 | 4 | 1.796 | 14.0832 | 3.5208 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 23.7632 |  | Scales | Scales | Scales | Scales | None
| 2 | COTD PIPES | CRATE |  | 315 | 176 | 136 | 66 | 4 | 1.58 | 9.5744 | 2.3936 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | 16.8144 |  | Scales | Scales | Scales | Scales | None
T011 - GT Water Injection (Including Water Skid)
| 1 | WATER INJECTION SKID | SHRINKWRAPPED SKID |  | 2490 | 280 | 180 | 180 | 4 | 9.072 | 20.16 | 5.04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 30.36 | Centrax | 6/31/2010 | 6/31/2010 | 2010-08-31 | 2010-08-31 | TBC
T012 - GT Fire and Gas System
| 1 | GT OFF-SKID FIRE SYSTEM (CO2 BOTTLE RACK, ETC) | SHRINKWRAPPED SKID |  | 1000 | 170 | 174 | 233 | 4 | 6.892 | 11.832 | 2.958 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19.712 | Centrax | 6/31/2010 | 6/31/2010 | 2010-08-31 | 2010-08-31 | TBC
T014 - GT Fuel System Liquid Only
| 1 | LIQUID FUEL/WATER FLUSH SKID | SHRINKWRAPPED SKID |  | 2495 | 240 | 125 | 221 | 4 | 6.63 | 12 | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20.3 | Centrax | 6/31/2010 | 6/31/2010 | 2010-08-31 | 2010-08-31 | TBC
T022 - GT HMI
| 1 | GT HMI (Human Machine Interface PC) | BOXED |  | 10 | 100 | 25 | 100 | 4 | 0.25 | 1 | 0.25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4.5 |  | Scales | Scales | Scales | Scales | None
T030 - AC Generator Package
| 1 | PAS7001-7004 (Alternator Packages 1-4) | WRAPPED |  | 106000 | 800 | 450 | 422 | 4 | 151.92 | 144 | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 273.15 |  | Scales | Scales | Scales | Scales | Lifting bollards supplied but to be removed for shipping then re-attached during storage. Spreader beam required for lift. Check hook height.
T034 - AC Generator Line and Neutral Cubicles
| 1 | LINE CUBICLES | CASE | 3150 | 2750 | 282 | 204 | 256 | 4 | 14.727 | 23.0112 | 5.7528 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 33.7312 |  | Scales | Scales | Scales | Scales | None
| 2 | NEUTRAL CUBICLES | CASE | 1640 | 1340 | 239 | 110 | 259 | 4 | 6.809 | 10.516 | 2.629 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 18.496 |  | Scales | Scales | Scales | Scales | None
T036 - AC Generator Control & Protection Panel
| 1 | GCP PANELS | SHRINKWRAPPED SKID |  | 500 | 100 | 180 | 220 | 4 | 3.96 | 7.2 | 1.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13.8 | Centrax | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | None
T037 - AC Generator Cooling / Vent System
| 1 | GEN VENT MDM SILENCER | SHRINKWRAPPED SKID | 7964.9 | 6926 | 462 | 265 | 325 | 4 | 39.79 | 48.972 | 12.243 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 64.512 | AAF-UK | Scales | Scales | 2010-04-16 | 2010-07-09 | None
| 2 | GEN VENT UNLINED TRANSITION | SHRINKWRAPPED SKID | 2105 | 2070 | 453 | 271 | 277 | 4 | 34.005 | 49.1052 | 12.2763 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 64.5852 | AAF-UK | Scales | Scales | 2010-04-16 | 2010-07-09 | None
| 3 | LOWER GEN VENT FILTER HOUSE | SHRINKWRAPPED SKID | 3025 | 2750 | 500 | 370 | 237 | 4 | 43.845 | 74 | 18.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 92.4 | AAF-UK | Scales | Scales | 2010-04-16 | 2010-07-09 | None
| 4 | UPPER GEN VENT FILTER HOUSE | SHRINKWRAPPED SKID | 1100 | 1000 | 260 | 115 | 251 | 4 | 7.505 | 11.96 | 2.99 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20.46 | AAF-UK | Scales | Scales | 2010-04-16 | 2010-07-09 | None
| 5 | GEN VENT UNLINED TRANSITION (SPLIT) | SHRINKWRAPPED SKID | 700 | 670 | 518 | 280 | 75 | 4 | 10.878 | 58.016 | 14.504 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 74.976 | AAF-UK | Scales | Scales | 2010-04-16 | 2010-07-09 | None
T109 - Site Acoustics – Air Intake Ducting, Filtration and Venting
| 1 | LOWER VENT OUTLET MIXING BOX | SHRINKWRAPPED PALLET | 690 | 600 | 321 | 151 | 215 | 4 | 10.421 | 19.3884 | 4.8471 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 29.8284 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 2 | UPPER VENT OUTLET MIXING BOX | SHRINKWRAPPED PALLET | 690 | 600 | 321 | 151 | 215 | 4 | 10.421 | 19.3884 | 4.8471 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 29.8284 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 3 | VENT OUTLET SILENCER | SHRINKWRAPPED PALLET | 3160 | 2960 | 357 | 148 | 377 | 4 | 19.919 | 21.1344 | 5.2836 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 32.2344 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 4 | VENT OUTLET COWL | SHRINKWRAPPED PALLET | 1245 | 1083 | 470 | 140 | 180 | 4 | 11.844 | 26.32 | 6.58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 39.52 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 5 | VENT OUTLET FAN | CASE/SHRINKWRAP | 1750 | 1850 | 232 | 126 | 245 | 4 | 7.162 | 11.6928 | 2.9232 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19.8528 | AAF-UK | 2010-04-16 | 2010-04-16 | 2010-04-30 | 2010-07-23 | None
| 6 | VENT OUTLET FAN | CASE/SHRINKWRAP | 1750 | 1850 | 232 | 126 | 245 | 4 | 7.162 | 11.6928 | 2.9232 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19.8528 | AAF-UK | 2010-04-16 | 2010-04-16 | 2010-04-30 | 2010-07-23 | None
| 7 | VENT OUTLET FAN | CASE/SHRINKWRAP | 1750 | 1850 | 232 | 126 | 245 | 4 | 7.162 | 11.6928 | 2.9232 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19.8528 | AAF-UK | 2010-04-16 | 2010-04-16 | 2010-04-30 | 2010-07-23 | None
| 8 | BLEED INTAKE QUICK RELEASE DUCT | SHRINKWRAPPED PALLET | 160 | 120 | 273 | 90 | 20 | 4 | 0.491 | 9.828 | 2.457 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 18.088 | AAF-UK | Scales | Scales | 2010-04-23 | 2010-07-23 | None
| 9 | BLEED SYSTEM DUMMY DUCT | SHRINKWRAPPED PALLET | 1193 | 1037 | 271 | 63 | 25 | 4 | 0.427 | 6.8292 | 1.7073 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14.5092 | AAF-UK | Scales | Scales | 2010-04-23 | 2010-07-23 | None
| 10 | BLEED SYSTEM PLENUM | SHRINKWRAPPED PALLET | 2001 | 1740 | 337 | 156 | 226 | 4 | 11.881 | 21.0288 | 5.2572 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 31.8888 | AAF-UK | Scales | Scales | 2010-04-23 | 2010-07-23 | None
| 11 | BLEED OUTLET SILENCER | SHRINKWRAPPED PALLET | 3750 | 3600 | 340 | 155 | 326 | 4 | 17.18 | 21.08 | 5.27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 31.98 | AAF-UK | Scales | Scales | 2010-04-23 | 2010-07-23 | None
| 12 | BLEED OUTLET COWL | SHRINKWRAPPED PALLET | 1140 | 1010 | 468 | 142 | 177 | 4 | 11.763 | 26.5824 | 6.6456 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 39.7824 | AAF-UK | Scales | Scales | 2010-04-23 | 2010-07-23 | None
| 13 | VENT INLET SILENCER | SHRINKWRAPPED SKID | 2260 | 2170 | 329 | 147 | 294 | 4 | 14.219 | 19.3452 | 4.8363 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 29.8652 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 14 | VENT INLET TRANSITION DUCT | SHRINKWRAPPED SKID | 530 | 456 | 315 | 125 | 115 | 4 | 4.528 | 15.75 | 3.9375 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 25.55 | AAF-UK | Scales | Scales | 2010-04-30 | 2010-07-23 | None
| 15 | UPPER LINED WEATHERHOOD ASSEMBLY | SHRINKWRAPPED SKID | 1255 | 1245 | 626 | 201 | 160 | 4 | 20.132 | 50.3304 | 12.5826 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 67.8704 | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 16 | UPPER LINED WEATHERHOOD ASSEMBLY | SHRINKWRAPPED SKID | 1255 | 1245 | 626 | 201 | 160 | 4 | 20.132 | 50.3304 | 12.5826 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 67.8704 | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 17 | LOWER LINED WEATHERHOOD ASSEMBLY | SHRINKWRAPPED SKID | 1255 | 1245 | 626 | 201 | 160 | 4 | 20.132 | 50.3304 | 12.5826 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 67.8704 | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 18 | LOWER LINED WEATHERHOOD ASSEMBLY | SHRINKWRAPPED SKID | 1255 | 1245 | 626 | 201 | 160 | 4 | 20.132 | 50.3304 | 12.5826 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 67.8704 | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 19 | UPPER LOUVRE BOX ASSEMBLY - 2 OFF | SHRINKWRAPPED PALLET | 1400 | 1480 | 339 | 166 | 145 | 4 | 8.16 | 22.5096 | 5.6274 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 33.6096 | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 20 | UPPER LOUVRE BOX ASSEMBLY - 2 OFF | SHRINKWRAPPED PALLET | 1400 | 1480 | 339 | 166 | 145 | 4 | 8.16 | 22.5096 | 5.6274 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 21 | LOWER LOUVRE BOX ASSEMBLY - 2 OFF | SHRINKWRAPPED PALLET | 1400 | 1480 | 339 | 166 | 145 | 4 | 8.16 | 22.5096 | 5.6274 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 22 | LOWER LOUVRE BOX ASSEMBLY - 2 OFF | SHRINKWRAPPED PALLET | 1400 | 1480 | 339 | 166 | 145 | 4 | 8.16 | 22.5096 | 5.6274 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | Scales | Scales | 2010-05-07 | 2010-07-09 | None
| 23 | UPPER SERVICE PLENUM | SHRINKWRAPPED SKID | 3030 | 3050 | 664 | 174 | 371 | 4 | 42.864 | 46.2144 | 11.5536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 63.9744 | AAF-UK | Scales | Scales | 2010-05-14 | 2010-07-09 | None
| 24 | LOWER SERVICE PLENUM | SHRINKWRAPPED SKID | 2980 | 2960 | 677 | 174 | 359 | 4 | 42.289 | 47.1192 | 11.7798 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 65.1392 | AAF-UK | Scales | Scales | 2010-05-14 | 2010-07-09 | None
| 25 | UPPER STACKED ASC ASSEMBLY 5X25 | SHRINKWRAPPED SKID | 4170 | 4190 | 688 | 224 | 389 | 4 | 59.95 | 61.6448 | 15.4112 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 80.8848 | AAF-UK | Scales | Scales | Scales | 2010-08-06 | None
| 26 | LOWER STACKED ASC ASSEMBLY 5X25 | SHRINKWRAPPED SKID | 4050 | 4070 | 700 | 238 | 359 | 4 | 59.809 | 66.64 | 16.66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 86.4 | AAF-UK | Scales | Scales | Scales | 2010-08-06 | None
| 27 | UPPER INTAKE TRANSITION ASSEMBLY | SHRINKWRAPPED SKID | 3530 | 3620 | 617 | 450 | 362 | 4 | 100.509 | 111.06 | 27.765 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 133.4 | AAF-UK | Scales | Scales | 2010-05-14 | 2010-08-06 | None
| 28 | LOWER INTAKE TRANSITION ASSEMBLY | SHRINKWRAPPED SKID | 4910 | 5110 | 617 | 470 | 362 | 4 | 104.976 | 115.996 | 28.999 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 138.736 | AAF-UK | Scales | Scales | 2010-05-14 | 2010-08-06 | None
| 29 | INTAKE SILENCER c/w COTD | SHRINKWRAPPED SKID | 8980 | 8900 | 440 | 311 | 420 | 4 | 57.473 | 54.736 | 13.684 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 70.756 | AAF-UK | Scales | Scales | 2010-05-14 | 2010-08-06 | None
| 30 | ASC DUST CHUTE ASSEMBLY | SHRINKWRAPPED SKID | 1245 | 2060 | 660 | 179 | 290 | 4 | 34.261 | 47.256 | 11.814 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 65.036 | AAF-UK | Scales | Scales | Scales | 2010-07-09 | None
| 31 | COMBUSTION INTAKE QUICK RELEASE DUCT | SHRINKWRAPPED SKID | 310 | 250 | 410 | 200 | 35 | 4 | 2.87 | 32.8 | 8.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 46 | AAF-UK | Scales | Scales | Scales | 2010-04-30 | None
| 32 | SECONDARY AIR FAN C/W SILENCERS | CASE | 850 | 1100 | 190 | 165 | 235 | 4 | 7.367 | 12.54 | 3.135 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20.64 | AAF-UK | Scales | Scales | Scales | Scales | None
| 33 | SECONDARY AIR FAN SILENCER (UNPODDED) | CASE | 259 | 370 | 190 | 170 | 144 | 4 | 4.651 | 12.92 | 3.23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 21.12 | AAF-UK | Scales | Scales | Scales | Scales | None
| 35 | VENT FAN SUPPORT STEELWORK | TBA | TBA | TBA | TBA | TBA | TBA | 4 |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | 2010-05-31 | 2010-05-31 | 6/31/2010 | 6/31/2010 | None
| 36 | COMBUSTION INTAKE SUPPORT STEELWORK | TBA | TBA | TBA | TBA | TBA | TBA | 4 |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | 2010-05-31 | 2010-05-31 | 6/31/2010 | 6/31/2010 | None
| 37 | ACCESS, PLATFORMS, LADDERS & HANDRAILS | TBA | TBA | TBA | TBA | TBA | TBA | 4 |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | None
| 38 | GEN VENT SUPPORT STEELWORK | TBA | TBA | TBA | TBA | TBA | TBA | 4 |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | AAF-UK | 2010-05-31 | 2010-05-31 | 31/06/2010 | 31/06/2010 | None
| 39 | ASC PANEL PAKS (FILTERS) | PALLETS IN 40' CONTAINER |  | 7020 | 1205 | 235 | 239 | 4 | 67.679 | 113.27 | 28.3175 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 143.07 | AAF-UAE or AAF-NL | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | None
T110 - Site Acoustics - Additional Items
| 1 | GT & GENERATOR BASEPLATE ACOUSTIC SKIRTS | CASE | 907 | 648 | 80 | 56 | 5 | 400 | 0.022 | 3 | 0.75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 551.2 | AAF-UK | 2010-04-30 | 2010-05-07 | 2010-05-31 | 2010-06-04 | None
| 2 | ACOUSTIC SKID SKIRT COVER PLATES & MOUNTING ANGLES (4units/box) | CASE | 907 | 648 | 100 | 100 | 100 | 1 | 1 | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.25 | AAF-UK | 2010-04-30 | 2010-05-07 | 2010-05-31 | 2010-06-04 | None
| 3 | ACOUSTIC SKID SKIRT BRACING ANGLES & CLADDING (2units/box) | CASE | 510 | 364 | 260 | 100 | 100 | 2 | 2.6 | 5.2 | 2.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9.3 | AAF-UK | 2010-04-30 | 2010-05-07 | 2010-05-31 | 2010-06-04 | None
[14 empty] | Total Footprint required per set (including engines) |  |  |  | Total Storage Footprint used per set (excluding engines)
[14 empty] | Total Footprint required per set (excluding engines) |  |  |  | #REF! | #REF! | #REF! | #REF!
ANNEX 2- KEY TO POINT OF COLLECTION
Centrax = Centrax Ltd, Newton Abbot, Devon, TQ12 4SQ, England
Brush = Brush Electrical Machines, Loughborough, LE11 1HJ, England
AAF-UK = AAF Ltd, Cramlington, Northumberland, NE23 8AF, England
AAF - UAE = AAF Facility, Abu Dhabi, UAE
AAF-NL = AAF Facility, Emmen, Netherlands
AAF-DERBY = Intermediate storage depot used by AAF near Derby in the UK
SCALES = Scales SA, 92 Avenue du Chateau, St Ouen l'Aumone, 95056 CERGY-PONTOISE, FRANCE