## Cost Sheet
Aberdeen, UK | GE 9E Relocation X 2 |  |  | GE 9E
Mobilization / Demobilization
Travel In / Out | Number | Cost per |  | Total Cost
Craftsmen | 37
Mobilization | 37 | 3500 |  | 129500
Time | 0 | 60.3405 |  | 0 |  | Mob/Demob Cost
Per Diem | 0 | 256 |  | 0 |  | 335593.3517
Local Transport | 1 | 25000 |  | 25000
Job Set Up | 0 | 0 |  | 0
154500
Foreman | 8
Mobilization | 8 | 10000 |  | 80000
Time | 256 | 69.4359 |  | 17775.5917
Per Diem | 16 | 256 |  | 4096
Local Transport | 8 | 1000 |  | 8000
Job Set Up | 0 | 0 |  | 0
109871.5917
TA's/Supervision/Gen. Spe | 4
Air fare | 4 | 10000 |  | 40000
Time | 128 | 85.9975 |  | 11007.68
Per Diem | 4 | 256 |  | 1024
Local Transport | 8 | 500 |  | 4000
Report | 0 | 85.9975 |  | 0
56031.68
Project Manager | 1
Air fare | 1 | 10000 |  | 10000
Time | 32 | 83.69 |  | 2678.08
Per Diem | 2 | 256 |  | 512
Local Transport | 4 | 500 |  | 2000
15190.08
Inspection | [5 empty] | Direct Labor |  | Outage Duration Direct Labor | Outage Duration Indirect Labor
| Number | ST. | O.T | Days | Per Diem | Straight time Days | Hours Per Day | Number of Work Days For Per Diem | Number of Work Days Per Diem
Craftsmen | 37 | 11840 | 9472 | 60 | 568320 | 40 | 8 | 60 | 60
Straight time Days with OT
Foreman | 8 | 2560 | 2048 | 60 | 122880 | 64 | 4
Overtime Days
TA's/Supervision | 4 | 1280 | 1024 | 60 | 61440 | 0 | 12
Project Manager | 1 | 320 | 256 | 60 | 15360
Indirect Labor
Generator Specialist | 0 | 0 | 0 |  |  | Straight time Days | Hours Per Day
[6 empty] | 40 | 8
Rates: | Cost ST | Cost OT | Price ST | Price OT |  | Straight time Days with OT
Craftsmen | 41.845 | 56.7675 | 60.3405 | 76.6361 |  | 64 | 4
Foreman | 48.1525 | 66.2287 | 69.4359 | 89.4088 |  | Overtime Days
T/A's/Supervision | 85.9975 | 85 | 165 | 165 |  | 0 | 12
Project Manager | 96.31 | 110 | 185 | 185
Project Cost Summary
| ST.Hours | ST Price | OT Hours | OT Price | Per Diem | Travel in / Out
Craftsmen | 11840 | 495444.8 | 9472 | 537701.76 | 568320 | 154500
Foreman | 2560 | 123270.4 | 2048 | 135636.48 | 122880 | 109871.5917
TA's/Supervision | 1280 | 110076.8 | 1024 | 87040 | 61440 | 56031.68
Project Manager | 320 | 30819.2 | 256 | 28160 | 15360 | 15190.08
Totals | 16000 | 759611.2 | 12800 | 788538.24 | 768000 | 335593.3517
Markup | 1.45
Project Price Summary
| ST.Hours | ST Price | OT Hours | OT Price | Per Diem | Travel in / Out
Craftsmen | 11840 | 714431.4016 | 9472 | 725897.376 | 824064 | 177675
Foreman | 2560 | 177755.9168 | 2048 | 183109.248 | 178176 | 126352.3304
TA's/Supervision | 1280 | 211200 | 1024 | 168960 | 89088 | 64436.432
Project Manager | 320 | 59200 | 256 | 47360 | 22272 | 17468.592
Totals | 16000 | 1162587.3184 | 12800 | 1125326.624 | 883200 | 385932.3544
| Cost | Price
Total Direct Hours | 25920
Total Indirect Hours | 2880
Total Direcr Labor | 1292053.44 | 1801193.9424
Total Indirect Labor | 197116.8 | 380160
Sub Total on Labor | 1489170.24 | 2181353.9424
Per Diem | 768000 | 883200
Travel in/out | 335593.3517 | 385932.3544
Subtotal | 1103593.3517 | 1269132.3544
Subtotal | 2592763.5917 | 3450486.2968
Other Cost
1. Tools/Truck | 35000 | 50750
2. Consumables | 95000 | 137750
3. Hytorque |  | 0
4. Rental Equipment and Fuel | 65000 | 94250
5 Three Rivers Training |  | 0
6 Drug Screening |  | 0
Subtotal | 195000 | 282750
Grand Total | 2787763.5917 | 3733236.2968
Warranty cost (3%) | 83632.9078 | 83632.9078
Total with Warranty | 2787763.5917 | 3816869.2046
Sub Contracts
1 Heavy Lift Crane | 1250000 | 1812500
2 NDE Estimate |  | 0
3.E&C Tech | 0 | 0
4. Insulators |  | 0
5. Scaffolding |  | 0
6 Vibration Analysis |  | 0
7 Office/Change Trailer | 10000 | 14500
Total Cost on Sub Contracts | 1260000 | 1827000
Commission
5% of Total Profit | 79805.2806
Total Commission | 79805.2806

## Summary Sales Sheet
Pricing Sheet
| Cost Numbers | Price Number | Margins $ | Margin %
Direct Labor Cost | 1292053.44 | 1801193.9424 | 509140.5024 | 28.27%
Per Diem/Mob | 1103593.3517 | 1269132.3544 | 165539.0028 | 13.04%
Indirect Labor Sales Price | 197116.8 | 380160 | 183043.2 | 48.15%
Other Cost | 195000 | 282750 | 87750 | 31.03%
Warranty cost | 0 | 83632.9078 | 83632.9078 | 100%
Sub Contracts | 1260000 | 1827000 | 567000 | 31.03%
Commission | 79805.2806 | 79805.2806 | 0 | 0%
Bid Bond | 0 | 0 | 0 | #DIV/0!
Total | 4127568.8723 | 5723674.4852 | 1596105.6129 | 27.89%
Contingency |  | 500000 | 500000 | 100%
See Sheet
Grand Total | 4127568.8723 | 6223674.4852 | 2096105.6129 | 33.68%
Midstones
Intial Mobilization (Site Survey) | 200000
Project Mobilization | 3011837 | 50%
Crating Complete | 2710653 | 40%
Load Out Complete | 301184 | 10%

## Labor Rates
Project: | Aberdeen, UK | Project #: | GE 9E | 6 | 1 | 12
Proposal Basis (assumptions) |  |  |  | Days Per Week | Shifts | HRS/Shift
1PM
4 TA
8 WF
TRADE OR CLASSIFICATION | BASE RATE – STRAIGHT TIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE S/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 3.5% | 1.5% | 10% | 26.15% | 3% | 40% | 69.15%
Foreman | 35 | 2.6775 | 0.28 | 0.945 | 4 | 1.225 | 0.525 | 3.5 | 48.1525 | 1.4446 | 19.8388 | 69.4359
Millwright | 30 | 2.295 | 0.24 | 0.81 | 4 | 1.05 | 0.45 | 3 | 41.845 | 1.2554 | 17.2401 | 60.3405
TA's | 65 | 4.9725 | 0.52 | 1.755 | 4 | 2.275 | 0.975 | 6.5 | 85.9975 |  |  | 125
Project Manager | 85 | 6.5025 | 0.68 | 2.295 | 0 | 2.975 | 1.275 | 8.5 | 107.2275 |  |  | 150
TRADE OR CLASSIFICATION | BASE RATE – OVERTIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE O/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 3.5% | 1.5% | 10% | 26.15% | 0% | 35% | 61.15%
Foreman | 52.5 | 4.0163 | 0.42 | 1.4175 | 0 | 1.8375 | 0.7875 | 5.25 | 66.2287 | 0 | 23.1801 | 89.4088
Millwright | 45 | 3.4425 | 0.36 | 1.215 | 0 | 1.575 | 0.675 | 4.5 | 56.7675 | 0 | 19.8686 | 76.6361