## Scope of Efforts

We will provide our field expertise with tools and equipment to perform Marse’s upcoming FT-8 Mobilepac Installation Project.  We will provide an experienced crew consisting of Project Manager, Technical Advisors, Mechanical Technicians, Experienced Millwrights and I&C Technicians with equipment to perform the work scope(s) per your RFQ.  This effort will be provided as outlined in the attached schedule and pricing sections.  We have carefully reviewed your specifications, and have familiarized ourselves with your project details and requirements.

WE understands this project will be based on installing and commissioning (2) FT-8 Mobilepacs at the Petroceneno site and (2) FT-8 Mobilepacs at the Petromonogas site.

WE will provide this work on a Firm Price basis in accordance with the clarifications listed below, the existing Terms and Conditions as agreed to by us & Marse C.A. will apply, and our Schedule of Extra Work Rates are accepted in this proposal document.

## Assumptions

- Any Purchase Order resulting from this offer must reference and incorporate this proposal as part of the contract.

- Marse C.A. will make available to us all special equipment required to work on the turbine/generators facilitating installation of the unit(s) as required. Items will be listed below. (This is a reference to Pratt specialty tooling for installation of the engine and generator)

- WE will hold daily progress meetings with the designated Marse representative.

- Marse will supply all BOP work/piping up to the respective skids on power island.

- Marse will supply temporary power when needed (1 phase 100 amp lighting and 3 phase 480 volt 100 amp to Control trailer)

- Marse will supply all material handling equipment and operators including: 100 ton crane for 1 day for each generator installation. 40 ton crane for 8 days for each unit, 2 forklifts for 16 days for each unit, 1 air ride truck for 2 days for each unit and 1 flat bed truck for 1 day for each unit on days specified by Project Manager

- Marse is responsible for acquisition and disposal of all consumables including hazardous waste and filling fire bottles for Fire Protection system on each unit.

- Marse will provide 2 climate controlled trailers (10’ X 40’) at each site with internet access and local phone access as well as sanitary facilities at each site adequate for a 12 man crew.

- WE will provide two (2) copies of the final installation report and commissioning manuals.  These will be supplied in electronic format on compact disks unless otherwise requested within 30 days.

- Trash will be emptied daily to a Marse supplied disposal containers.

- Any delays beyond our control that result in extra cost to WE will be billed to Marse based on T & M rates. (Exhibit 2)

## Schedule

This proposal is based on working one (1), ten (10) hour shift, six days a week for the duration of the work scope depending on final inspection outcome.  We expect to complete this effort in thirty four (34) days per unit. (Exhibit 3)

Marse can use either and/or any combination of the following pricing for work scope(s).

- Installation per unit (firm price)	$583,045.51

- With Out Performance Bond

- Installation per site (firm price, two concurrent units)	$980,000.00