## HOMEOFFICE START-UP
| Project Name | MARGARITA ISLAND | [6 empty] | HOME OFFICE BUDGET | [20 empty] | Per Diem |  | 120 | 3600
| Location | VENEZUELA | [25 empty] | HOME
| Description | Dual Fuel | [25 empty] | OFFICE |  | Monthly Family Visit |  |  | 1200
| Job No. | xxxxx | [25 empty] | EXPENSES |  | Computer |  |  | 200
| Prepared by | TG | Date | 2010-05-04
| Reviewed by | TE | Date | [26 empty] | TOTAL H/O EXPENSES |  |  | 5000
| Approved by | 0 | Date
| Period of Performance |  | Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | Total | Total
|  |  | Date | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30 | 2010-09-06 | 2010-09-13 | 2010-09-20 | 2010-09-27 | 2010-10-04 | 2010-10-11 | 2010-10-18 | 2010-10-25 | 2010-11-01 | 2010-11-08 | 2010-11-15 | 2010-11-22 | 2010-11-29 | 2010-12-06 | 2010-12-13 | 2010-12-20 | 2010-12-27 | 2011-01-03 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-01-31 | 2011-02-07 | Manhours | W2
HOME OFFICE TASK
1 | Senior S/U Mgr | W2 Rate | 70 | 20 | 20 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [18 empty] | 56 | 3920
2 | SDOI Supervision | W2 Rate | 0 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 0 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 0 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 0 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 0 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 20 | 20 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 3920
7 | Start-up Manager | W2 Rate | 0 | [28 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | 0 | [28 empty] | 0 | 0
9 | F.A.T. | W2 Rate | 0 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Period of Performance |  | Week No. | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | Total | Total
|  |  | DATE | 2011-02-14 | 2011-02-21 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-28 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-04-25 | 2011-05-02 | 2011-05-09 | 2011-05-16 | 2011-05-23 | 2011-05-30 | 2011-06-06 | 2011-06-13 | 2011-06-20 | 2011-06-27 | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | 70 | [28 empty] | 0 | 0
2 | SDOI Supervision | W2 Rate | 0 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 0 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 0 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 0 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 0 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up Manager | W2 Rate | 0 | [28 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | 0 | [28 empty] | 0 | 0
9 | F.A.T. | W2 Rate | 0 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Period of Performance |  | Week No. | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | Total | Total
|  |  | DATE | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | 70 | [28 empty] | 0 | 0
2 | SDOI Supervision | W2 Rate | [29 empty] | 0 | 0
3 | SDOIs | W2 Rate | [29 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | [29 empty] | 0 | 0
5 | IOI/AR | W2 Rate | [29 empty] | 0 | 0
6 | Admin Support | W2 Rate | [29 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up Manager | W2 Rate | [29 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | [29 empty] | 0 | 0
9 | F.A.T. | W2 Rate | [29 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Period of Performance |  | Week No. | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | Total | Total
|  |  | DATE | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | [29 empty] | 0 | 0
2 | SDOI Supervision | W2 Rate | [29 empty] | 0 | 0
3 | SDOIs | W2 Rate | [29 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | [29 empty] | 0 | 0
5 | IOI/AR | W2 Rate | [29 empty] | 0 | 0
6 | Admin Support | W2 Rate | [29 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up Manager | W2 Rate | [29 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | [29 empty] | 0 | 0
9 | F.A.T. | W2 Rate | [29 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HOME OFFICE PERSONNEL EXPENSES |  | Month | 2010-08-02 | 2010-09-02 | 2010-10-02 | 2010-11-02 | 2010-12-03 | 2011-01-02 | 2011-02-02 | 2011-03-04 | 2011-04-04 | 2011-05-05 | 2011-06-02 | 2011-07-03 | 2011-08-02 | 2011-09-02 | 2011-10-02 | 2011-11-02 | 2011-12-03 | 2012-01-02 | 2012-02-02 | 2012-03-04 | 2012-04-04 | 2012-05-05 | 2012-06-04 | 2012-07-05 | 2012-08-05 | 2012-09-05
|  |  | Manhours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenses
TOTAL HOME OFFICE BUDGET
|  | Home Office Wages Sub-Total |  |  | 3920 | [25 empty] | 0
|  | Field Office Wages Sub-Total |  |  | 0
|  | HomeOffice Overhead at0 |  |  | 0
|  | FHomeOffice Overhead at 0 |  |  | 0
|  | Home Office Wages Total |  |  | 3920 |  |  | TOTAL HOME OFFICE MANHOURS |  |  |  | 56
|  | Home Office Personnel Expenses |  |  | 0
|  |  | TOTAL BUDGET |  | 3920

## START-UP SUMMARY REPORT
ESTIMATE IS BASED ON 2010 DOLLARS
Project Name | MARGARITA ISLAND
Location | VENEZUELA
Description | Dual Fuel
Project Number | xxxxx
Prep by: | TG | Date | 2010-05-04 | DF UNIT #1 | 2010-09-06
Reviewed by | TE | Date |  | DF UNIT #2 | 2010-09-27
Approved by |  | Date |  | ACCEPTANCE | 4-0ct-10
BUDGET ITEM |  | MANHOURS | SUB-TOTALS | Markup | TOTALS
HOMEOFFICE START-UP |  | 56 | 3920 | 40% | 5488
HOMEOFFICE EXPENSES |  |  | 0 |  | 0
SUBTOTALS ON HOME OFFICE STARTUP |  | 56 | 3920 |  | 5488
FIELD START-UP S/T | S/T | 1160 | 103600 | 40% | 145040
FIELD START-UP O/T | O/T | 460 | 42600 | 40% | 59640
FIELD START-UP EXPENSES |  |  | 45637.2832 | 40% | 63892.1965
SUBTOTALS ON FIELD STARTUP |  | 1620 | 191837.2832 |  | 268572.1965
CRAFT START-UP SUPPORT | S/T |  | 0 |  | 0
| O/T |  | 0 |  | 0
SUBTOTALS ON CRAFT SUPPORT |  | 0 | 0 |  | 0
FUEL OIL/LIQUID FUEL AND WATER FLUSHES |  |  | 100390 | 40% | 140546
OFFICE EQUIPMENT |  |  |  |  | 0
START-UP SPARES |  |  | 30200 | 40% | 42280
START-UP TEST EQUIPMENT |  |  | 5000 | 40% | 7000
MOBILIZATION/DEMOBILIZATION |  |  | 28000 | 40% | 39200
SUBTOTALS ON STARTUP INDRECTS |  |  | 163590 |  | 229026
TOTAL PROJECT START-UP COSTS |  |  | 359347.2832 |  | 503086.1965

## START-UP SUPPORT
VENDORS, CONTRACTORS & MISC SUPPORT
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE | MONTH(S) | COST
1 | Specialty Contractor | [11 empty] | 6 | Local Supplier | Test Equipment |  | 1 |  | 2500 |  | 2 |  | 5000 | 11 | Speciatly Contractor
| Chemical Cleaning | Equip. Rental |  | 0 |  | LUMP SUM |  | 68000 |  |  |  | 0 |  | Test Equipment | [10 empty] | Performance Testing | Subcontractor |  | 2 (2X!) | 128500 |  | FALSE
|  | Support Labor |  | 0 |  | 2-6 Man teams |  | 0 |  |  |  | 0 | [15 empty] | 2X1 | 126500 |  | FALSE
| CRMS Code No xxxxx.xxx | Subcontractor |  | 0 |  | LUMP SUM |  | 150000 |  |  |  | 0 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx |  |  | 3X1 | 129000 |  | FALSE
|  | Demin Trailers |  | 0 |  | TRAILER |  | 8200 |  |  |  | 0 | [15 empty] | 3 (1X1) | 127000 |  | FALSE
|  | Setup Cost |  | 0 |  | LUMP SUM |  | 450000 |  |  |  | 0 | [15 empty] | 1X1 | 120000 |  | FALSE
| Total Cost | Waste Disposal |  | 0 |  | GAL |  | 0.65 |  |  |  | 0 |  | Total Cost | [10 empty] | Total Cost |  |  | S/Cycle | 80000 |  | FALSE
| 0 | [12 empty] | 5000 | [10 empty] | 0
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE | MONTH(S) | COST
2 | Specialty Contractor | Fills Flushing Oil |  |  |  | GAL |  | 6 |  |  |  | 0 | 7 | Specialty Contractor | Subcontractor |  |  | Lump Sum |  | 75000 |  | 0 |  | 12 | Project Support |  |  | VISIT | 5000 |  | 0
| FUEL LINE FLUSHES | Flush Kits |  |  |  | Kits |  | 15000 |  |  |  | 0 |  | Electrical Testing | [10 empty] | Site Vistiation
|  | Support Labor |  |  |  | 2-4 Man Teams |  | 0 |  |  |  | 0
| CRMS Code No xxxxx.xxx | Setup Cost |  | 1 |  | LUMP SUM |  | 100000 |  |  |  | 100000 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx
|  | Wste Dspsl/Splls |  | 600 |  | GAL |  | 0.65 |  |  |  | 390
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 100390 | [12 empty] | 0 | [10 empty] | 0
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE | MONTH(S) | COST
3 | Specialty Contractor | [11 empty] | 8 | Specialty Contractor | Subcontractor |  | 2X1 | 145000 |  |  |  |  | FALSE | 13 | Project Support |  | 4 | MOBE | 4500 |  | 18000
| Steam/Air Blows | Equipment Rental |  | 0 |  | Lump Sum |  | 5000 |  |  |  | 0 |  | Emmissions Testing |  |  | 3X1 | 165000 |  |  |  |  | FALSE |  | Mobilization/demobilization |  | 4 | DEMOBE | 2500 |  | 10000
|  | Subcontractor |  | 0 |  | Lump Sum |  | 150000 |  |  |  | 0 |  |  |  |  | 2 (2x1) | 225000 |  |  |  |  | FALSE
| CRMS Code No xxxxx.xxx | Set-up |  | 0 |  | Lump Sum |  | 450000 |  |  |  | 0 |  | CRMS Code No xxxxx.xxx |  |  | 1X1 | 180000 |  |  |  |  | FALSE |  | CRMS Code No xxxxx.xxx
|  | Equipment Rebuild |  | 0 |  | Lump Sum |  | 65000 |  |  |  | 0 |  |  |  |  | Simple | 120000 |  |  |  |  | FALSE
|  | Support Labor |  | 0 |  | 2-8 Man Teams |  | 0 |  |  |  | 0
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 0 | [12 empty] | 0 | [10 empty] | 28000
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTHS(S) |  | COST |  |  |  | QTY | TYPE | RATE | MONTH(S) | COST
4 | Local Supplier | Fax |  |  |  | RENTAL |  | 300 |  | 6 |  | 0 | 9 | Local Supplier | Filters |  | 4 | LS | 600 |  |  |  | 2400 | 14 | Not Used
| Office Equipment | Copier |  |  |  | RENTAL |  | 350 |  | 6 |  | 0 |  | Start-up Spares | Valve Rebuild Kits |  | 2 | LS | 15000 |  |  |  | 2800 |  | Later
|  | Radios |  | 12 |  | RENTAL |  | 300 |  | 6 |  | 21600 |  |  | Misc |  | 15 | LS | 25000 |  |  |  | 25000
| CRMS Code No xxxxx.xxx | Computers |  | 4 |  | RENTAL |  | 350 |  | 6 |  | 8400 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 30000 | [12 empty] | 30200 | [10 empty] | 0
|  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST | [5 empty] | QTY | TYPE | RATE | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE | MONTH(S) | COST
5 | Project Support |  | 0 |  | LS |  | 15000 |  |  |  |  | 0 | 10 | Local Suppliers | Turbine Lube Oil |  |  | GAL | 6 |  |  | 0 |  | 15 | Not used
| Soft Product Reproduction | [12 empty] | First Fills | Gycol |  |  | GAL | 6.36 |  |  | 0 |  |  | Later
[15 empty] | CO2 |  |  | GAL | 8.51 |  |  | 0
| CRMS Code No xxxxx.xxx | [12 empty] | CRMS Code No xxxxx.xxx | Hydgron |  |  | GAL | 3.25 |  |  | 0 |  |  | CRMS Code No xxxxx.xxx
[15 empty] | Wtr/Wstwtr chem |  |  | GAL | 3 |  |  | 0
[15 empty] | Blr Chemicals |  |  | GAL | 2.5 |  |  | 0
| Total Cost | [12 empty] | Total Cost | Hydraulic Oil |  |  | LBS | 4.31 |  |  | 0 |  |  | Total Cost
| 0 | [12 empty] | 0 | Oils & Greases |  |  | GAL | 4 |  |  | 0 |  |  | 0
[15 empty] | Ammoina |  |  | GAL | 0.3 |  |  | 0

## FIELD STARTUP
| Project Name |  | MARGARITA ISLAND | [41 empty] | Field Expenses |  | Per Diem Allowance |  | 250 | 7500
| Location |  | VENEZUELA | [8 empty] | FIELD OFFICE BUDGET
| Description |  | DUAL FUEL | [43 empty] | 90 Day Trip |  |  | 1400
| Job No. |  | xxxxx
| Prep by: |  | TG |  | Date
| Reviewed by |  |  |  | Date
| Approved by |  | 0 |  | Date | [41 empty] | Total Expenses per Man Month |  |  | 8900
| Period of Performance |  |  | Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | Total | Total
|  |  |  | Date | 2010-08-16 | 2010-08-23 | 2010-08-30 | 2010-09-06 | 2010-09-13 | 2010-09-20 | 2010-09-27 | 2010-10-04 | 2010-10-11 | 2010-10-18 | 2010-10-25 | 2010-11-01 | 2010-11-08 | 2010-11-15 | 2010-11-22 | 2010-11-29 | 2010-12-06 | 2010-12-13 | 2010-12-20 | 2010-12-27 | 2011-01-03 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-01-31 | 2011-02-07 | 2011-02-14 | 2011-02-21 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-28 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-04-25 | 2011-05-02 | 2011-05-09 | 2011-05-16 | 2011-05-23 | 2011-05-30 | 2011-06-06 | 2011-06-13 | Manhours | Cost
|  |  | Manhours | Rate |  |  |  | UNIT 1 |  |  | UNIT 2
1 | Senior Startup Manager |  | Normal | 125 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
2 | Startup Manager |  | Normal | 90 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
3 | Fld Startup Dir |  | Normal | 85 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
4 | Mechanical Lead |  | Normal | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [36 empty] | 320 | 24000
|  |  | Overtime |  |  | 20 | 20 | 20 | 20 | 20 | 20 | [37 empty] | 120 | 9000
5 | Mechaincal #2 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Mechanical #3 |  | Normal | 65 | [44 empty] | 0 | 0
6 |  |  | Overtime | [45 empty] | 0 | 0
7 | GE Mechanical Field Rep |  | Normal | 150 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
8 | Electrical Lead |  | Normal | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [36 empty] | 320 | 25600
|  |  | Overtime |  |  | 20 | 20 | 20 | 20 | 20 | 20 | [37 empty] | 120 | 9600
9 | Electrical #2 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
10 | Electrical #3 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
11 | GE Electrical Field Rep |  | Normal | 150 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
12 | I&C Lead |  | Normal | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [36 empty] | 320 | 24000
|  |  | Overtime |  |  | 20 | 20 | 20 | 20 | 20 | 20 | [37 empty] | 120 | 9000
13 | I&C #2 |  | Normal | 73 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
14 | GE I&C Field Rep |  | Normal | 165 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
15 | DCS Lead |  | Normal | 90 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
16 | DCS #2 |  | Normal | 80 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
17 | Controls Engineer |  | Normal | 150 |  |  | 40 | 40 | 40 | 40 | 40 | [37 empty] | 200 | 30000
|  |  | Overtime |  |  |  | 20 | 20 | 20 | 20 | 20 | [37 empty] | 100 | 15000
18 | [48 empty] | 0 | 0
[49 empty] | 0 | 0
19 | Shift Operator #1 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
20 | Shift Operator #2 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
21 | Shift Operator #3 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
22 | LOTO Coordinator |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
23 | T/O Coordinator |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Support Wage Rate |  | Total Normal Hours |  | 120 | 120 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160 | 103600
| EL S/T | 0 | Total Overtime Hours |  | 0 | 60 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 42600
| EL O/T | 0 | Total Startup Engineers |  | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 146200
| ME S/T | 0 | Electrcial Support S/T |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 0
| ME O/T | 0 | Electrcial Support O/T |  | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0
| I&C/DCS S/T | 0 | I&C-DCS support S/T |  | 80 | 80 | 160 | 160 | 160 | 160 | 160 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0
| I&C/DCS O/T | 0 | I&C-DCS support O/T |  | 0 | 40 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0
| Craft per Startup Engineer |  | Mechanical Support S/T |  | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 0
| Electrcial | 2 | Mechanical Support O/T |  | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0
| Mechanical | 4 | TOTAL CRAFT |  | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&c/DCS | 2
| Period of Performance |  |  | WEEK No. | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | Total | Total
|  |  |  | DATE | 2011-06-20 | 2011-06-27 | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | Manhours | Cost
|  |  | Manhours | Rate
1 | Senior Startup Manager |  | Normal | 125 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
2 | Startup Manager |  | Normal | 90 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
3 | Fld Startup Dir |  | Normal | 85 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
4 | Mechaincal #1 |  | Normal | 75 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
5 | Mechanical #2 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
6 | Mechainical #3 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
7 | Mechanical N/S |  | Normal | 150 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
8 | Electrical #1 |  | Normal | 80 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
9 | Electrical #2 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
10 | Electrical #3 |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Electrical N/S |  | Normal | 150 | [44 empty] | 0 | 0
11 |  |  | Overtime | [45 empty] | 0 | 0
12 | I&C #1 |  | Normal | 75 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
13 | I&C #2 |  | Normal | 73 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
14 | I&C N/S |  | Normal | 165 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
15 | DCS #1 |  | Normal | 90 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
16 | DCS #2 |  | Normal | 80 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
17 | DCS #3 |  | Normal | 150 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
18 | [48 empty] | 0 | 0
[49 empty] | 0 | 0
19 | Shift Operator #1 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
20 | Shift Operator #2 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
21 | Shift Operator #2 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
22 | Lead Trainer |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
23 | T/O & Safety |  | Normal | 70 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Support Wage Rate |  | Total Normal Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EL S/T | 46 | Total Overtime Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EL O/T | 69 | Total Startup Engineers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ME S/T | 44 | Electrcial Support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ME O/T | 66 | Electrcial Support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&C/DCS S/T | 54 | I&C-DCS support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&C/DCS O/T | 81 | I&C-DCS support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Craft per Startup Engineer |  | Mechanical Support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Electrcial | 2 | Mechaincal Support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mechanical | 4 | TOTAL CRAFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&c/DCS | 2
[46 empty] | Grand Total Normal Hours |  |  | 1160
[46 empty] | Grand Total Overtime Hours |  |  | 460
[46 empty] | TOTAL HOURS |  |  | 1620
| TOTAL FIELD STAFF BUDGET | [7 empty] | TOTAL FIELD SUPPORT BUDGET
|  | Field Wages Sub-Total |  |  |  | 146200 |  |  | Field Support Wages |  |  | S/T | 0 | [32 empty] | Total Support S/T Hours |  |  | 2960
|  | Overhead at 0 |  |  |  | 0 |  |  | Field Support Expenses |  |  | O/T | 0 | [32 empty] | Total Support O/T Hours |  |  | 1160
|  | Field Wages Total |  |  |  | 146200 |  |  | Field Support Expenses | [36 empty] | Total Support Hours |  |  | 4120
|  | Field Personnel Expenses |  |  |  | 45637.2832
|  |  |  | TOTAL BUDGET |  | 191837.2832 | [5 empty] | Total | 0