## Sheet1
ProEnergy- Alton, IL to Houston, TX
Rail project daily tracking report
Railcar # | Description | Origin | Destination | Route | Loaded / Empty | 2006-11-20 | Forecast | 2006-11-21 | Forecast | 2006-11-22 | Forecast | 2006-11-27 | Forecast | 2006-11-28 | Forecast | 2006-11-29 | Forecast | 2006-11-30 | Forecast | 11/30/2006 PM | Forecast | 2006-12-01 | Forecast | 2006-12-04 | Forecast | 2006-12-05 | Forecast | 2006-12-06 | Forecast | 2006-12-07 | Forecast | 2006-12-08 | Forecast | 2006-12-11 | Forecast | 2006-12-12 | Forecast | 2006-12-13 | Forecast | 2006-12-14 | Forecast | 2006-12-15 | Forecast | 2006-12-18 | Forecast | 2006-12-19 | Forecast | 2006-12-20 | Forecast | 2006-12-21 | Forecast | 2006-12-22 | Forecast | 2006-12-26 | Forecast | 12/26/06 *PM Report* | Forecast | 2006-12-27 | Forecast | 2006-12-28 | Forecast | 2006-12-29 | Forecast | 2007-01-02 | Forecast | 2007-01-03 | Forecast | 2007-01-04 | Forecast | 2007-01-05 | Forecast | 2007-01-08 | Forecast | 2007-01-09 | Forecast | ETA | Empty Spot Date | Scheduled Load date | Departure Date | Arrival Date | L | W | H | Weight (Lbs)
QTTX130716 | Turbine | Alton, IL | Houston, TX | UP / PTRA | L | Car arrived Calumet,IL 11/05/06 @ 1:52 am. | Spoke with the NS and they are in the process of looking for this lost car. Will get in contact with SRT to give me further information for scheduling once railcar is found. | Car arrived Calumet,IL 11/05/06 @ 1:52 am. | TXX to re-waybill the empty car to Wood River, IL. Norfolk Southern to provide further information for scheduling once railcar order is finalized. | Car arrived Calumet,IL 11/05/06 @ 1:52 am. | Spoke with the NS in Chicago and the car is lost and will begin to locate the car and create a departure schedule. | Car arrived Clearing,IL 11/26/06 @ 6:25 pm and was interchanged to the BRC. | Spoke to the BRC and is scheduled to interchange with UP tomorrow evening. ETA to be offered after interchange to UP. | Car arrived Proviso, IL 11/28/06 @ 3:45 am. | Car is scheduled to depart Proviso, IL 11/28/06 @ 9:00 pm. Scheduled to arrive Yard Center, IL 11/29/06 @ 7:00 am and depart 11/29/06 @ 9:00 am. ETA to Woodriver, IL 12/01/06 @ 1:15 pm. | Car arrived Proviso, IL 11/28/06 @ 3:45 am. | Car is rescheduled to depart Proviso, IL 11/29/06 @ 12:00 pm. Scheduled to arrive Yard Center, IL 11/29/06 @ 10:00 pm and depart 12/01/06 @ 9:00 am. ETA to the Wann Yard 12/04/06 @ 1:15 pm. | Car arrived Yard Center, IL 11/29/06 @ 10:15 pm. | Car is scheduled to depart Yard Center, IL 12/01/06 @ 9:00 am. Scheduled to arrive Valley Junction, IL 12/01/06 @ 10:15 pm and depart 12/04/06 @ 11:30 am. | Car is in transit, passed Villa Grove, IL 11/30/06 @ 1:45 pm. | Car is scheduled to arrive Valley Junction, IL 12/01/06 @ 10:20 pm for interchange to the ALS. | Car arrived Valley Junction, IL 11/30/06 @ 9:00 pm and was interchanged to the ALS. | Unable to make contact with the ALS short line RR. | Car arrived Valley Junction, IL 11/30/06 @ 9:00 pm and was interchanged to the ALS. | Unable to make contact with the ALS short line RR. Will advise on ETA as soon as we get scheduling from the ALS. | Car arrived Valley Junction, IL 11/30/06 @ 9:00 pm and was interchanged to the ALS. | Unable to make contact with the ALS short line RR. Will advise on ETA as soon as we get scheduling from the ALS. | Car arrived Valley Junction, IL 11/30/06 @ 9:00 pm and was interchanged to the ALS. | Still working to get in contact with the ALS RR to get a update on schedule. | Car arrived Wood River, IL 12/06/06 @ 5:00 pm on the UP. | Car arrived Wood River, IL Wann Yard 4 track 1. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car arrived Wann, IL Wann Yard 4 track 1 position 1. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car arrived Wann, IL Wann Yard 4 track 1 position 1. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car arrived Wann, IL Wann Yard 4 track 1 position 1. Edwards scheduled to start loading railcar on Friday morning. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car arrived Wann, IL Wann Yard 4 track 1 position 1. Edwards scheduled to start loading railcar on Friday morning. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car is loaded and tie-downs are in work. Should be complete by Friday or Saturday. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car is loaded and tie-downs are in work. Should be complete by today or Saturday. | Car is loaded and tiedowns are complete. | Waiting for inspection, and will be waybilled this afternoon. | Car is loaded and tiedowns are complete. | Load will be inspected this afternoon. | Car is loaded ,tied down and waybilled. | Car will be inspected and final measurements will be taken 12/21 a.m. | Car is loaded ,tied down and waybilled. | Car is in the process of getting inspected and measured this morning. Turbine to be re-tarpped with shrink material. | Car is loaded ,tied down and waybilled. | Waitng for the UP Mechanical Dept. to re-inspect car. Opened problem log# 82845 to expedite car. | Car is loaded ,tied down and waybilled. | On hold for high wide clearance review & scheduling. Will report again this afternoon with update. | Car is waybilled and inspected. | Car has been released from clearance hold and waiting for high wide scheduling. | Car is waybilled, inspected and cleared. | Car is scheduled to depart Wann, IL 12/29/06 @ 2:15 am.Scheduled to arrive Valley Junction, IL 12/29/06 @ 3:30 am and will be placed on High wide hold, for manual scheduling. | Car is waybilled, inspected and cleared. | Car is scheduled to depart Wann, IL 12/29/06 @ 2:15 am.Scheduled to arrive Valley Junction, IL 12/29/06 @ 3:30 am and will be placed on High wide hold, for manual scheduling. | Car arrived Valley Jct, IL at 7:00pm on the 28th. | Waiting for the ALS RR to assign car to outbound UP train. Will call back on 30th to get departure schedule. | Car arrived Pine Bluff, AR 1/01/07 @ 7:30 pm. | Car is scheduled to depart 1/03/07 @ 5:00 am, and arrive Houston, TX North yard 1/04/07 @ 6:00 am. | Car is in transit, departed Camden, AR 1/3/07 @ 8:17 am. | Car is scheduled to arrive Houston, TX North Yard 1/04/07 @ 6:00 am. | Car is in transit, passed Humble, TX 1/04/07 @ 12:23 am. | Car is scheduled to arrive Houston, TX North Yard 1/04/07 @ 4:40 pm. | Car arrived Houston,TX 1/04/06 @ 10:15 am. | Car is in Houston, TX in Yard 6 on track 308. Car is on high wide hold, waiting for scheduling. | Car interchanged to the PTRA at Houston,TX 1/06/07. | Car on PTRA track # 62 waiting for delivery to Siemens facility. Siemens must place order with PTRA before car placement. | Car interchanged to the PTRA at Houston,TX 1/06/07. | Car is in Yard 11 track 48 and has been updated to "Spot" at the Seimens facility. | [5 empty] | 34' | 13' | 15' 1" | 425000
KRL370361 | Generator | Alton, IL | Houston, TX | UP / PTRA | L | Car is in Houston, TX North yard 11/17/06 @ 7:45 pm. | Car is scheduled to depart Houston, TX 11/21/06 @ 4:00 pm. Scheduled to arrive Wann, IL 11/27/06 @ 1:15 pm. | Car is in Houston, TX North yard 11/17/06 @ 7:45 pm. | Car is scheduled to depart Houston, TX 11/21/06 @ 4:00 pm. Scheduled to arrive Little Rock, AR 11/22/06 @ 10:00 pm and depart 11/23/06 @ 6:00 pm. Scheduled to arrive Wann, IL 11/27/06 @ 1:15 pm. | Car is in Houston, TX Inglewood yard 11/22/06 @ 5:00 am. | Car is in Bad order status due to Accident Damage and is waiting to be sent to the Repair track. | Car is in Houston, TX Inglewood yard 11/25/06 @ 12:50 am. | Car is in Bad order status due to Accident Damage and is on repair track 503 in Yard 15. Waiting to be repaired. Locating replacement car. | Car is in Houston, TX Inglewood yard 11/25/06 @ 12:50 am. | Car should be repaired 11/29/06 @ 11:00 am. It was delayed due to heavy volumes of Bad ordered cars in the yard. | Car is in Houston, TX Inglewood yard 11/25/06 @ 12:50 am. | Car is scheduled to depart Houston, TX 11/30/06 @ 11:59 pm. Scheduled to arrive Spring, TX 12/01/06 @ 4:00 am and depart 12/02/06 @ 8:00 am. | Car is in Houston, TX Inglewood yard 11/25/06 @ 12:50 am. | Car is scheduled to depart Houston, TX 11/30/06 @ 11:59 pm. Scheduled to arrive Spring, TX 12/01/06 @ 4:00 am and depart 12/02/06 @ 8:00 am. | Car arrived Spring, TX 11/30/06 @ 10:30 am. | Car is scheduled to depart 12/01/06 @ 8:00 am. Scheduled to arrive Valley Junction, IL 12/02/06 @ 8:35 pm and interchange with the ALS. Then scheduled to change back to the UP 12/03/06 @ 8:35 am and depart 12/04/06 @ 11:30 am. Scheduled to interchange with the NS 12/05/06 8:00 pm. | Car arrived Spring, TX 11/30/06 @ 10:30 am. | Car is scheduled to depart 12/02/06 @ 8:00 am. Scheduled to arrive Valley Junction, IL 12/03/06 @ 8:35 pm and interchange with the ALS. . Scheduled to arrive Wann, IL 12/05/06 @ 5:30 to interchange with the NS. ETA Woodriver, IL 12/05/06 @ 8:00 pm. | Car arrived Valley Junction, IL 12/3/06 @ 9:00 am and was interchanged to the ALS. | Unable to make contact with the ALS short line RR. Will advise on ETA as soon as we get scheduling from the ALS. | Car arrived Valley Junction, IL 12/3/06 @ 9:00 am and was interchanged to the ALS. | Unable to make contact with the ALS short line RR. Will advise on ETA as soon as we get scheduling from the ALS. | Car arrived Valley Junction, IL 12/3/06 @ 9:00 am and was interchanged to the ALS. | Still working to get in contact with the ALS RR to get a update on schedule. | Car arrived Wann, IL 12/06/06 @ 4:55 pm on the UP. | Car arrived Wood River, IL Wann Yard 4 track 1. | Car arrived Wann, IL 12/07/06 @ 4:40 pm. | Car arrived Wann, IL Wann Yard 4 track 1 position 2. | Car arrived Valley Junction, IL 12/10/06 @ 12:00 pm on the ALS RR. | Spoke with the ALS and stated that UP would have to correct route. Called UP RR and opened Problem Log# 80490 to expedite railcar back to Wann, IL. | Car arrived Wann, IL 12/11/06 @ 8:30 pm. | Car arrived Wann Yard on a Team track waiting to be loaded. Edwards scheduled to start loading railcar on Tuesday. | Car arrived Wann, IL 12/11/06 @ 8:30 pm. | Car is scheduled to go to the track for securements and tiedowns for next week. | Car arrived Valley Junction, IL 12/12/06 @ 11:59 pm and interchanged to the ALS by mistake. | Union Pacific mistakenly sent to the ALS in Valley Junction, IL and is scheduled to interchange back to the UP RR on 12/15/06 @ 11:30 am. The ALS will try to get it back to the UP today. Problem Log# 81344 to expedite the car. | Car arrived Valley Junction, IL 12/12/06 @ 11:59 pm and interchanged to the UP. | Car has been interchanged back to the UP RR and is scheduled to be in Wann, IL 12/15/06 @ 12:30 pm. | Car arrived Wann, IL 12/15/06 @ 2:10 pm on the UP. | Car is scheduled to begin loading late today if not tomorrow. | Car arrived Wann, IL 12/15/06 @ 2:10 pm on the UP. | Car is "Spotted" 12/18/06 @ 3:30 pm in Yard 4 track 502 , waiting to be loaded. Scheduled to complete T/D late this afternoon and get inspected. | Car is loaded and tied down. Welding and final securements to be completed by this evening. | Car will be inspected and final measurements will be taken 12/21 a.m. | Car is loaded, tied down and secured. | Car is in the process of getting inspected and measured this morning. | Car is loaded ,tied down and waybilled. | Waitng for the UP Mechanical Dept. to inspect car. Opened problem log# 82845 to expedite car. | Car is loaded ,tied down and waybilled. | On hold for high wide scheduling. | Car is waybilled and inspected. | Car has been released from clearance hold and waiting for high wide scheduling. | Car is waybilled, inspected and cleared. | Car is scheduled to depart Wann, IL 12/29/06 @ 2:15 am.Scheduled to arrive Valley Junction, IL 12/29/06 @ 3:30 am and will be placed on High wide hold, for manual scheduling. | Car is waybilled, inspected and cleared. | Car is scheduled to depart Wann, IL 12/29/06 @ 2:15 am.Scheduled to arrive Valley Junction, IL 12/29/06 @ 3:30 am and will be placed on High wide hold, for manual scheduling. | Car arrived Valley Jct, IL at 7:00pm on the 28th. | Waiting for the ALS RR to assign car to outbound UP train. Will call back on 30th to get departure schedule. | Car arrived Pine Bluff, AR 1/01/07 @ 7:30 pm. | Car is scheduled to depart 1/03/07 @ 5:00 am, and arrive Houston, TX North yard 1/04/07 @ 6:00 am. | Car is in transit, departed Camden, AR 1/3/07 @ 8:17 am. | Car is scheduled to arrive Houston, TX North Yard 1/04/07 @ 6:00 am. | Car is in transit, passed Humble, TX 1/04/07 @ 12:23 am. | Car is scheduled to arrive Houston, TX North Yard 1/04/07 @ 4:40 pm. | Car arrived Houston,TX 1/04/06 @ 10:15 am. | Car is in Houston, TX in Yard 6 on track 308. Car is on high wide hold, waiting for scheduling. | Car interchanged to the PTRA at Houston,TX 1/06/07. | Car on PTRA track # 62 waiting for delivery to Siemens facility. Siemens must place order with PTRA before car placement. | Car interchanged to the PTRA at Houston,TX 1/06/07. | Car is in Yard 11 track 48 and has been updated to "Spot" at the Seimens facility. | [5 empty] | 39' 6" | 12' 10" | 13' 2" | 530000