## Sheet1
Pro Energy- Las Vegas, NV to Houston, TX
Rail project daily tracking report
Railcar # | Description | Origin | Destination | Route | Loaded / Empty | 2006-01-09 | Forecast | 2006-01-10 | Forecast | 2006-01-11 | Forecast | ETA | Empty Spot Date | Scheduled Load date | Departure Date | Arrival Date | L | W | H | Weight (Lbs)
QTTX130702 | Turbine | Las Vegas, NV | Houston, TX | UP | L | Finished Tie-downs today. | Car is scheduled to be inspected tomorrow. | Car is loaded, and tie downs are complete. | Inspection is scheduled for this morning. | Car is loaded, tied down, and inspected. | Loaded dimensions have been sent in to UP clearance group and being reviewed. Departure schedule will be offered after clearance approval. | [5 empty] | 34" | 12'11" | 15' 1" | 425000