## Sheet1
Pro Energy- Las Vegas, NV to Houston, TX
Rail project daily tracking report
Railcar # | Description | Origin | Destination | Route | Loaded / Empty | 2006-01-09 | Forecast | 2006-01-10 | Forecast | 2006-01-11 | Forecast | 2006-01-12 | Forecast | 2006-01-15 | Forecast | 2006-01-16 | Forecast | 2006-01-17 | Forecast | 2006-01-18 | Forecast | 2006-01-19 | Forecast | ETA | Empty Spot Date | Scheduled Load date | Departure Date | Arrival Date | L | W | H | Weight (Lbs)
QTTX130702 | Turbine | Las Vegas, NV | Houston, TX | UP | L | Finished Tie-downs today. | Car is scheduled to be inspected tomorrow. | Car is loaded, and tie downs are complete. | Inspection is scheduled for this morning. | Car is loaded, tied down, and inspected. | Loaded dimensions have been sent in to UP clearance group and being reviewed. Departure schedule will be offered after clearance approval. | Car is scheduled to depart Nellis Industrial Park, NV 1/12/07 @ 8:00 pm. | Car is scheduled to arrive Las Vegas, NV 1/12/07 @ 10:00 pm and depart 1/13/07 @ 3:45 am. Scheduled to arrive Arden, NV 1/13/07 @ 5:55 am and depart @ 8:00 pm. | Car arrived Arden,NV 1/15/07 @ 5:25 am. | Car is scheduled to depart Arden, NV 1/15/07 @ 8:00 pm. Car is scheduled to arrive Yermo, CA 1/16/07 @ 6:00 am and will be placed on High wide hold for scheduling. | Car arrived Yermo, CA 1/15/07 @ 11:20 pm. | Car is on high wide hold, waiting to be scheduled. | Car arrived Yermo, CA 1/15/07 @ 11:20 pm. | Car is scheduled to depart 1/18/07 @ 5:00 am. Scheduled to arrive West Colton, CA 1/18/07 @ 2:30 pm and will be placed on High wide hold for scheduling. | Car arrived Barstow, CA 1/18/07 @ 5:35 am. | Car is scheduled to arrive West Colton, CA 1/18/07 @ 11:55 am. The car will be placed on high wide hold, for a departure schedule. | Car arrived West Colton, CA 1/18/07 @ 11:00 am | The car is placed on high wide hold, for a departure schedule. | [5 empty] | 34" | 12'11" | 15' 1" | 425000